## Log of changes
REF NO. | TITLE AND DESCRIPTION | Proposer | STC/STCP Section to potentially be changed | PROGRESS UPDATE | Next Steps | Date raised as issue to the STC Panel | Date Change Proposal raised to the STC Panel | Route of change | REPORT TO THE AUTHORITY | IMPLEMENTATION [Date of Change]
TBC | Section K & EU Network Codes: HVDC (HVDC entered into force Sept 16 and changes to be implemented by Sept 18.) | ESO, Network Capability | Section K | Draft discussed at December panel, raised in Jan 19 | Proposal formal | 2018-12-01 | 2019-01-01 | TBC | TBC | TBC
TBC | Admin updates following RfG to check references to CC and ECC | ESO, Network Capability | STCPs | Verbal update at February Panel, aiming to raise it formally in March. | Discuss at February panel | 2019-01-01 | Future date | TBC | TBC | TBC
TBC | ECIT Extending Competition in Transmission | TBC | Multiple Sections (Likely to impact Sections B, C, D, E, F, G, H, J, K) | Ofgem driven change allowing other parties to construct/own onshore transmission assets. Not sure of any code changes. On hold till after legal sep? | TBC | Future date | Future date | TBC | TBC | TBC
TBC | SO/TO Funding Mechanism (STCP 11-3 & STCP11-4): O-TO Funding Mechanism: Likely changes as a result of Ofgem driven SO Funding mechanism for BSIS incentive scheme for Scottish TOs, discussed at the joint Ofgem/SO/TO Network Access Policy workgroup | SP Transmission |  | Consolidating final industry feedback before proposal in October | sign off by the Panel- date to be confirmed | Future date | Future date | TBC | TBC | TBC
TBC | Queue Management | ESO, CUSC team | TBC | We are currently engaging with the industry under the ENA Open Networks project Pdt 5 work group to align our approach with other industry parties. ENA will be rolling out a consultation to the industry on some initial thoughts by October. The final proposals will be published by Mar 19 after which we can look to modify the CUSC. So this mod is held off till Mar 19. | Waiting for CUSC changes first | Future date | Future date | TBC | N/A | TBC
TBC | New STCP for Network Output Measures (NOMS) | NGETO, Engineering and Asset team | TBC | TO Proposer to attend Jan 19 STC Panel to provide an update and first draft of new STCP | Proposer to present to panel | Future date | Future date | TBC | N/A | TBC
CM065-CM069 | Legal Separation STC Modifications | National Grid | Multiple Sections | National Grid to raise the STC Modifications and STCP's at the April 2018 Panel meeting. | Panel determination vote at the August Panel meeting | 2018-04-01 | 2018-04-01 | Standard route | TBC | 2019-04-01
PM0102-PM0103 | Legal Separation STCP Modifications | National Grid | Multiple Sections | National Grid to raise the STC Modifications and STCP's at the April 2018 Panel meeting. | sign off by the Panel- date to be confirmed | 2017-12-01 | 2018-04-01 | STCP Changes | N/A | 2019-04-01
CM063 | Force Majeure Definition | Balfour Beatty | Section J- Interpretations and Definitions | Proposal submitted to the March STC Panel. 1st WG Oct and 2nd WG held in Nov. Action on Ofgem to suggest best route forward alongside their own industry doc changes that include FM | Awaiting Ofgem feedback by end Dec | 2018-04-01 | 2018-04-01 | STC Change | TBC | TBC
STCP27-01 | System Performance Monitoring | ESO, Network Capability | STCP27-01 | Proposer is finalising Proposal Form. Raised at October Panel. | sign off by the Panel- date to be confirmed | 2018-07-01 | TBC | STCP Change | N/A | TBC
PM0104 | STCP09-1 NGET Legal Separation | National Grid | STCP09-1 | Raised and approved at the Panel meeting in August. | sign off by the Panel- date to be confirmed | 2018-07-01 | 2018-07-01 | STCP Change | N/A | 2019-04-01
PM0105 | STCP13-2 NGET Legal Separation | National Grid | STCP13-2 | Raised and approved at the Panel meeting in August. | sign off by the Panel- date to be confirmed | 2018-07-01 | 2018-07-01 | STCP Change | N/A | 2019-04-01
PM0106 | STCP19-3 NGET Legal Separation | National Grid | STCP19-3 | Raised and approved at the Panel meeting in August. | sign off by the Panel- date to be confirmed | 2018-07-01 | 2018-07-01 | STCP Change | N/A | 2019-04-01
TBC | Consequential modification as result of CUSC modifications; CMP288 ‘Explicit charging arrangements for customer delays and backfeeds’ and CMP289 ‘ Consequential change to support the introduction of explicit charging arrangements for customer delays and backfeeds via CMP288’ | ESO, CUSC Team | TBC | CMP288 and CMP289 are currently at Workgroup stage in the CUSC modifications process. Any further updates on the progression of these modifications will be rasied at the STC Panel. | TBC | TBC | TBC | TBC | TBC | TBC
TBC | Consequential modification as a result of CUSC modification CMP306 ‘Align annual connection charge rate of return at CUSC 14.3.21 to price control cost of capital’ | ESO, CUSC team | TBC | CMP306 is currently at Workgroup stage in the CUSC modifications process. Any further updates on the progression of these modifications will be rasied at the STC Panel. | TBC | TBC | TBC | TBC | TBC | TBC
TBC | STC Modification as a result of Ofgem decision on CM069 | Code Administrator, ESO | Section J- Interpretations and Definitions | Modification to be rasied at February's Panel as directed by the Authority in their decision letter for CM069. | TBC | 2019-01-01 | 2019-02-01 | STC Change | N/A | 2019-04-01

## Changes implemented
REF NO. | TITLE AND DESCRIPTION | Proposer | STC/STCP Section to potentially be changed | PROGRESS UPDATE | Next Steps | Date raised as issue to the STC Panel | Date Change Proposal raised to the STC Panel | Route of change | REPORT TO THE AUTHORITY | IMPLEMENTATION [Date of Change]
PM0097 | STCP18-1: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-1 | Draft Proposal sent to Code Admin for review | N/A | 2017-06-28 | 2017-06-28 | STCP Change | N/A | 2017-07-25
PM0098 | STCP18-4: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-4 | Draft Proposal sent to Code Admin for review | N/A | 2017-06-28 | 2017-06-28 | STCP Change | N/A | 2017-07-25
PM0094 | STCP18-2: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-2 | Implemented 23 May 2017 | N/A | 2017-03-29 | 2017-03-29 | STCP Change | N/A | 2017-05-23
PM0095 | STCP18-3: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-3 | Implemented 23 May 2017 | N/A | 2017-03-29 | 2017-03-29 | STCP Change | N/A | 2017-05-23
PM0096 | STCP08-02: Missing diagram in Appendix A (last change June 2009) | Caroline Wright Code Administrator | STCP08-2 | Implemented 7 June 2017 | N/A | 2017-05-31 | 2017-05-31 | STCP Change | N/A | 2017-06-07
PM0101 | STCP09-1: Proximity outage | National Grid | STCP09-1 | STCP09-1 was submitted to the March 2018 STC Panel meeting. | sign off by the Panel on 12 June 2018. STCP09-1 will be implemented on 25 June 2018 | 2016-05-25 | 2018-03-01 | STCP Change | N/A | 2018-06-25
PM0100 | STCP19-3: Checklist to be reviewed re embedded connections | National Grid | STCP19-3 | STCP19-3 was submitted to the March 2018 Panel. | sign off by the Panel on 12 June 2018. STCP19-3 wiil be implemented on 25 June 2018. | 2017-10-25 | 2018-03-01 | STCP Change | N/A | 2018-06-25
PM099 | SIF and LARF Methodology- STCP13-2 | National Grid | STCP13-2 | STCP13-2 was submitted to the March 2018 STC Panel meeting. | sign off by the Panel on 12 June 2018. STCP13-2 will be implemented on 9 July 2018. | 2017 | 2018-03-01 | STCP Change | N/A | 2018-07-09
CM064 | Schedule 4 | National Grid | Schedule 4 | Appeals window open until 25 June 2018 | Appeals window open until 25 June 2018. Pending no appelas CM064 will be implemented on 11 July 2018 | 2018-04-01 | 2018-04-01 | STC Change | N/A | 2018-07-11

## changes not being progressed
REF NO. | TITLE AND DESCRIPTION | Proposer | STC/STCP Section to potentially be changed | PROGRESS UPDATE | Next Steps | Date raised as issue to the STC Panel | Date Change Proposal raised to the STC Panel | Route of change | REPORT TO THE AUTHORITY | IMPLEMENTATION [Date of Change]
TBC | Review of Section B Governance: Review Governance arrangements to check fit for purpose and cover STCP approval process | Caroline Wright Code Administrator | Section B | Areas for inclusion being identified for review with National Grid's legal team | Legal confirmed no amendment needed - guidance note to be drafted. | Future date | Future date | TBC | TBC | TBC
TBC | Section K & changes from GC0075: Consequential changes from GC0075 Hybrid Static Compensators | TBC | Section K | TBC | TBC | Future date | Future date | TBC | TBC | TBC
| RW | TBC | STCP22-1: Single Scottish model for ETYS production. Being reviewed by the JPC Modelling Subgroup | TBC | STCP22-1 | STCP22-1 is under review by the JPC Modelling Sub Group. | TBC | Future date | N/A | STCP Change | N/A | TBC