## Slide 1: Implementation Options
There are 2 streams of work which need to be completed to implement the intent of the proposal
Regulatory
      Changing the ESO licence to enact the SQSS change (as a minimum)
      Changing the SQSS in line with Panel process
  Analysis and Recommendation for variations from SQSS baseline
    Agree content of Frequency Risk and Control Report
      Full process from consultation on methodology through to implementation of results will take 6 months
      An interim report based on single consultation cycle could be implemented in ~3 months
  The two work-streams could be de-coupled to facilitate faster implementation of the SQSS change
    PROS
      Modification timescales not constrained by production of the Frequency Risk and Control Report
      Implementation of Frequency Risk and Control Report outcome not restricted to modification and licence change timescales
      Regular (annual) process gives all stakeholders the opportunity to influence the outcome
    CONS
      Workgroup and Panel have to asses the proposal without knowing its precise effect

## Slide 2: Implementation Options
1 | Decoupled | 
2 | Coupled - Interim FRCR | 
3 | Coupled -Full FRCR | 
AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
Workgroup/Panel Process
Interim FRCR
Full FRCR
Licence Process
Workgroup/Panel Process
Interim FRCR
Licence Process
Workgroup/Panel Process
Full FRCR
Licence Process
Option 1A
Option 1B
Earliest Implementation of Proposal

## Slide 3: OPTION 1: Timeline for GSR027 (Process decoupled from analysis - the only analysis will be what has already been produced)
Milestone | Date | Milestone | Date
Workgroup Nominations (15 working days) | 29 April 2020 to 21 May 2020 | Panel sign off that Workgroup Report has met its Terms of Reference | 27 October 2020
Workgroup 1 (Introductions, understand the Modification and proposed solution and confirmation on Terms of Reference | 8 July 2020 | Code Administrator Consultation (15 Working Days) | 29 October 2020 to 19 November 2020
Workgroup 2 (Develop details of solution - a) housed where? b) review draft methodology and c) review proposed changes to SQSS legal text) | 28 July 2020 (9.30 -12.30) | Draft Final Modification Report (DFMR) issued to Panel (5 Working Days) | 23 November 2020
Workgroup 3 (Agree Workgroup consultation and solution including what analysis has been produced and agree how and when the full analysis will produced) | w/c 17 August 2020 | Panel undertake DFMR recommendation vote | 1 December 2020
Workgroup Consultation (15 working days) | 28 August 2020 to 21 September | Final Modification Report issued to Panel to check votes recorded correctly (5 Working Days) | 3 December 2020
Workgroup 4 - Assess Workgroup Consultation Responses and agree legal text | w/c 28 September 2020 | Final Modification Report issued to Ofgem | 11 December 2020
Workgroup 5 – Workgroup Vote | 12 October 2020 | Ofgem decision | TBC
Workgroup report issued to Panel | 19 October 2020 | Implementation Date | TBC

## Slide 4: OPTION 2: Timeline for GSR027 (Process + Interim Frequency Risk and Control Report - minimum analysis)
Milestone | Date | Milestone | Date
Workgroup Nominations (15 working days) | 29 April 2020 to 21 May 2020 | Panel sign off that Workgroup Report has met its Terms of Reference | 8 December 2020
Workgroup 1 (Introductions, understand the Modification and proposed solution and confirmation on Terms of Reference | 8 July 2020 | Code Administrator Consultation (15 Working Days [not including 24 December to 5 January 2021] | 10 December 2020 to 13 January 2021
Workgroup 2 (Develop details of solution - a) housed where? b) review draft methodology and c) review proposed changes to SQSS legal text) | 28 July 2020 (9.30 -12.30) | Draft Final Modification Report (DFMR) issued to Panel (5 Working Days) | 15 January 2021
Workgroup 3 (Analysis of scenarios) | w/c 24 August 2020 | Panel undertake DFMR recommendation vote | 25 January 2021
Workgroup 4 (Agree Workgroup consultation and confirm details of solution) | w/c 28 September 2020 | Final Modification Report issued to Panel to check votes recorded correctly (5 Working Days) | 27 January 2021
Workgroup Consultation (15 working days) | 9 October 2020 to 30 October 2020 | Final Modification Report issued to Ofgem | 4 February 2021
Workgroup 5 - Assess Workgroup Consultation Responses and agree legal text | w/c 9 November 2020 | Ofgem decision | TBC
Workgroup 6 – Workgroup Vote | 23 November 2020 | Implementation Date | TBC
Workgroup report issued to Panel | 30 November 2020 |  | 

## Slide 5: OPTION 3: Timeline for GSR027 (Process + Full Frequency Risk and Control Report - full analysis)
Milestone | Date | Milestone | Date
Workgroup Nominations (15 working days) | 29 April 2020 to 21 May 2020 | Panel sign off that Workgroup Report has met its Terms of Reference | 9 March 2021
Workgroup 1 (Introductions, understand the Modification and proposed solution and confirmation on Terms of Reference | 8 July 2020 | Code Administrator Consultation (15 Working Days | 11 March 2021 to 1 April 2021
Workgroup 2 (Develop details of solution - a) housed where? b) review draft methodology and c) review proposed changes to SQSS legal text) | 28 July 2020 (9.30 -12.30) | Draft Final Modification Report (DFMR) issued to Panel (5 Working Days) | 5 April 2021
Workgroups 3 to 8 (Analysis of scenarios) | w/c 24 August 2020, w/c 28 September 2020, w/c 26 October 2020, w/c 23 November 2020, w/c 14 December 2020 | Panel undertake DFMR recommendation vote | 13 April 2021
Workgroup 9 (Agree Workgroup consultation and confirm details of solution) | 11 January 2021 | Final Modification Report issued to Panel to check votes recorded correctly (5 Working Days) | 15 April 2021
Workgroup Consultation (15 working days) | 18 January 2021 to 8 February 2021 | Final Modification Report issued to Ofgem | 23 April 2021
Workgroup 9 - Assess Workgroup Consultation Responses and agree legal text | w/c 15 February 2021 | Ofgem decision | TBC
Workgroup 10 – Workgroup Vote | 22 February 2021 | Implementation Date | TBC
Workgroup report issued to Panel | 1 March 2021 |  |