## Prioritisation Stack for Panel
Grid Code - Prioritisation Stack |  |  |  |  | â | á
Control Total |  | 10 | [6 empty] | Enter Y or N or "-"
Position in stack | [5 empty] | Enter a date if relevant |  | Sum from panel members | Stakeholder/consumer Benefit | [5 empty] | Number of benefits impacted |  | As agreed by Panel |  | Modification status | Active/Inactive WG meetings
Change | This month | Last Month | Mod Number | Title | Modification Driver | Target Delivery Date | Rationale for Target Delivery Date | To be discussed? | Facilitating competition | Lower Bills | Environmental Impact | Reliability and safety | Quality of service | Society as a whole | Stakeholder / Consumer benefits | Cross Code Impacts | Strategic importance? | Age (Months) | Status | 2020-12-01 | Estimated number of meetings remaining | Alan Creighton | Alastair Frew | Christopher Smith | Guy Nicholson | John Harrower | Rob Wilson | Robert Longden | Roddy Wilson | Sigrid Bolik | Steve Cox/Grahame Vincent | Panel Comments on Prioritisation | Proposer Name | Proposer Organisation | Proposal raised | Complexity | Importance | Urgency
|  | 1 | GC0139 | Enhanced Planning Data Exchange to Facilitate Whole System Planning | System Planning |  |  | 0 | Y | N | N | N | N | N | 1 |  | - | 16 | WG Meeting | #REF! | An estimate of 3 or 4 meetings | [10 empty] | New modification presented at February Panel - deemed to be higher priority as implementation end of 2020 | Ian Povey | Electricity North West | 2020-02-10 | Medium While the fundamentals of the enhancements to the data are not inherently complex, facilitation of the mod is requiring a shift to using the Common Information Model format for data exchange (an Ofgem backed output of the Open Networks group project). This will require investment and IS resource at all DNOs and so discussions of that element alone will take an not-insignificant amount of time. Without the change in format for exchange of data, the proposed enhancements to data would result in a very costly and time-intensive outcome for all parties in processing such data through traditional means. | Medium The enhancements within this mod will ensure effective, coordinated, efficient planning of Networks moving forwards. As more renewables connect at distribution level, it is increasingly more important to ensure the most complete picture possible is understood by DNOs, IDNOs, and Grid when planning network infrastructure upgrades, and assessing new connections etc. It will also provide NGESO with greater confidence when considering grid stability and security. | Medium A great deal of background work has been put in by the Open Networks group, resulting in several related reports outlining the importance and impact. Ofgem are keen to see outputs from the ON project work streams, and industry is largely aligned with the need for these enhancements as swiftly as possible.
|  | 2 | GC0141 | Compliance Processes and Modelling amendments following 9th August Power Disruption | GB Compliance |  |  | 0 | N | N | N | Y | N | Y | 2 |  | - | 15 | WG Meeting | #REF! | 3 more meetings | [10 empty] | This proposal has been raised following instruction from the Authority following the 9 August investigation and therefore the Panel concluded that this work should be completed as soon as possible. | Mark Horley | National Grid ESO | 2020-03-11 | High. Updates to compliance testing and modelling process requirements further to Ofgem/BEIS reports on 9th August event. Particularly impactful for complex arrangements. Requires changes to OC, PC, CC, ESS, CP, ECP, DRC, and possibly sections of STC. Includes new five-year compliance repeat plan requirement. Likely to also result in STC changes, and an update to the DRC. Likely to be 6+ workgroups remaining. | High Direct result of Ofgem/BEIS Actions from 9th August. Failure to deliver in a timely fashion would leave ESO exposed to further scrutiny and appropriate consequences. Compliance testing and modelling standards would not be deemed robust enough without this review by the industry. | High. Given the complexity and importance, and the implications of the 9th August reports, timely progression of these mods is vital. With 4-6 workgroups estimated as remaining, we must ensure momentum is maintained within the ESO and wider industry.
|  | 3 | GC0138 | Compliance process technical improvements (EU and GB User) | GB Compliance |  |  | 0 | N | N | N | Y | N | Y | 2 |  | - | 16 | WG Meeting | #REF! | 3 more meetings | [10 empty] | Compliance modification to be aligned with GC0141. Work to be completed in line with GC0141 where possible. | Mark Horley | National Grid ESO | 2020-02-10 | High. Updates to compliance testing and modelling process requirements further to Ofgem/BEIS reports on 9th August event. Particularly impactful for complex arrangements. Requires changes to OC, PC, CC, ESS, CP, ECP, DRC, and possibly sections of STC. Includes new five-year compliance repeat plan requirement. Likely to also result in STC changes, and an update to the DRC. Likely to be 6+ workgroups remaining. | High Direct result of Ofgem/BEIS Actions from 9th August. Failure to deliver in a timely fashion would leave ESO exposed to further scrutiny and appropriate consequences. Compliance testing and modelling standards would not be deemed robust enough without this review by the industry. | High. Given the complexity and importance, and the implications of the 9th August reports, timely progression of these mods is vital. With 4-6 workgroups estimated as remaining, we must ensure momentum is maintained within the ESO and wider industry.
|  | 4 | GC0137 | Minimum Specification Required for Provision of Virtual Synchronous Machine (VSM) Capability | New Technologies |  |  | 0 | Y | Y | N | Y | Y | Y | 5 |  | Yes | 18 | WG Meeting | #REF! | WG report Stage (meetings concluded) | [10 empty] | New modification presented in February where the first meeting is already in place for early April 2020. | Matt Baller | National Grid ESO | 2019-12-04 | High Baseline specification being codified to provide clarity and confidence to participating parties and ESO of what services may be procured. Spec has undergone several iterations and is nearing completion. Discussions remain regarding the commercial elements alongside Stability Pathfinder Phase 2 service provision to ensure widespread inclusivity. Continuation of progress is necessary as implementation of this mod will further facilitate greater stability in the GB grid. | Mod facilitates a commercial service offering a variety of benefits including near-immediate response, reduction of RoCoF drop, instant frequency management/inertia, instant current injection, dynamic voltage support, and synchronising torque. Specification is almost complete, needs one more workgroup meeting before consulting. Service will heavily compliment stability pathfinder phase 2 service provision (being a shorter-term liquid market equivalent) Greatly. Will also provide new revenue streams and incentivise further investment in new plant for our customers/stakeholders. | High Mod has had significant interest and engagement, with Workgroups of circa 40 people contributing greatly to make this work. Must also not be too far out from Stability Pathfinder Phase 2 outcomes/tendering, as a level playing field is crucial for inclusivity. Momentum must be maintained.
|  | 5 | GC0117 | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of PGM requirements | Efficiency |  |  | 0 | Y | Y | N | Y | Y | Y | 5 |  | Yes | 33 | WG Meeting | #REF! | An estimate of 6 meetings remaining. | [10 empty] | New nominations email and presentation and GCDF to be completed ahead of work recommencing on this change. | Garth Graham | SSE Generation Ltd | 2018-06-01 | This is a simple quick win change, to harmonise on a set of plant sizes in GB. The Workgroup has met on a number of occasions and has come to the view that there are simply four options: namely to use the levels from one of the three existing onshore TO (NGET, SHE-T, SPT) or adopt a new level not based on one of the existing three. In the view of the proposer this is a simple change to harmonise on a set of plant size thresholds in GB. The effects of this which also apply across codes are however significant. The Workgroup had considered options based around the existing regional thresholds. | Generators connecting to and operating within the GB system are doing so based on three different levels which is inefficient, non-harmonised and leads to higher consumer costs. | This Modification was raised in June 2018 – we are now celebrating its second birthday. To complete the Workgroup consultation should require two more Workgroup meetings, followed by a further two Workgroup meetings to conclude the work on this Modification.
|  | 6 | GC0148 | Implementation of EU Emergency and Restoration Code Phase II | EU Compliance |  |  | 0 | N | N | N | Y | N | Y | 2 |  | - | 11 | WG Meeting | #REF! | Not started - 6 plus | [10 empty] | This change was not deemed to be as high a priority when compared to those above it currently. | Tony Johnson | National Grid ESO | 2020-07-12 | High The work is resource intensive covering some very large issues (Articles 15(5) - 15(8), 41 and 42(1)(2) and (5) and related Articles, outstanding issues from E&R Phase I (access to Non-CUSC Parties and Storage Unit performance under low frequency conditions and Distributed re-Start. All this needs to be done by December 2022. There is a lot to be done with no real room for slippage. | High There is considerable risk we may not get the mods in by December 2022. If however we manage to get all the mods in before this time it will resolve some very large issues which are to the wider benefit of GB. | High There is a considerable amount of work to be done. This can be managed through the current Grid Code Governance Process but any delay could make this very difficult.
|  | 7 | GC0146 | Solutions for frequency control of Power Park Modules | New Technologies |  |  | 0 | Y | N | N | N | N | N | 1 |  | - | 13 | WG Meeting | #REF! | Not started - 1 to 2 meetings required | [10 empty] | New modification presented at May 2020 Panel | Nicola Barberis Negra | Ørsted | 2020-05-12 | We believe this modification is not complex and small amount of works should be required to address the questions raised by NGESO and progress the NG modification further | The proposed change of the Grid code would allow developers to reduce the costs of their frequency controller design and this would ultimately provide a benefit (reduced costs) for the end consumer as the design would be cheaper | The sooner the change is accepted, the sooner developers can implement the change to their design and benefit for the larger flexibility in the Grid Code. Until the Grid Code change is not approved, developers will still be forced to opt for more expensive design solution, which in our view do not provide any additional benefit to the overall operation of the network
|  | 8 | GC0140 | Grid Code Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | Governance |  |  | 0 | Y | N | N | N | N | N | 1 |  | - | 15 | WG Meeting | #REF! | Not started - An estimate of 5 meetings remaining. | [10 empty] | A key change that should be progressed in a joint workgroup with CUSC. Time passed and should proceed as soon as possible to enable more innovation. | Phil Smith | National Grid ESO | 2020-03-11 | Medium. Not expected to be hugely resource intensive, as it is implementing something that’s already been done for BSC and DCUSA and has a good amount of guidance from Ofgem. It does need a new process to be developed though so there's some complexity. Medium impact for a few parties, including ESO's Code Admin team and Panel, but not expected to have big impacts across the industry. Joint workgroup with Grid Code may add complexity and to the number of workgroups needed. | Medium. It's important that this is done as it reflects CACOP Principle 14 ('to develop cross code processes, and identify and facilitate changes to their codes to support Ofgem’s innovation activities'). However, to date there doesn't appear to be significant push from industry for this to be progressed for CUSC (and Grid Code - it's a joint workgroup). | Low. We committed to raising this by the end of the last financial year which we've done. There's no set timeline that this needs to be delivered to, but we support it, it's also in the CACOP and encouraged by Ofgem, and will support customers who want to test new approaches so should not be delayed unnecessarily.
|  | 9 | GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes | Harmonisation |  |  | 0 | Y | N | N | N | N | N | 1 |  | - | 43 | WG Meeting | #REF! | ON HOLD | [10 empty] | This change was not deemed to be as high a priority when compared to those above it currently. | Garth Graham | SSE Generation Ltd | 2017-07-01 | This is a simple quick win change, to harmonise on a set of applicable Electrical Standards in GB. The Workgroup has met on a number of occasions and has come to the view that there are simply four options: namely to use the Electrical Standards from one of the three existing onshore TO (NGET, SHE-T, SPT) or adopt a new version not based on one of the existing three. | Generators are connecting to the GB system and procuring equipment based on three different standards which is inefficient, non-harmonised and leads to higher consumer costs. | This Modification was raised on 1st July 2017 – we are now a few days shy of its third birthday. To complete the Workgroup consultation should require two more Workgroup meetings, followed by a further two Workgroup meetings to conclude the work on this Modification.
|  | TBC | GC0151 | Grid Code Compliance with Fault Ride Through Requirements | System Planning |  |  | 0 | Y | N | N | Y | Y | Y | 4 |  | - | 2 | WG Meeting | #REF! | 4 | [11 empty] | Garth Graham | SSE Generation Ltd | 2021-06-23 |  |  | Granted urgency by Ofgem on 02 July 2021
Formulas:
Age (Months) = ROUND(SUM(NETWORKDAYS([Proposal raised],NOW())/25),0)
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A strategic modification is one that will result in or underpin a very significant development within the electricity industry but which, in terms of prioritisation, may not be subject to any particular delivery deadline.

## Prioritisation to be published
Grid Code - Prioritisation Stack
Mod Number | Previous Priority No: | New Priority No | Change | Panel Comments on Prioritisation | Proposer Name | Proposer Organisation | Proposal raised | Complexity | Importance | Urgency | Estimated number of meetings remaining | Title
GC0151 | TBC | 1 | - | This change was not deemed to be as high a priority when compared to those above it currently. | Garth Graham | SSE Generation Ltd | 2017-07-01 | This is a simple quick win change, to harmonise on a set of applicable Electrical Standards in GB. The Workgroup has met on a number of occasions and has come to the view that there are simply four options: namely to use the Electrical Standards from one of the three existing onshore TO (NGET, SHE-T, SPT) or adopt a new version not based on one of the existing three. | Generators are connecting to the GB system and procuring equipment based on three different standards which is inefficient, non-harmonised and leads to higher consumer costs. | This Modification was raised on 1st July 2017 – we are now a few days shy of its third birthday. To complete the Workgroup consultation should require two more Workgroup meetings, followed by a further two Workgroup meetings to conclude the work on this Modification. |  | Grid Code Compliance with Fault Ride Through Requirements
GC0139 | 1 | 2 | - | This proposal has been raised following instruction from the Authority following the 9 August investigation and therefore the Panel concluded that this work should be completed as soon as possible. | Mark Horley | National Grid ESO | 2020-03-11 | High. Updates to compliance testing and modelling process requirements further to Ofgem/BEIS reports on 9th August event. Particularly impactful for complex arrangements. Requires changes to OC, PC, CC, ESS, CP, ECP, DRC, and possibly sections of STC. Includes new five-year compliance repeat plan requirement. Likely to also result in STC changes, and an update to the DRC. Likely to be 6+ workgroups remaining. | High Direct result of Ofgem/BEIS Actions from 9th August. Failure to deliver in a timely fashion would leave ESO exposed to further scrutiny and appropriate consequences. Compliance testing and modelling standards would not be deemed robust enough without this review by the industry. | High. Given the complexity and importance, and the implications of the 9th August reports, timely progression of these mods is vital. With 4-6 workgroups estimated as remaining, we must ensure momentum is maintained within the ESO and wider industry. | An estimate of 6> meetings remaining. To be run concurrently with GC0138 | Enhanced Planning Data Exchange to Facilitate Whole System Planning
GC0141 | 2 | 3 | - | Compliance modification to be aligned with GC0141. Work to be completed in line with GC0141 where possible. | Mark Horley | National Grid ESO | 2020-02-10 | High. Updates to compliance testing and modelling process requirements further to Ofgem/BEIS reports on 9th August event. Particularly impactful for complex arrangements. Requires changes to OC, PC, CC, ESS, CP, ECP, DRC, and possibly sections of STC. Includes new five-year compliance repeat plan requirement. Likely to also result in STC changes, and an update to the DRC. Likely to be 6+ workgroups remaining. | High Direct result of Ofgem/BEIS Actions from 9th August. Failure to deliver in a timely fashion would leave ESO exposed to further scrutiny and appropriate consequences. Compliance testing and modelling standards would not be deemed robust enough without this review by the industry. | High. Given the complexity and importance, and the implications of the 9th August reports, timely progression of these mods is vital. With 4-6 workgroups estimated as remaining, we must ensure momentum is maintained within the ESO and wider industry. | An estimate of 6> meetings remaining. To be run concurrently with GC0141 | Compliance Processes and Modelling amendments following 9th August Power Disruption
GC0138 | 3 | 4 | - | New modification presented in February where the first meeting is already in place for early April 2020. | Matt Baller | National Grid ESO | 2019-12-04 | High Baseline specification being codified to provide clarity and confidence to participating parties and ESO of what services may be procured. Spec has undergone several iterations and is nearing completion. Discussions remain regarding the commercial elements alongside Stability Pathfinder Phase 2 service provision to ensure widespread inclusivity. Continuation of progress is necessary as implementation of this mod will further facilitate greater stability in the GB grid. | Mod facilitates a commercial service offering a variety of benefits including near-immediate response, reduction of RoCoF drop, instant frequency management/inertia, instant current injection, dynamic voltage support, and synchronising torque. Service will heavily compliment stability pathfinder phase 2 service provision (being a shorter-term liquid market equivalent) Greatly. Will also provide new revenue streams and incentivise further investment in new plant for our customers/stakeholders. | High Mod has had significant interest and engagement, with Workgroups of circa 40 people contributing greatly to make this work. Must also not be too far out from Stability Pathfinder Phase 2 outcomes/tendering, as a level playing field is crucial for inclusivity. Momentum must be maintained. | An estimate of 3 to 4 meetings remaining. | Compliance process technical improvements (EU and GB User)
GC0137 | 4 | 5 | - | This change was not deemed to be as high a priority when compared to those above it currently. | Garth Graham | SSE Generation Ltd | 2017-07-01 | High The work is resource intensive covering some very large issues (Articles 15(5) - 15(8), 41 and 42(1)(2) and (5) and related Articles, outstanding issues from E&R Phase I (access to Non-CUSC Parties and Storage Unit performance under low frequency conditions and Distributed re-Start. All this needs to be done by December 2022. There is a lot to be done with no real room for slippage. | High There is considerable risk we may not get the mods in by December 2022. If however we manage to get all the mods in before this time it will resolve some very large issues which are to the wider benefit of GB. | High There is a considerable amount of work to be done. This can be managed through the current Grid Code Governance Process but any delay could make this very difficult. | 6 plus | Minimum Specification Required for Provision of Virtual Synchronous Machine (VSM) Capability | At WG Report Stage
GC0117 | 5 | 6 | - | New modification presented at May 2020 Panel | Nicola Barberis Negra | Ørsted | 2020-05-12 | We believe this modification is not complex and small amount of works should be required to address the questions raised by NGESO and progress the NG modification further | The proposed change of the Grid code would allow developers to reduce the costs of their frequency controller design and this would ultimately provide a benefit (reduced costs) for the end consumer as the design would be cheaper | The sooner the change is accepted, the sooner developers can implement the change to their design and benefit for the larger flexibility in the Grid Code. Until the Grid Code change is not approved, developers will still be forced to opt for more expensive design solution, which in our view do not provide any additional benefit to the overall operation of the network | The working group hasn’t started yet, but we would expect a reduced number of meetings (1 or 2?) to be required, given the relatively simple issues raised by NGESO on the proposed changes to the Grid Code. | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of PGM requirements
GC0148 | 6 | 7 | - | New nominations email and presentation and GCDF to be completed ahead of work recommencing on this change. | Garth Graham | SSE Generation Ltd | 2018-06-01 | This is a simple quick win change, to harmonise on a set of plant sizes in GB. The Workgroup has met on a number of occasions and has come to the view that there are simply four options: namely to use the levels from one of the three existing onshore TO (NGET, SHE-T, SPT) or adopt a new level not based on one of the existing three. | Generators connecting to and operating within the GB system are doing so based on three different levels which is inefficient, non-harmonised and leads to higher consumer costs. | This Modification was raised in June 2018 – we are now celebrating its second birthday. To complete the Workgroup consultation should require two more Workgroup meetings, followed by a further two Workgroup meetings to conclude the work on this Modification. | An estimate of 6 meetings remaining. | Implementation of EU Emergency and Restoration Code Phase II
GC0146 | 7 | 8 | - | Ofgem made ESO aware of the issue on the basis that Article 35.1b of the Emergency Restoration code | Tony Johnson | National Grid ESO | 2020-05-12 | Low In terms of a solution this is comparatively straightforward. The aim is to provide clarity to the Grid Code so it is clear under what conditions the market would be suspended an how this maps to Article 35.1(b) of the EU Emergency and Restoration Code. There is another piece of work that needs to be completed which details how the TERRE market can be suspended. This element of work will be run in co-ordination with Elexon. | Low A high level solution has already been discussed with Elexon and Ofgem. There is general agreement on the principle although some further work is required on the detail. There not believed to be any material issues to customers or stakeholders. | Medium The work has been instigated specifically by Ofgem to ensure consistency with Article 35.1(b). There is also a need to ensure consistency with Elexon over TERRE Market suspension. | 2 | Solutions for frequency control of Power Park Modules
GC0140 | 8 | 9 | - | A key change that should be progressed in a joint workgroup with CUSC. Time passed and should proceed as soon as possible to enable more innovation. | Phil Smith | National Grid ESO | 2020-03-11 | Medium. Not expected to be hugely resource intensive, as it is implementing something that’s already been done for BSC and DCUSA and has a good amount of guidance from Ofgem. It does need a new process to be developed though so there's some complexity. Medium impact for a few parties, including ESO's Code Admin team and Panel, but not expected to have big impacts across the industry. Joint workgroup with Grid Code may add complexity and to the number of workgroups needed. | Medium. It's important that this is done as it reflects CACOP Principle 14 ('to develop cross code processes, and identify and facilitate changes to their codes to support Ofgem’s innovation activities'). However, to date there doesn't appear to be significant push from industry for this to be progressed for CUSC (and Grid Code - it's a joint workgroup). | Low. We committed to raising this by the end of the last financial year which we've done. There's no set timeline that this needs to be delivered to, but we support it, it's also in the CACOP and encouraged by Ofgem, and will support customers who want to test new approaches so should not be delayed unnecessarily. | An estimate of 5 meetings remaining. | Grid Code Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions
GC0103 | 9 | 10 | - | This change was not deemed to be as high a priority when compared to those above it currently. | Garth Graham | SSE Generation Ltd | 2017-07-01 | This is a simple quick win change, to harmonise on a set of applicable Electrical Standards in GB. The Workgroup has met on a number of occasions and has come to the view that there are simply four options: namely to use the Electrical Standards from one of the three existing onshore TO (NGET, SHE-T, SPT) or adopt a new version not based on one of the existing three. | Generators are connecting to the GB system and procuring equipment based on three different standards which is inefficient, non-harmonised and leads to higher consumer costs. | This Modification was raised on 1st July 2017 – we are now a few days shy of its third birthday. To complete the Workgroup consultation should require two more Workgroup meetings, followed by a further two Workgroup meetings to conclude the work on this Modification. |  | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes

## Drop Downs
Drivers | Consumer Benefits
Cross-Code Change | Lower bills
Efficiency | Reduced environmental damage
EU Compliance | Improved reliability and safety
GB Compliance | Better quality of service
Governance | Benefits for society as a whole
Harmonisation
New Markets
New Technologies
Ofgem-led/SCR
System Operability
System Planning
System Security
Transparency