## SO Lead
[5 empty] | Customer: |  | Anygen | Energisation of User Assets - Date: |  |  |  |  | 2005-03-01
[5 empty] | Connection Site: |  | Scotland | Synchronisation of User Assets - Date: |  |  |  |  | 2005-03-01
[5 empty] | Date of Bilateral/Construction Agreement: |  | 2001-01-01 | Metering Commissioning Date (Demand) |  |  |  |  | 2005-03-01 | The latest possible date for is the Energisation Date. | Connection Types
[5 empty] | Transmission Connection Asset Comm. Prog. Commencement Date: |  | 2005-01-15 | Completion Date |  |  |  |  | 2005-07-15 |  | Grid Entry Point | GEP
[5 empty] | Transmission Owner |  | SSE | [8 empty] | Grid Supply Point | GSP
[16 empty] | Licence-Exempt Generator | LEG
Compliance Monitoring Statement
[5 empty] | Part 1: | SO LEAD | [8 empty] | Notes and Comments, not for printed version:
[10 empty] | Connection: | GEP | [6 empty] | Timing of Approvals:
ONP Stage | Required pre: | CCCR part | Lead contact (1 = SO, 2 = TO) | Item Number | Information/Data and Activity Requirements | Code or Agreement Ref. | User Data Library Ref. | Required by TO | NGC Responsible Unit | Interim Approval |  | Final Approval |  |  | Applicable To (GEP, GSP or LEG) | Normal Lead Time | Date | Interim Approval | Final Approval | Comments
[10 empty] | Planned Date | Signature and Date | Planned Date | Signature and Date
Before Start of Commissioning:
1 | C | 1 | 1 | 2.01 | User Site Name (not in STCP19-3 CMS) | CC 5.2(f) |  | Yes | Customer Agreements | [5 empty] | GSP,GEP | BCA | 2001-01-01 |  | On BCA signature
1 | C | 1 | 1 | 2.03 | Confirm BCA/CONSAG technical issues in line with TOCA | BCA/CONSAG and TOCA |  | Yes | Customer Agreements | [5 empty] | All | BCA | 2001-01-01 |  | On BCA signature | CAM should ensure inal confirmation that BCA and CONSAG reflect requirements of TOCA before commissioning starts
2 | C | 2 | 1 | 1.2 | Detailed Planning Data | PC5.4 / PC4.4.2, PC.A.5 | 3 | Yes | Network Design | [5 empty] | All | BCA +28D | 2001-01-29 |  | within 28 days of BCA
2 | C | 2 | 1 | 1 | Gen Unit Outages/Output & Other User Equipment Outages | OC2, DRC Sched 3 | 4.1/4.2 | No | Operations and Trading, Planning | [5 empty] | All | BCA | 2001-01-01 |  | On BCA signature, pre-sync
1 | C | 0 | 1 | 18 | Legal Agreements (CUSC) |  | A.1 | Yes | Customer Agreements | [5 empty] | All | BCA | 2001-01-01 | Before Energisation | Before FON
1 | C | 0 | 1 | 2.5 | Commissioning Programme issued | CONSAG 2.10 | A.2 | Yes | Engineering Services | [5 empty] | GSP, GEP | CPCD-3M | 2004-10-15 |  | 3 months before CPCD
1 | C | 0 | 1 | 21.1 | User's Statement of Readiness to Commence Commissioning Programme | CONSAG 4.1 | A.3 | Yes | Customer Agreements | [5 empty] | GSP, GEP | Before CPCD | 2005-01-15 |  | Before Energisation
3 | C | 3 | 1 | 22 | Mandatory Services Agreement - to be entered | CUSC 1.3.3 | A.5 | No | Contracts & Trading | [5 empty] | GEP, LEG | CPCD-6M | 2004-07-15 |  | Normally before Energisation
Before Energisation:
1 | E | 1 | 1 | 16.1 | Exchange of Telephone Numbers for Joint System Incidents | CC5.2/OC9 & BCA 5.4 | 1.12 | Yes | Operations and Trading, Operational Performance. | [5 empty] | All | Energ - 8W | 2005-01-04 | not applicable | Before Energisation (synch for EMG)
2 | E | 2 | 1 | 14 | Grid Code Data - User System Data | PCA.4 DRC Scheds 5, 10,11 & 13 CONSAG 5.5 | 2.1.1 | Yes | Network Design | [5 empty] | GSP,GEP | Energ - 3M | 2004-12-01 | Before Energisation | Before FON
2 | E | 2 | 1 | 12 | Evidence of User Equipment compliance - Tariff Metering | CC.6.2.2.3.5 BCA F5 | 2.5 | No | Elexon | [5 empty] | All | Synch - 3M | 2004-12-01 | not applicable | Before Energisation (synch for EMG) | (Code requirement changed by DJC from STCP19-3)
[5 empty] | Registration of a new TSBP (where applicable) for demand and / or generation | BSCP25 | 2.5 | No | NGET / Elexon
2 | E | 0 | 1 | 21.2 | User confirmation of readiness for energisation |  | A.3 | Yes | Customer Agreements | [5 empty] | GSP, GEP | Before Energ | 2005-03-01 | not applicable | Before Energisation
2 | E | 0 | 1 | 20.1 | Codes for BMUs | (1) Scheme Team Process (2) BSCP15 | A.6 | No | Customer Agreements / O&T | [5 empty] | All | TCCD-30 wd | 2005-01-30 | not applicable | immediate on BCA signature, and before Energisation | BMU codes need to be agreed at BCA signature or earlier.
2 | E | 0 | 1 | 20.2 | National Grid (Transmission Company) BMU registration confirmation | BSCP15 | A.7 | No | Operations and Trading, Business Systems | [5 empty] | All | TCCD-5 wd | 2005-02-24 | not applicable | Before Energisation | Elexon can block energisation until units registered. User must become familiar with BM process (visit to Wokingham etc) CAM to facilitate.
2 | E | 2 | 1 | 15 | Connection Conditions Compliance Report Parts 1&2 | CONSAG 5.5 | User Data Library | Yes | Generator Dynamic Performance | [5 empty] | All | Energ-3M | 2004-12-01 00:01 | Before Energisation | Before FON
Before Synchronisation (ION):
1 | S | 3 | 1 | 40.3 | FAX machine and Tel No | CC6.5.9. BCA F5 Sched | 1.13 | Yes | IS Telecomms | [5 empty] | All | Synch - 3M | 2004-12-01 |  | before synchronisation
3 | S | 3 | 1 | 40.1 | Site Specific Technical, BCA App F5, evidence of compliance - Additional Communication Facilities e.g. EDL, EDT | CONSAG 8 & BCA App F5 | 2.6 | No | Operations and Trading, Performance | [5 empty] | All | Synch - 3M | 2004-12-01 |  | before synchronisation
3 | S | 3 | 1 | 40.2 | Physical Notification Submission | CC6.5.8 (a) BCA F5 Sched | 2.6 | No | IS Telecomms | [5 empty] | GEP,LEG | Synch - 3M | 2004-12-01 |  | before synchronisation
3 | S | 3 | 1 | 40.4 | Data Entry Terminals | CC6.5.8 (b) BCA F5 Sched | 2.6 | No | IS Telecomms | [5 empty] | GEP,LEG | Synch - 3M | 2004-12-01 |  | before synchronisation
2 | S | 2 | 1 | 33 | Grid Code Data - Generating Plant | PCA 5, OC 2, DRC Sched 1 & 2. CONSAG 5.5 | 3.1, 3.2 | Yes | Generator Dynamic Performance | [5 empty] | GEP,LEG | Synch - 3M | 2004-12-01 | before synchronisation | before FON
3 | S | 3 | 1 | 32 | Control Systems (Excitation and Governor) - evidence of compliance including suitability of generating plant data supplied | CC6.3, BCA App F5 | 3.1.2 | Yes | Generator Dynamic Performance | [5 empty] | GEP,LEG | Synch - 3M | 2004-12-01 | before synchronisation | before FON
3 | S | 3 | 1 | 31 | Pole Slipping Protection | CC6.2.2.3.4, SA App F5 | 3.5 | Yes | Generator Dynamic Performance | [5 empty] | GEP,LEG | Synch - 3M | 2004-12-01 | before synchronisation | before FON
2 | S | 0 | 1 | 21.3 | User Statement of Readiness to Use the GB Transmission System | CONSAG 5.5 | A.3 | Yes | Customer Agreements | [5 empty] | LEG | Charging Date - 3M | 2005-04-15 | not applicable | before synchronisation
3 | S | 0 | 1 | 39.1 | Users Familiarity with Balancing mechanism process. |  | A.8 | No | Operations and Trading, Business Systems | [5 empty] | All | Synch - 8W | 2005-01-04 |  | normally before synchronisation
3 | S | 0 | 1 | 36 | Ancillary Services Monitoring |  | A.9 | No | Generator Dynamic Performance | [5 empty] | GEP,LEG | Synch - 3M | 2004-12-01 |  | normally before synchronisation
3 | S | 3 | 1 | 34 | Connection Conditions Compliance Report (Interim) Part 3 | CONSAG 5.5 | User Data Library | Yes | Generator Dynamic Performance | [5 empty] | All | Synch - 3M | 2004-12-01 00:01 | before synchronisation
Before Final Operational Notification:
4 | X | 4 | 1 | 51.2 | Islanding Protection | CC 6.3.15 | 3.1 | Yes | Generator Dynamic Performance | [5 empty] | All | Synch +TBA | 2005-05-31 |  | before FON
4 | X | 4 | 1 | 50 | Compliance tests: Governor, AVR/PSS, CC 6.3.3 | CC 6.3.3 | 3.5 | Yes | Generator Dynamic Performance | [5 empty] | GEP,LEG | Synch + TBA | 2005-05-31 |  | before FON
4 | X | 4 | 1 | 51.1 | Reactive Capability tests | CC 6.3.2 CC 6.3.4 | 3.6.1 | Yes | Generator Dynamic Performance | [5 empty] | GEP,LEG | Synch + TBA | 2005-05-31 |  | before FON
[5 empty] | Fault Ride Through Compliance | CC 6.3.15 | 3.6.4 | Yes | Generator Dynamic Performance | [5 empty] | All | Synch +TBA | 2005-05-31 |  | before FON
4 | X | 4 | 1 | 52 | Connection Conditions Compliance Report (Final) | CC 6/CC 7 & SA 5 | User Data Library | Yes | Generator Dynamic Performance | [5 empty] | All | Synch +TBA+1 | 2005-06-01 |  | before FON
Note on I8: CoatD: Development version. Additions to 19-3 version: User site name, RISSP prefixes (in GC but not in 19-3 version); BCA/TOCA cross-chexk and Affected TO check 21-10e version: corect/modify CONSAG 5.5 refs

## TO Lead
[5 empty] | Customer: |  | Anygen | Energisation Date: |  |  |  |  | 2005-03-01
[5 empty] | Connection Site: |  | Scotland | Synchronisation Date: |  |  |  |  | 2005-03-01
[5 empty] | Date of Bilateral/Construction Agreement: |  | 2001-01-01 | Transmission Company Commissioning Date & Effective From Date (BSCP 15 terminology) |  |  |  |  | 2005-03-01 | The latest possible date for is the Energisation Date. | Connection Types
[5 empty] | Comm. Prog. Commencement Date: |  | 2005-01-15 | Completion Date: |  |  |  |  | 2005-07-15 |  | Grid Entry Point | GEP
[5 empty] | Transmission Owner |  | SSE | [8 empty] | Grid Supply Point | GSP
[16 empty] | Licence-Exempt Generator | LEG
Compliance Monitoring Statement
[5 empty] | Part 2: | TO LEAD | [8 empty] | Notes and Comments, not for printed version:
[10 empty] | Connection: | GEP | [6 empty] | Timing of Approvals:
ONP Stage | Required pre: C=Comm, E = Energ, S= Synch, X=FON | CCCR part | Lead contact No (1 = SO, 2 = TO) | Item Number | Information/Data and Activity Requirements | Code or Agreement Ref. | User Data Library Ref. | Required by NGC | TO Responsible Unit | Interim Approval |  | Final Approval |  |  | Applicable To (GEP, GSP or LEG) | Normal Lead Time | Planned Date | Interim Approval | Final Approval | Comments
[10 empty] | Planned Date | Signature and Date | Planned Date | Signature and Date
Before Start of Commissioning:
1 | C | 1 | 2 | 2.05 | RISSP Prefixes (not in STCP19-3 CMS) | CC 5.2(h) | 1.11 | Yes | [6 empty] | GSP,GEP | ??? | 2001-01-01 |  | TBA
1 | C | 1 | 2 | 2.1 | Safety Rules applicable during commissioning | OC8/CC5.2, TOCA | 1.2 | Yes | [6 empty] | GSP, GEP | BCA +3M | 2001-04-01 |  | Before Energisation
1 | c | 1 | 2 | 2.2 | Safety Rules applicable after commissioning | OC8/CC5.2 | 1.2 | Yes | [6 empty] | GSP, GEP | TBA | 2005-01-04 |  | Before Contract Takeover
1 | C | 1 | 2 | 3.1 | Local Safety Procedures applicable during commissioning | OC8, TOCA | 1.9 | No | [6 empty] | GSP, GEP | BCA +3M | 2001-04-01 |  | Before Energisation
1 | c | 1 | 2 | 3.2 | Local Safety Procedures applicable after commissioning | OC8 | 1.9 | No | [6 empty] | GSP, GEP | TBA | 2005-01-04 |  | Before Contract Takeover
1 | C | 1 | 2 | 2.3 | Safety Co-ordinators - confirmation of names, authorisation and competence | CC 5.2/OC 8 & TOCA | 1.10 | No | [6 empty] | GSP, GEP | Energ - 8W | 2005-01-04 | not applicable | Before Safety Rule Clearance
Before Energisation:
1 | E | 1 | 2 | 19 | Interface Agreements | CC7.6 | 1.1 | Yes | [6 empty] | GSP, GEP | Energ - 8W | 2005-01-04 |  | Before Energisation
2 | E | 2 | 2 | 16.2 | Evidence of LJRP 'miniplan' (if NGCESO do not require a substantive LJRP) | OC9 | 1.14 | Yes | [6 empty] | GSP/GEP | Energ - 8W? | 2005-01-04 |  | Before Energisation
1 | E | 1 | 2 | 17.5 | Evidence of DRZP 'miniplan' (if NGC do not require a substantive DRZP) | OC9 | ? | Yes | [6 empty] | GSP/GEP | Energ - 8W?? | 2005-01-04 |  | Before Energisation
1 | E | 1 | 2 | 17.1 | Local Switching Procedures | OC7.6 | 1.3 | Yes | [6 empty] | GSP, GEP | Energ - 8W | 2005-01-04 |  | Before Safety Rule Clearance
1 | E | 1 | 2 | 17.2 | Site Responsibility Schedules - Persons authorised to sign | CC5.2/CC7.3 TOCA | 1.5 | Yes | [6 empty] | GSP, GEP | Energ - 8W | 2005-01-04 |  | Before Safety Rule Clearance
1 | E | 1 | 2 | 17.3 | Site Responsibility Schedules - Exchange of Information for preparation | CC5.2, TOCA | 1.5 | Yes | [6 empty] | GSP, GEP | Energ - 8W | 2005-01-04 |  | Before Safety Rule Clearance
1 | E | 1 | 2 | 5 | Site Responsibility Schedules - Issue | CC5.2/CC7.3 | 1.5 | Yes | [6 empty] | All | Energ -3M | 2004-12-01 |  | Before Safety Rule Clearance
2 | E | 2 | 2 | 6 | Operation Diagrams and Gas Zone Diagram for the Connection Point (or equivalent User diagram for LEG) | CC5.2/CC7.4 TOCA | 1.6 | Yes | [6 empty] | GSP, GEP | Energ - 3M | 2004-12-01 |  | Before Energisation
1 | E | 1 | 2 | 11 | Site Common Drawings – to be agreed and exchanged | CC5.2/CC7.5 TOCA | 1.7 | Yes | [6 empty] | All | Energ -3M | 2004-12-01 |  | Before Safety Rule Clearance
2 | E | 2 | 2 | 35 | Control Telephony | CC6.5.2. TOCA | 1.8 | Yes | [6 empty] | All | Energ - 3M* | 2004-12-01 | Before Synchronisation | Before FON, after on-load checks
2 | E | 2 | 2 | 9 | Evidence of User's Equipment compliance - Operational Metering | CC6.2.2.3.5 | 2.4 | Yes | [6 empty] | GSP, GEP | Energ - 3M | 2004-12-01 |  | Before Enegisation
2 | E | 2 | 2 | 7 | Earthing | CC6.3.11 for GEP, CC6.4.2 for GSP. TOCA | 1.4 | Yes | [6 empty] | GSP, GEP | Energ -3M | 2004-12-01 | Before Energisation | After On-Load checks
2 | E | 2 | 2 | 8 | Protection of Interconnecting Connections | CC6.2.3.6.1 for GSP, CC6.2.2.3.1 for GEP. TOCA | 2.1.2 | Yes | [6 empty] | GSP, GEP | Energ - 3M | 2004-12-01 | Before Energisation | After On-Load checks
2 | E | 2 | 2 | 10 | Circuit Breaker fail | CC6.2.3.1.1(c) for GSP, CC6.2.2.3.1 for GEP. TOCA | 2.1.2 | Yes | [6 empty] | GSP, GEP | Energ - 3M | 2004-12-01 |  | Before Enegisation
2 | E | 2 | 2 | 13.2 | Fault Disconnection Facilities (from Transmission protection) | CC6.2.3.2(PES), TOCA | 2.1.2 | Yes | [6 empty] | GSP | Energ - 3M | 2004-12-01 |  | Before Energisation
2 | E | 2 | 2 | 23 | System Fault clearance times, Protection and Relay Settings | CC6.2.2.5 for GEP, CC6.2.3.4 for GSP. TOCA | 2.1.2 | Yes | [6 empty] | GSP, GEP | Energ - 3M | 2004-12-01 | Before Energisation | Before FON
[5 empty] | Harmonic distortion, flicker, NPS. (generation) | CC6.1.5-7, CC6.2.1.1, CC6.4.2 | 2.1.3 | Yes
3 | S | 3 | 2 | 30 | Before Synchronisation (ION): | [9 empty] | GSP, GEP | Synch - 3M | 2004-12-01 |  | Before Synchronisation - depends on facility
3 | S | 3 | 2 | 38 | Special Automatic Facilities (e.g. intertrip) | TOCA | 2.3 | Yes | [6 empty] | All | Synch -2M | 2005-01-01 |  | Normally before synchronisation
[5 empty] | Site Specific Technical, BCA App F5, evidence of compliance - System Monitoring | CC 6.6, TOCA | 2.7 | Yes
4 | X | 4 | 2 | 51.3 | Before Final Operational Notification: | [9 empty] | GSP | Synch + TBA | 2005-05-31 |  | BeforeFON, after on-load measurements
[5 empty] | Compliance Tests on Demands (harmonics, flicker etc) | CC6.1.5-7, CC6.2.1.1, CC6.4.2 | 2.8 | Yes