## Main Sheet
Stage | Engagement |  | May |  |  |  |  | June |  |  |  | Comments | Main Deliverables
|  | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27
Strategic Workshop | June Strategic Workshop with UK TSOs and UK Authorities | [10 empty] | To progress further on the UK position for DA CC. A view on the following: - What are the questions that the ESO considers when applying an NTC; - 70% Rule; - Technical Procedure Strawman Document; and - What's in scope and out of scope. | Agreement on these areas and finalise UK position. | bar: 2022-06-20
JESG | February JESG | [10 empty] | Purpose of the JESG sessions is to provide ongoing updates to wider industry stakeholders.
March JESG
April JESG | bar: 2022-04-25
May JESG Cancelled
June JESG | bar: 2022-06-13
UK TSO SteerCo | TSO SteerCo | bar: 2022-05-16
TSO SteerCo
Cross Border SteerCo | Cross Border SteerCo | bar: 2022-05-23
Cross Border SteerCo
Cross Border SteerCo | bar: 2022-06-27
UK TSO Workgroups | Weekly Workgroups | [10 empty] | Fortnighly progress discussions on the UK TSO deliverable for Capacity Calculation ahead of EU TSO discussion
Fortnightly Workgroups | bar: 2022-05-09
Fortnightly Workgroups
Fortnightly Workgroups | bar: 2022-06-06
Fortnightly Workgroups