## Slide 1: 18 May 2022 Online Meeting via Teams
CMP286/287

## Slide 2
WELCOME

## Slide 3
Objectives and Timeline
Paul Mullen – National Grid ESO Code Administrator

## Slide 4: Timeline for CMP286/287 V2 as of 24 February 2022
Milestone | Date | Milestone | Date
Workgroup 1 (re-education of proposal (including the Workgroup Consultation Responses) and solution (what has changed), agree timeline and review terms of reference) | 7 December 2021 | Code Administrator Consultation | 27 June 2022 to 18 July 2022
Workgroup 2 and 3 (finalise solution to be consulted on, flesh out impacts, review legal text, agree alternatives, agree Workgroup Consultation questions and finalise Workgroup Consultation) | 13 January 2022, 24 February 2022 and 23 March 2022 | Draft Final Modification Report (DFMR) issued to Panel | 21 July 2022
Workgroup Consultation (20 Working Days) | 6 April 2022 to 9 May 2022 | Panel undertake DFMR recommendation vote | 29 July 2022
Workgroup 4 - Assess Workgroup Consultation Responses and legal text | 18 May 2022 | Final Modification Report issued to Panel to check votes recorded correctly (5 working days) | 2 August 2022
Workgroup 5 – finalise solutions, review terms of reference, hold Workgroup Vote | 1 June 2022 | Final Modification Report issued to Ofgem | 10 August 2022
Workgroup report issued to Panel (5 working days) | 16 June 2022 | Ofgem decision | TBC – by 31 October 2022
Panel sign off that Workgroup Report has met its Terms of Reference | 24 June 2022 | Implementation Date | Effective Date: 1 April 2024 so needs to be implemented by 1 January 2023

## Slide 5
Outstanding Action Updates
Paul Mullen – National Grid ESO Code Administrator

## Slide 6
Action Number | Action | Owner | Due by | Status
1 | ESO and Transmission Owners to meet to identify STC / STCPs impacts | Richard Woodward, Victoria Macleod and Nicola White | 18 May 2022 | Open
2 | Share draft of legal text | Nicola White | 18 May 2022 | Open
3 | Provide view as to whether or not a licence change may be required for the Transmission Owners | Richard Woodward and Victoria Macleod | 18 May 2022 | Open

## Slide 7
Summary Of Workgroup Consultation Responses
Paul Mullen – National Grid ESO Code Administrator

## Slide 8
Discuss new points raised re: Workgroup Consultation Responses
All

## Slide 9
Workgroup Alternative
Nicola White – National Grid ESO

## Slide 10
Workgroup Alternative Vote
All

## Slide 11
Next Steps
Paul Mullen – National Grid ESO Code Administrator