## GCDF (hidden)
Mod Number | Title | Prioritisation | ESO codes interaction | Comments | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
GC0109 | Publication of the various GB electricity Warnings or Notices or Alerts or Declarations or Instructions or Directions etc., issued by or to the Network Operator(s). | 1 |  | FMR to be sent to Ofgem on 12 May 2021 | Apr: DFMR
GC0133 | Timely informing of the GB NETS System State condition | 2 |  | The Code Administrator Consultation was issued on 13 April 2021 and will close 5pm on 13 May 2021. | May: DFMR
GC0134 | Removing the telephony requirements for small, distributed and aggregated market participants who are active in the Balancing Mechanism | 3 |  | WG report approved by Panel. CAC issued on 07 May 2021 for one month | Apr: WG and WG REPORT; Jun: DFMR
GC0139 | Enhanced Planning Data Exchange to Facilitate Whole System Planning | 4 | STC | Next WG Meeting 17 May 2021 | May: WG; Jun: WG; Aug: WG; Sep: WG; Oct: WG REPORT; Dec: DFMR
GC0138/GC0141 | Compliance related to 9th August Event | 5 | STC | Subgroups working on Alternatives until 21 May 2021. WG Vote on 03 June 2021 | Apr: WG x2; Jun: WG and WG REPORT (x2); Aug: DFMR (X2)
GC0137 | Minimum Specification Required for Provision of Virtual Synchronous Machine (VSM) Capability | 6 |  | WG meetings planned for 10 and 28 May 2021 | May: WG x2; Jul: WG REPORT; Sep: DFMR
GC0117 | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of PGM requirements | 7 |  | WG meeting to restart on 19 May 2021 | May: WG; Jul: WG; Aug: WG; Sep: WG; Oct: WG; Nov: WG and WG REPORT; Jan: DFMR
GC0148 | Implementation of EU Emergency and Restoration Code Phase II | 8 |  | WG meetings to start in June 2021 |  |  | WG | WG | WG | WG | WG | WG | WG | WG REPORT |  | DFMR
GC0146 | Solutions for frequency control of Power Park Modules | 9 |  | Not prioritised by Panel
GC0140 | Grid Code Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | 10 |  | Not prioritised by Panel
GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes | 11 |  | Not prioritised by Panel
GC0149 | Grid Code changes to reflect the terms of the UK’s departure from the EU | N/A - No workgroup |  | Issue CAC this week for one calendar month | Jun: DFMR
Workgroups |  |  |  |  | 3 | 4 | 3 | 2 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0
Workgroup Reports |  |  |  |  | 1 | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0
DFMRs |  |  |  |  | 1 | 1 | 2 | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 1

## Sheet2 (hidden)
Mod Number | Title
GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes
GC0109 | Publication of the various GB electricity Warnings or Notices or Alerts or Declarations or Instructions or Directions etc., issued by or to the Network Operator(s).
GC0117 | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of PGM requirements
GC0126 | Implementing Profiled Stable Import and Export Limits, and reversing unimplemented aspects of GC0068
GC0133 | Timely informing of the GB NETS System State condition
GC0134 | Removing the telephony requirements for small, distributed and aggregated market participants who are active in the Balancing Mechanism
GC0137 | Minimum Specification Required for Provision of Virtual Synchronous Machine (VSM) Capability
GC0138 | Compliance process technical improvements (EU and GB User)
GC0139 | Enhanced Planning Data Exchange to Facilitate Whole System Planning
GC0140 | Grid Code Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions
GC0141 | User Compliance Processes and Modelling following 9th August Power Disruption
GC0144 | Alignment of Market Suspension Rights to the EU Emergency and Restoration Code Article 35.1(b)
GC0146 | Solutions for frequency control of Power Park Modules
GC0147 | Last resort disconnection of Embedded Generation – enduring solution
GC0148 | Implementation of EU Emergency and Restoration Code Phase II

## CUSC GC STC SQSS Workgroups
Mod Number | Prioritisation | ESO codes interaction | May | Jun | Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Comments
CMP315 and CMP375 | High | STC |  |  |  | WG | WG x2 |  | WG |  | WG |  | WG x 2 |  | WG | WG x 2 | WG REPORT |  | DFMR
CMP363/CMP364 | High |  | WG | WG | WG | WG | WG | [6 empty] | WG | WG and WG REPORT |  | DFMR
CMP373 | High |  | WG, WG REPORT and DFMR
CMP326 | Medium/High |  | DFMR
CMP316 | Medium/High | [5 empty] | WG | WG | WG x2 | WG | WG | WG | WG x 2 | WG | WG | WG REPORT | DFMR
CMP330/CMP374 | Medium/High | STC (CM079) | WG | WG | WG | WG | WG | WG x2 |  | WG x 3 | WG | WG | WG |  |  | WG | WG and WG REPORT |  | DFMR
CMP344 | Medium/High | [5 empty] | WG | [10 empty] | UPDATE re: Terms of Ref |  | DFMR | [5 empty] | Proposer carrying out analysis with some input/guidance from ESO. This needs to be then presented to a Workgroup.
CMP376 | Medium/High | STC | [5 empty] | WG |  | WG | WG | [7 empty] | WG x 2 | WG | WG | WG and WG REPORT | DFMR
CMP304 | Medium | [7 empty] | WG | WG |  | WG |  |  | WG | WG x2 | WG REPORT |  | DFMR
CMP288/CMP289 | Medium | STC | [8 empty] | WG | WG | WG |  | WG x2 | WG REPORT | DFMR
CMP286/CMP287 | Medium | STC | [7 empty] | WG | WG | WG | WG |  | WG | WG and WG REPORT | DFMR
CMP384 | Medium | [12 empty] | WG | WG | WG | WG | WG and WG REPORT |  | DFMR
CMP331 | Low/ Medium | [14 empty] | WG | WG | WG |  | WG x 2 |  | DFMR
CMP379 | Low/ Medium | [14 empty] | WG | WG | WG |  | WG x2 | WG and WG REPORT |  | DFMR
CMP291 | Low | [24 empty] | Reached out to Proposer on 5 November 2021 to discuss indicative timeline
CMP311 | Low | [24 empty] | No current plans from Proposer to seek re-start of this
CMP341 | Low | Grid Code | [23 empty] | No current plans from Proposer to seek start of this
CMP358/CMP359 | Low
CMP365 | N/A - No workgroup |  | DFMR
CMP308 | N/A - Workgroup phase passed |  | WG | WG | WG | WG REPORT (Special Panel 6 Aug) | DFMR (Special Panel 14 Sep)
CMP368/CMP369 | N/A - Workgroup phase passed |  | WG x 2 | WG x2 | WG x 3 | WG REPORT (Special Panel 6 Aug) | DFMR (Special Panel 14 Sep)
CMP370 | N/A - No workgroup | STC |  |  | DFMR
CMP371 | N/A - No workgroup |  |  | DFMR
CMP372 | N/A - No workgroup |  |  | DFMR
CMP377 | N/A - No workgroup | [5 empty] | DFMR
CMP378 | N/A - No workgroup | [5 empty] | DFMR
CMP328 | N/A - Workgroup phase passed | STC | WG | WG | WG | WG | WG and WG REPORT | DFMR
CMP300 | Workgroup Phase Completed | [7 empty] | WG x2* | UPDATE re: Terms of Ref |  | DFMR
CMP361/CMP362 | Workgroup Phase Completed |  | WG | WG | WG | WG |  | WG | WG x2 and WG REPORT |  |  | DFMR
CMP298 | Workgroup Phase Completed |  |  | WG | WG | WG | WG | WG | WG x2 |  | WG and WG REPORT |  | DFMR
CMP381 | Workgroup Phase Completed | [8 empty] | WG x 2 | WG REPORT and DFMR
CMP380 | N/A - No workgroup | [9 empty] | DFMR
CMP382 | N/A - No workgroup | [11 empty] | DFMR
CMP383 | N/A - No workgroup | [11 empty] | DFMR
CMP385 | To be withdrawn? and separate Mods to be re-raised | STC
CMP388 | To be presented at April 2022 Panel | [14 empty] | DFMR
CMP389 | To be presented at April 2022 Panel | [14 empty] | DFMR
CMP390 | To be presented at April 2022 Panel | [14 empty] | DFMR
TNUoS Taskforces | N/A
Workgroups | CUSC |  | 8 | 8 | 9 | 6 | 8 | 6 | 10 | 9 | 7 | 5 | 7 | 3 | 10 | 8 | 3 | 3 | 2 | 5 | 2 | 1 | 0 | 0 | 0
Workgroup Reports | CUSC |  | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 4 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0
DFMRs | CUSC |  | 3 | 2 | 1 | 0 | 4 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 3 | 6 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 0
GC0139 |  | STC | [5 empty] | WG |  |  |  |  | WG |  | WG | WG | WG | WG and WG REPORT |  | DFMR
GC0141 |  | STC |  |  | WG | WG | WG |  | WG | WG |  | WG | WG x 2 | WG | WG and WG REPORT |  | DFMR
GC0148 |  |  |  | WG | WG | WG | WG | WG | WG | WG | WG | WG | WG |  | WG x 2 | WG REPORT |  | DFMR
GC0156 | [13 empty] | WG | WG | WG | WG | WG | WG | WG | WG |  | WG x2 | WG | WG REPORT | Joint Workgroup with D Code
GC0117 |  | SQSS | WG |  |  |  | WG | WG | WG | WG |  | WG | WG | WG | WG | WG |  | WG | WG and WG REPORT |  | DFMR
GC0154 | [10 empty] | WG | WG | WG |  |  | WG | WG | WG x 2 and WG REPORT |  | DFMR
GC0155 | [11 empty] | WG |  |  |  | WG | WG | WG | WG and WG REPORT |  | DFMR
GC0146 | [9 empty] | WG | WG | WG |  |  |  | WG |  | WG | WG and WG REPORT |  | DFMR
Workgroups | Grid Code |  | 3 | 3 | 7 | 5 | 3 | 3 | 3 | 4 | 3 | 6 | 6 | 3 | 5 | 6 | 4 | 7 | 4 | 1 | 1 | 0 | 2 | 1 | 0
Workgroup Reports | Grid Code |  | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 1
DFMRs | Grid Code |  | 0 | 2 | 0 | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 3 | 0 | 0 | 0 | 0
CM076 | N/A - No workgroup |  |  | DFMR
CM077 | N/A - No workgroup |  | STC FORMAL PROPOSAL | DFMR
PM0119 | N/A - No workgroup |  |  | STCP Vote
CM078 (CMP328 consequential) | N/A - No workgroup | CUSC | [12 empty] | DFMR
CM079 (CMP330/374 consequential) | N/A as no prioritisation currently in STC | CUSC | [8 empty] | WG | WG | WG |  |  | WG | WG | WG and WG REPORT |  | DFMR
CM080 (CMP298 consequential) | N/A - No workgroup | CUSC | [13 empty] | DFMR
CM081 (Gender Neutral Mod) | N/A- No workgroup | [13 empty] | DFMR
Workgroups | STC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workgroup Reports | STC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DFMRs | STC |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
GSR028 (Gender Neutral Mod) | N/A- No workgroup | [13 empty] | DFMR
Workgroups | SQSS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workgroup Reports | SQSS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DFMRs | SQSS |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0