## Slide 1: Timeline for CMP304 V5 as of 11 January 2022
Milestone | Date | Milestone | Date
Workgroup 1 (re-education of proposal and solution, agree timeline and terms of reference) | 8 November 2021 | Code Administrator Consultation | 9 May 2022 to 30 May 2022
Workgroup 2 and 3 (finalise solution to be consulted on, agree alternatives and agree Workgroup Consultation questions) | 15 December 2021 and 1 February 2022 | Draft Final Modification Report (DFMR) issued to Panel | 16 June 2022 (CMP305 as well?)
Workgroup Consultation (15 Working Days) | 15 February 2022 to 8 March 2022 | Panel undertake DFMR recommendation vote | 24 June 2022 (CMP305 as well?)
Workgroup 4 - Assess Workgroup Consultation Responses and any alternatives + hold alternative vote | 24 March 2022 | Final Modification Report issued to Panel to check votes recorded correctly (5 working days) | 28 June 2022
Workgroup 5 – finalise solutions, review terms of reference, hold Workgroup Vote | 11 April 2022 | Final Modification Report issued to Ofgem | 6 July 2022
Workgroup report issued to Panel (5 working days) | 20 April 2022 | Ofgem decision | TBC (Note CMP305 as well)
Panel sign off that Workgroup Report has met its Terms of Reference | 29 April 2022 | Implementation Date | TBC