## Slide 1
WELCOME
GC0155
Clarification of Fault Ride Through Technical Requirements Meeting 4 25 July 2022 Online Meeting via Teams

## Slide 2: Agenda
Topics to be discussed | Lead
Welcome | Chair
Review of Actions Log | Chair Terry Baldwin / Bieshoy Awad
Review ESO plan for Overvoltage Requirements Workgroup Feedback / Discussions | Bieshoy Awad All
AOB & Next Steps | Chair

## Slide 3: Members / Alternates & Observers
Role | Name | Representing
Chair | Banke John-Okwesa | Code Administrator (ESO)
Technical Secretary | Ruth Roberts | Code Administrator (ESO)
Proposer | Terry Baldwin | NGESO
Workgroup Member | Alan Mason | Oceanwinds
Workgroup Member | Alan Creighton | Northern Powergrid
Workgroup Member | Alastair Frew | Drax Power Station
Workgroup Member | Andrew Larkins | Sygensys
Workgroup Member | Andrew Vaudin | EDF
Workgroup Member | Bieshoy Awad | NGESO
Observer | David Griffiths | RWE Generation UK, RWE Renewables
Observer | Fiona Williams | NGESO
Workgroup Member | Forooz Ghassemi | NGET
Workgroup Member | Frank Martin | Siemens
Workgroup Member | Fraser Norris | SSE
Workgroup Member | Garth Graham | SSE Generation
Workgroup Member | Isaac Gutierrez | Scottish Power
Observer | Mike Kay | Independent
Workgroup Member | Nicola Barberis Negra | Orsted
Observer | Owen Curran | Siemens
Workgroup Member | Priyanka Mohapatra | Scottish Power
Workgroup Member | Ryan Tumilty | SSE
Workgroup Member | Sean Gauton | Uniper Energy
Workgroup Member | Tim Ellingham | RWE Generation UK, RWE Renewables
Workgroup Member (Alternate) | Julie Richmond | Scottish Power
Workgroup Member (Alternate) | Martin Aten | Uniper
Workgroup Member (Alternate) | Sridhar Sahukari | Orsted
Workgroup Member (Alternate) | Tobias Siepker | Siemens
Authority Representative | Shilen Shah | Ofgem

## Slide 4
Timeline
Banke John-Okwesa – ESO Code Administrator

## Slide 5: Timeline for GC0155 (Pending Panel Approval)
Milestone | Date | Milestone | Date
Proposal Presented to Panel | 16 December 2021 | Workgroup 10 – Finalise solution(s) and legal text, agree that Terms of Reference have been met, Review Workgroup Report and hold Workgroup Vote | 14 March 2023
Workgroup 1 – Understand / discuss proposal and solution, note the scope and identify any possible alternative solutions, agree timeline and review terms of reference, agree next steps. | 10 February 2022 | Workgroup Report issued to Panel | 22 March 2023
Workgroup 2 – Refresher: review and agree timeline and Terms of Reference, Review/Develop solution(s) and legal text, identify/assess possible alternatives. | 07 June 2022 | Panel sign off that Workgroup Report has met its Terms of Reference | 30 March 2023
Workgroup 3 – Develop Solution(s), review of legal text and alternatives | 05 July 2022 | Code Administrator Consultation | 07 April 2023 – 07 May 2023
Workgroup 4 – ESO to present plan and next steps re Definition of Overvoltage Requirements following a Fault, agree on the proposed plan | 25 July 2022 | Draft Final Modification Report (DFMR) issued to Panel | 17 May 2023
Workgroup 5 – Review / assess on-going work on Overvoltage requirements | 23 August 2022 | Panel undertake DFMR recommendation vote | 25 May 2023
Workgroup 6 – Review / assess ongoing work on Overvoltage requirements | 07 September 2022 | Final Modification Report issued to Panel to check votes recorded correctly (5 working days) | 29 May 2023 – 02 June 2023
Workgroup 7 – Finalise Overvoltage requirements, consider / finalise alternatives, draft consultations questions | 15 November 2022 | Final Modification Report issued to Ofgem | 06 June 2023
Workgroup 8 – Finalise consultation questions, review consultation report | 19 January 2023 | Ofgem decision | TBC
Workgroup Consultation (15 Working Days) | 30 January 2023 – 17 February 2023 | Implementation Date | 10 working days after Ofgem decision
Workgroup 9 (Post Workgroup Consultation) – Review / assess Workgroup consultation responses and Workgroup Report. | 28 February 2023 |  | 

## Slide 6
Banke John-Okwesa – ESO Code Administrator
Review of Actions Log

## Slide 8
Workgroup
Review ESO plan for Overvoltage Requirements

## Slide 9
Terms of Reference
Banke John-Okwesa – ESO Code Administrator

## Slide 10: GC0155 – Terms of Reference
Workgroup Term of Reference | Location in Workgroup Report
Implementation and costs; | 
b) Review draft legal text should it have been provided. If legal text is not submitted within the Grid Code Modification Proposal the Workgroup should be instructed to assist in the developing of the legal text; and | 
c) Consider whether any further Industry experts or stakeholders should be invited to participate within the Workgroup to ensure that all potentially affected stakeholders have the opportunity to be represented in the Workgroup. Demonstrate what has been done to cover this clearly in the report | 
d) Consider Electricity Balancing Regulation (EBR) implications | 
e) Minor changes and clarifications to the existing Grid Code Fault Ride Through (FRT) requirements specifically but not limited to consideration of the following areas: i. Clarify instances where User plant is required to trip in order to clear transmission system faults ii. Amending requirements for generating maximum reactive current during faults where these may be unachievable for some generators iii. Amending post-fault active power requirements to consider whether generators at low load may have greater levels of oscillation than permitted iv. To consider clarifying and or defining requirements for over-voltage following a fault | 
f) Identify and address any cross code impacts on other codes especially Distribution Code (e.g. G99 requirements) | TBC

## Slide 11
AOB & Next Steps
Banke John-Okwesa – ESO Code Administrator

## Slide 12: ESO to consolidate Workgroup responses to Questionnaire Review of Over voltage requi