***STCP 11.4 Enhanced Service Provision***

***STC Procedure Document Authorisation***

|  |  |  |  |
| --- | --- | --- | --- |
| **Company** | **Name of Party  Representative** | **Signature** | **Date** |
| National Grid Electricity System Operator plc |  |  |  |
| National Grid Electricity  Transmission plc |  |  |  |
| SP Transmission plc |  |  |  |
| Scottish Hydro-Electric Transmission plc |  |  |  |
| Offshore Transmission Owners |  |  |  |
| Competitively Appointed Transmission Owners |  |  |  |

***STC Procedure Change Control History***

|  |  |  |
| --- | --- | --- |
| Draft 001 | 09/05/2016 | Initial draft prepared by MD |
| Draft 002 | 15/01/2017 | Update original draft - MD |
| Draft 003 | 27/03/2017 | Updates received from NGET & SHETL |
| Draft 004 | 17/05/2017 | Updates received from SPT, NGET & SHETL. Appendices also amended |
| Draft 004.1 | 25/05/2017 | Further updates received from SPT & NGET |
| Draft 004.2 | 07/08/2018 | Further comments from NGET & SHETL |
| Draft 004.3 | 29/09/2018 | Further comments from the NAP panel |
| Final | 08/10/2018 | All comments updated into document |
| Issue 001 | 01/04/2019 | Implementation |
| Issue 002 | 01/04/2021 | Incorporating PM0118 |
| Issue 003 | xx/xx/xxxx | CATO Go-Live version |

**1 Introduction**

***1.1 Scope***

1.1.1 This procedure describes the processes associated with the Electricity System Operator (ESO) buying a service from an Onshore Transmission Owner (TO), where this service will have been identified as having a positive impact in assisting the ESO in minimising costs on the GB Transmission network. This procedure reflects the requirements of NGESO’s Electricity Transmission Licence Special Condition 4.

1.1.2 This procedure will cover works associated with Commercial Operational services and Joint Works projects as defined in NGESO license special condition 4.

1.1.3 This procedure applies to the Electricity System Operator (ESO) and each Onshore Transmission Owner (TO) as defined in STC Section J Clause 3. For the avoidance of doubt this document, the TOs are:

* SP Transmission Plc
* Scottish Hydro Electric Transmission Plc
* National Grid Electricity Transmission Plc
* Competitively Appointed Transmission Owners

***1.2 Objectives***

1.2.1 The objective of this STCP is to specify the process and procedures associated with the ESO buying a service of a TO categorised as either a Commercial Operational Service (COS) or a Joint Works projects (JW), where that service is deemed to have a positive impact in assisting the ESO in reducing system operating costs e.g. constraint costs

1.2.2 To meet this objective, this process specifies the following:

* Information exchange required between the ESO and TO identifying projects where this process could apply
* Process associated with TO service provision “within year” (year 0)
* ESO responsibilities to record details of any service provision and costs submitted by the TO
* Responsibility of each TO in preparing and submitting details of the service they will provide and the costs involved
* Quarterly and end of year reporting by the ESO

**2 Key Definitions**

***2.1 The following definitions apply for the purposes of this document:***

2.1.1 **Commercial Operational Service (COS) as defined in NGESO SLC4J** and means a service provided to the ESO by National Grid Electricity Transmission plc, SP Transmission plc, Scottish Hydro Electric Transmission plc the purpose of lowering the overall costs associated with the procurement and use of balancing services by the ESO.

2.1.2 **Joint Works Project (JW) as defined in NGET SLC4J** and means where the ESO and the TO agree to a Commercial Operational Service so as to minimise costs on the national electricity transmission system when the costs are higher than £1,146,800 (in 2009/10 prices)

2.1.3 **Knock On Works** means an outage or works that will need to change as a direct or subsequent result of a COS or JW and which may or may not itself incur additional costs

2.1.4 **TO Commercial Operational Service Estimate** means a forecast of the estimated costs the TO would incur should they initiate a COS or JW on their Transmission network during Year 0 (See appendix B)

2.1.5 **TO Commercial Operational Service Provision Cost Estimate** means a pro-forma that will be completed by the ESO to request the TO to provide a TO Commercial Operational Service Estimate. (See appendix A)

**3 Procedure**

***3.1 Change to a TO’s Outage, Delivery Project or Project Design***

3.1.1 Changes to a TO’s outage program, project delivery method or project design may be requested by either the TO or ESO, if the change is deemed to reduce system operating costs and the TO’s change costs are acceptable to the ESO. This procedure is designed to be used in both the Long-Term Planning (year 1 – 6) and within year (year 0) timescales. The type of TO Commercial Operational Service offered may include, but is not limited to:

* Temporary bypass circuit breakers or circuits
* Off-line build rather than in-line build
* Temporary Intertripping schemes

3.1.2 Commercial Operational Service requests can be requested by either the ESO or the TO. The process by which any extra cost incurred by the TO for any service provided is described below.

***3.2 Within Year (Year 0) – Commercial Operational Service process***

3.2.1 The ESO or TO may request a Commercial Operational Service for any outage that is in the plan at week 49 of the year ahead stage or any outage accepted into the current year plan.

3.2.2 If any plan change is identified that will reduce overall system costs, the party raising the change shall contact the other party to discuss the potential change and, where appropriate, any options associated with the change. If following discussion between both parties, and if the TO incurs any extra costs for implementing the change a TO Commercial Operational Service Provision Cost Estimate shall be produced by the TO for submission to the ESO using the pro forma in Appendix A. If the ESO accepts the TO Commercial Operational Service Provision Cost Estimate the ESO will request the TO proceeds with the change request.

3.2.3 The TO will submit a **TO Commercial Operational Service Provision Cost Estimate** covering all relevant cost associated with the change request.

3.2.4 The TO shall submit a **TO Commercial Operational Service Provision Cost Estimate** to the ESO that shall be made up of the following forecasted cost:

* A forecast of the direct costs associated with the agreed outage change, project delivery change or design change
* A forecast of any administrative costs

***3.3 ESO & TO Payment Process*** – ***Within Year Changes***

3.3.1 Commercial Operational Service or Joint Work costs shall be cost reflective and the estimated costs will have been agreed between both parties prior to the outage change taking place. The estimated costs will have been submitted by a TO to the ESO via a **TO Commercial Operational Service Estimate** in the form of the pro-forma in appendix B. At the time of submission of the **TO Commercial Operational Service Estimate** the TO and the ESO will agree a date by which the TO shall submit the invoice

3.3.2 In accordance with STCP 13.1 Invoicing and Payment and Other Charges in Schedule 10 of the STC:

* The ESO shall provide a purchase order number to the TO when approving the Commercial Operational Service or Joint Work costs request
* The TO shall issue an invoice to the ESO quoting the appropriate ESO purchase order number
* The TO invoice will also quote the Unique Works Identifier Code used in the Commercial Operational Service or Joint Work costs Pro forma

3.3.3 On completion of the Commercial Operational Service or Joint Work the TO will despatch the invoice to recover the costs by the date agreed and specified in accordance with the **TO Commercial Operational Service Estimate.** All invoice dates will be no later than the 30th April immediately following the Financial Year for which the works relates and would normally be no later than 2 months after the latest date involving the Commercial Operational Service or Joint Work costs

***3.4 Planning Years (Year 1*** – ***6)*** – ***TO service provision Long Term process***

3.4.1 The Electricity System Operator or Transmission Owner in the Long Term planning phase may request a project design change, a project outage delivery change e.g. off line build rather than in line build or any other change to a program of work being carried out on a TO’s network that if designed and\or delivered differently from what was agreed at start of the RIIO-T1 period could produce significant system operating cost savings. Examples of these types of changes are listed below.

* Design changes to future proof the network that cannot be funded under the TO’s regulatory allowance
* Design changes – Offline build of key network nodes rather than inline build.
* Accelerated working by the TO – Compressing a 4-month outage into 3 months requires to be done in the long-term planning period.
* Building contingency circuits

3.4.2 Due to the complexity in delivering some of the examples shown in section 3.4.1 the costs submitted by the TO could be substantial therefore a Joint Works project will be triggered were costs are in excess of the COS term as defined in NGESO standard licence condition 4J. A Joint Works project will follow the process defined in NGET standard licence condition 4J which will require regulatory approval. If the costs are less than the COS value the ESO can sanction the spend.

3.4.3 A request by either party to investigate the possibility of a project \ outage change as described in section 3.4.1 can be made verbally or in writing with it formally being initiated via a TO Service Provision Proposal form as shown in the pro-forma in Appendix B

3.4.4 If any outage change, project delivery change or design change is identified by either the ESO or TO in the Long Term Planning time frames the party raising the change shall contact the other party to discuss the potential change and, where appropriate, any options associated with the change. If following discussion between both parties, and if the TO incurs any extra costs for implementing the change a **TO Commercial Operational Service Estimate** shall be

produced by the TO for submission to the ESO using the pro forma in Appendix B. If the estimated costs are less than the COS value and the ESO accepts the proposals the ESO will request the TO proceeds with the change request.

3.4.5 If the estimated costs are greater than the COS value the ESO shall inform OFGEM of the proposal and seek to gain their approval of the project change and a funding increase to the STCP 11.4 budget should it be required. If OFGEM agrees to the proposal the ESO will inform the TO and the TO will then proceed with the change request. Rejection of the proposal will be communicated back to the TO by the ESO along with an explanation from OFGEM

***3.5 ESO & TO Payment Process*** – ***Long Term Changes***

3.5.1 On completion of the works specified in the **TO Service Provision Cost Estimate** and in which the TO’s costs will have been identified the TO will submit an invoice

3.5.2 Commercial Operational Service or Joint Work costs shall be cost reflective and the estimated costs will have been agreed between both parties prior to the outage change taking place. The estimated costs will have been submitted by a TO to the ESO via a **TO Service Provision Cost Estimate** in the form of the pro-forma in appendix B. At the time of submission of the **TO Service Provision Cost Estimate** the TO and the ESO will agree a date by which the TO shall submit the invoice

3.5.3 In accordance with STCP 13.1 Invoicing and Payment and Other Charges in Schedule 10 of the STC:

* The ESO shall provide a purchase order number to the TO when approving the Commercial Operational Service or Joint Work costs request
* The TO shall issue an invoice to the ESO quoting the appropriate ESO purchase order number
* The TO invoice will also quote the Unique Works Identifier Code used in the Commercial Operational Service or Joint Work costs Pro forma

**4 Commercial Operational Service and Joint Works Cost Monitoring**

***4.1 TO***

4.1.1 Each TO shall monitor all variable Cost Estimates submitted by that TO to the ESO for which out-turn has not yet been achieved

4.1.2 Each month the TO shall inform the ESO in writing of any significant change or potential significant change to the Outage Change Cost Estimates. A significant change is a change that differs to the last value given to the ESO by the greater of either 10% of the previous value or a change in excess of £10000

***4.2 ESO***

4.2.1 The ESO shall maintain a record of all Commercial Operational Service and Joint Works requests made, Cost Estimates and Actual Costs.

***Appendix A:* TO Commercial Operational Service Provision Cost Estimate*.***

Date Issue No. **Page 1 of 1**

|  |  |  |
| --- | --- | --- |
| **Activity** | **Input Notes** | |
| **Works information - completed by NGESO** | | |
| Name of Requester |  | Name of NGESO engineer requesting the change |
| Unique Works Identification Code |  |  |
| Works description |  | Works description |
| Date |  | Date request made by NGESO |
| Service Provision |  | Description of the required service the ESO would like the TO to provide |
| Indicative delivery date and time |  | NGESO shall give indication of a new proposed start and end date of the Works |
| Any additional information |  | Any additional information that NGESO feel will be useful to enable the TO to cost the outage |
|  | | |
| **Receipt information - completed by TO** | | |
| Date received by TO |  | Date Works request received by TO |
| Name of TO Representative |  |  |
| TO reference number |  |  |

***Appendix B:* TO Commercial Operational Service Estimate**

**Service Cost Estimate (complete this section on page 1 only)**

**Date Issue No Page of**

|  |  |  |
| --- | --- | --- |
| From Name & Company |  | Name & Company of person submitting estimate |
| Unique Works Identification  Code |  |  |
| Works Cost Estimate | £ | Total cost of Works |
| Works Invoice date |  | Normally no later than 2 months after latest date involved in Works |

**Works Costs for**

|  |  |  |
| --- | --- | --- |
| **Activity** | **Input Notes** | |
| **Outage information - completed jointly by TO / NGESO** | | |
| Brief description of TO Service being provided |  |  |
| Date of the request |  | Date Works \ Service request made by NGESO |
| Unique Works Identification Code |  |  |
| **Cost information - completed by TO** | | |
| Total Works Costs | £ | Total TO cost of Works |
| **Decision information - completed by NGESO** | | |
| Date received by NGESO and by whom | NGESO | Date cost information received by NGESO and recipient name |
| Decision | Approve / Cancel \* | NGESO approve or cancel the Works |
| NGESO Order Number |  | Order number for approved Works |
| Confirmed to TO  Date and name (NGESO) | NGESO | Date decision confirmed to the TO and by whom |