## Slide 1
GC0159
Thursday 6th March 2023
Online Meeting via Teams
Welcome

## Slide 2
Modification Process
Catia Gomes – National Grid ESO Code Administrator

## Slide 3: Code Modification Process Overview
Decision
Consult
Refine solution
Raise a mod
Talk to us
Forums
Panels
Workgroups
(Workgroup Consultations)
Ofgem/Panel
Implement
Notes: We are on the “Refine Solution” phase

## Slide 4
Alastair Grey/Stephen Baker – NGESO
Proposer’s Update

## Slide 5
Review of Workgroup Report
Catia Gomes – National Grid ESO Code Administrator

## Slide 6
Terms of Reference
Catia Gomes – National Grid ESO Code Administrator

## Slide 7
Workgroup Term of Reference | Location in Workgroup Report (to be completed at Workgroup Report stage)
Implementation and costs; | 
b) Review draft legal text should it have been provided. If legal text is not submitted within the Grid Code Modification Proposal the Workgroup should be instructed to assist in the developing of the legal text; | 
c) Consider whether any further Industry experts or stakeholders should be invited to participate within the Workgroup to ensure that all potentially affected stakeholders have the opportunity to be represented in the Workgroup. Demonstrate what has been done to cover this clearly in the report; | 
d) Consider EBR implications; | 
e) Consider interactions and impacts on wider Grid Code modifications in particular GC0103, GC0117 and GC0156 modifications; and | 
f) Consider the alignment with cross code impacts and their timelines. | 
g) Ensure that the proposed Grid Code changes effectively implement the CATO regime in a proportionate manner, adopting minimum necessary change whilst also ensuring that the new arrangements are future proofed as much as possible. | 

## Slide 8
Timeline Review
Catia Gomes – National Grid ESO Code Administrator

## Slide 9: Timeline for GC0159 as at 6th of April 2023
Milestone | Date | Milestone | Date
Proposal Presented to Panel | 29 September 2022 | Workgroup Report issued to Panel (5 working days) | 18 August 2023
Workgroup Nominations | 03 October 2022 – 21 October 2022 | Panel sign off that Workgroup Report has met its Terms of Reference | 24 August 2023
Workgroup 1 – Understand / discuss proposal and solution(s), review and agree on Terms of Reference and Timeline, review cross code impacts, review analysis and agree next steps. | 3 November 2022 | Code Administrator Consultation | 04 September 2023 – 05 October 2023
Workgroup 2 – Refine solution(s), draft legal text and consider potential Workgroup Consultation questions | 8 December 2022 | Draft Final Modification Report (DFMR) issued to Panel | 16 October 2023
Workgroup 3 – Review Workgroup Consultation questions and finalise Workgroup Consultation | 11 January 2023 | Panel undertake DFMR recommendation vote | 26 October 2023
Workgroup Consultation | 25 January 2023 – 15 February 2023 | Final Modification Report issued to Panel to check votes recorded correctly (5 working days) | 30 October 2023 – 03 November 2023
Workgroup 4 – Review Workgroup Consultation responses, consider new points raised, refine solution, review legal text and discuss any potential alternatives | 2 March 2023 | Final Modification Report issued to Ofgem | 09 November 2023
Workgroup 5 – Finalise solutions (including legal text) and alternatives and hold alternative vote | 06 April 2023 | Ofgem decision | Q4 2023
Workgroup 6 – Finalise Workgroup Report and hold Workgroup Vote | 11 August 2023 | Implementation Date | 10 Working Days after Ofgem Decision

## Slide 10
 | 2022 |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  | 
Deliverable | .... July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Finalise defect list and develop solutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop mod proposal forms & submit to Code Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Establishment of work groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Workgroup engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Workgroup consultation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Code Administrator consultation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop and issue Final Modification Report to Ofgem |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Grid code
STC
SQSS
External workshop on ‘minded’ to positions
Raise Grid Code mods
Raise CUSC & STC mods
CUSC
Raise SQSS mods
POAP for all CATO mods
Notes: Alastair

## Slide 11
Ruth Roberts – National Grid ESO Code Administrator
Next Steps