## Deliverables Tracker
Role | Sub activity | Deliverable reference number | Deliverable name | Milestone Description | Milestone date | Milestone Status | Milestone completion date (quarter) | Deliverable commentary
1 | Ongoing activities | D1.1.1 | Balance Great Britain’s (GB) demand for energy with supply from generators around the clock | Meeting agreed metrics on balancing costs and security of supply. | Q4 2024-25 | Continuous activity |  | In Progress
1 | Ongoing activities | D1.1.2 | Maintain security of supply in real time and the ability to restart the system in the event of a partial or total loss of power | Meeting agreed metrics on balancing costs and security of supply. Carry out necessary work to meet GB restoration standard as described in A3.2. | Q4 2024-25 | Continuous activity |  | In Progress
1 | Ongoing activities | D1.1.3 | Maintain the integrity of the transmission network, while managing the economical operation of the system | Meeting agreed metrics on balancing costs and security of supply. | Q4 2024-25 | Continuous activity |  | In Progress
1 | Ongoing activities | D1.1.4 | Support development of new methodology under Trade and Cooperation Agreement and support European cooperation including and with the European Network of Transmission System Operators for Electricity (ENTSO-E) based on the outcome of Memorandum of Understanding (MoU) with ENTSO and CORESO based on the agreement with EU NRAs. Strategic relationships with European institutions are covered in Activity A21 Role in Europe. | Enhanced cooperation between EU and GB on electricity operation following EU-Exit. Support the development, delivery and implementation of new interconnector capacity calculation methodology. Maintain the delivery of the Day Ahead NG Security Analysis process in the NG control centre in preparation for future developments | Q4 2023-24 | Delayed - External Reasons |  | The Day Ahead Security Analysis process was being maintained in preparation for conclusion of ongoing capacity calculation methodology workstream. The capacity calculation methodology workstream is ongoing and NGESO has a preferred position but is still waiting for the EC to allow EU TSOs to engage with UK TSOs on this issue.
1 | Ongoing activities | D1.1.4 | Support development of new methodology under Trade and Cooperation Agreement and support European cooperation including and with the European Network of Transmission System Operators for Electricity (ENTSO-E) based on the outcome of Memorandum of Understanding (MoU) with ENTSO and CORESO based on the agreement with EU NRAs. Strategic relationships with European institutions are covered in Activity A21 Role in Europe. | Enhanced cooperation between EU and GB on electricity operation following EU-Exit. Support the development, delivery and implementation of new interconnector capacity calculation methodology. Maintain the delivery of the Day Ahead NG Security Analysis process in the NG control centre in preparation for future developments | Q4 2024-25 | Continuous activity |  | The Day Ahead Security Analysis process was being maintained in preparation for conclusion of ongoing capacity calculation methodology workstream. The capacity calculation methodology workstream is ongoing and NGESO has a preferred position but is still waiting for the EC to allow EU TSOs to engage with UK TSOs on this issue. In this interim period, there have been significant IT issues that have prevented the Day Ahead Security Analysis process from running and the costs to resolve were deemed to be too significant for the low value being realised from the process. This process has therefore been stopped but the ability to send IGM files required for any future capacity calculation methodology will remain so we are ready to participate whenever a methodology is agreed and implemented.
1 | Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being developed | Priority asset health improvements made to meet expectations as per the ESO Roles Guidance. Priority Control Centre user enhancements made to tools, including greater automation and upgrades to the bulk dispatch tool, to help meet efficient balancing expectations in the ESO Roles Guidance and improved stability situational awareness such as oscillation monitoring. Increased PMU location coverage and improved situational awareness. Replacement FATE system fully integrated with legacy balancing tools. | Q4 2023-24 | Complete | Q4 2023-24 | Legacy Dispatch Systems (Notable Features): •Complete: Jun23 (BM Release 3) Situational awareness improvements for utilisation of bi-directional units and fixes around bulk instruction/send of reason codes. •Complete: Jul23-ASDP (Release 14a) Dynamic Response enhancements to visualise contracted units Physical Notification data. •Complete: Sep23-ASDP (Release 15) Technical go live of the MW Dispatch service for NGED, asset health and control room improvements. •Complete: Sep23-BM (Interim Release 4) Upgrades and security patches. Inertia data integration for the decommissioning of EBS. •Complete: Dec23-BM (Release 4) Improving unit and constraint visibility and navigation, nuisance alarms, and process automation. Interfaces between BM & Open Balancing Platform (OBP), changes to dispatch to enable the Balancing Reserve (BR), and processes to BM to support decommissioning of EBS. •Complete: Dec23-ASDP (Release 16) Features of MW Dispatch for UK Power Network (UKPN), asset health and control room improvements. •Complete: Mar 24-BM Interim (Release 5) Code and hardware performance improvements, final process changes for EBS decommissioning, work to enable Greenlink commissioning and further changes to support BR dispatch. •Complete: Mar 24-ASDP (Release 17) UKPN MW dispatch technical go live, Dynamic Response enhancements for disarming, asset health and control room improvements. Network Control (Situational Awareness): Work ongoing to deliver oscillation monitoring within the new situational awareness tools. Offline analysis tools brought forward and are available for post event analysis. •New Oscillation situational awareness tool, Oscillation Guard Pro, delivered in 4 months providing indication of Scottish Oscillations is in use. Discussions are on going to widen this up to all GB later in FY25. •Access SSE production PMU data was established in January 2024, enabling additional data to be available. •Milestone completed.
1 | Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being developed | Priority asset health improvements made to meet expectations as per the ESO Roles Guidance. Priority Control Centre user enhancements made to tools, including greater automation and upgrades to the bulk dispatch tool, to help meet efficient balancing expectations in the ESO Roles Guidance and improved stability situational awareness such as oscillation monitoring. Increased PMU location coverage including potentially within DNOs. | Q4 2024-25 | Continuous activity |  | Legacy Dispatch Systems (Notable Features): •Complete: EBS Functional Migration and end of service •Complete: Jun24 (ASDP Release 18): Dynamic Response enhancements for disarming and MW Dispatch Service enhancements. •Future: Delay to Q2 2025 (BM Release 5): Dynamic Response enhancements for disarming, additional data provision to the Open Balancing Platform (OBP), performance improvements and Pathfinder enhancements. •Future: Release 19 - technical and asset health improvements Network Control (Situational Awareness): Replacement FATE went live May 2024 for an extended parallel run due to PMU availability. Increased PMU location coverage and improved situational awareness (Network Control) - Connection to NGET PMU data in late FY25 as their infrastructure is installed and continued development of the WAMS situational tools within the NCMS project, Extention of Oscillation Guard Pro across GB.
1 | Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually | Publish Operability Strategy Report | Q3 2023-24 | Complete | Q3 2023-24 | The report was published on the 28 Dec 2023. External comms followed w/c 8 Jan 2024. Webinar was held on 23 Jan. 89% learnt something new and scored the webinar 3.9/5
1 | Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually | Publish Operability Strategy Report | Q3 2024-25 | On track |  | Our annual process for producing and publishing the OSR begins in Q2 24-25.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Solar Power Product Implementation | Q1 2023-24 | Delayed - Internal Reasons |  | The initial phase of the Solar Power product has been successfully developed in BP1, delivering value to consumers. In BP2, our objective is to transition the existing product from the current ORACLE cloud solution to a strategic Azure cloud solution and complete the remaining feature delivery. This will be delivered In FY25. To ensure alignment with consumer value and business requirements, we have re-prioritised the forecasting roadmap/backlog through the cost monitoring framework (CMF). We now have an updated PEF strategy with a revalidated forecasting roadmap. This will accelerate the retirement of legacy forecasting systems (EFS, Operational PEF) and remove operational and business debt/risk while we deliver new and existing products and features on our strategic Azure cloud platform.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Wind Power & National Demand Product Implementation | Q4 2023-24 | Delayed - Internal Reasons |  | In order to enhance deliverability confidence for the milestones and address an error in the BP2 submission (two milestones as one), a reassessment has been conducted regarding the priority, size, and complexity of this milestone. As a result, the milestone has been split into two separate milestones. The target completion dates have been set as follows: 1. Wind Power Milestone: Q2-FY25 2. National Demand Milestone: Q4-FY25 Change requests, duly approved, have been processed through the cost monitoring framework (CMF) to ensure regulatory compliance. The ongoing work on the Wind Power product development is progressing, and we anticipate the completion of its initial phase by Q2-FY25 on the strategic Azure cloud platform Furthermore, the initial phase of the National Demand product has been successfully delivered during BP1, already providing value to consumers. Our objective is to transition this product from the current ORACLE cloud solution to a strategic Azure cloud solution and finalise the delivery of remaining features by Q4-FY25 in BP2. We now have an updated PEF strategy with a revalidated forecasting roadmap. This will accelerate the retirement of legacy forecasting systems (EFS, Operational PEF) and remove operational and business debt/risk while we deliver new and existing products and features on our strategic Azure cloud platform.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Integration with OBP and DAP (as far as possible) | Q4 2024-25 | On track |  | Discovery Work is in progress for integration of strategic PEF with the Open Balancing platform (OBP) PEF/DAP Integration has been temporarily de-coupled to re-validate needs and benefits in line with overall ESO Data strategy
1 | Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre | Delivery of a business continuity solution for trade capture and notification will allow trading to continue in the event that our primary systems became unavailable. Success looks like processes which are more robust and reliable, supported appropriately and automation is increased, reducing the risk of error occurring in manual processes. | Q4 2023-24 | Complete | Q4 2023-24 | Trading tool (Faradyn) now in place which reduces trade data entry errors. Common failure point (LIMS) being investigated for improvements with trade notifications. 25/3/24 We have confirmation that a major counterparty has the ability to notify on our behalf following a system failure (written in the GTMA). This means that we have a limited route to market following system failure.
1 | Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre | Delivery of a business continuity solution for trade capture and notification will allow trading to continue in the event that our primary systems became unavailable. Success looks like processes which are more robust and reliable, supported appropriately and automation is increased, reducing the risk of error occurring in manual processes. | Q4 2024-25 | Continuous activity |  | Trading tool (Faradyn) now in place which reduces trade data entry errors. Common failure point (LIMS) being investigated for improvements with trade notifications. 25/3/24 We have confirmation that a major counterparty has the ability to notify on our behalf following a system failure (written in the GTMA). This means that we have a limited route to market following system failure.Settlements changing internal reporting to display and changing GTMA with another 3 counterparties to carry out testing.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 8. Issued an end of Increment report on Earned Value and Progress. | Q1 2023-24 | Complete | Q1 2023-24 | Completed on 18 July as per original plan
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | First release of OBP to the Control Room. This will improve efficiency and reduce workload by enabling multi-dispatch instruction, which will reduce unit skips. Functionality for Real-Time Energy Balancing in OBP. First tranche of margin analysis in OBP. | Q3 2023-24 | Delayed - Consumer Benefits |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme enduring engagement events for our balancing transformation roadmap plan we have completed the deliverables against our existing plan. We have gone live with the Open Balancing Platform (OBP), small BMU unit zone and additionally included delivery of the battery zone, which was accelerated based on feedback from our enduring Balancing Programme engagement events. In addition, this now enables multiple zones to be dispatched by different roles in the control room - this area of functionality has been released earlier than originally planned. In agreement with the industry, the first tranche of margin analysis in OBP will be delivered as per our updated roadmap during Q4 2025/26. First tranche of margin analysis in OBP will be delivered in our roadmap during Q4 FY26
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Initial integration of OBP with the Data and Analytics Platform which will replace our long-term retention and analytics capability. Integration of unit contract data with OBP to ensure procured services are scheduled, optimised and available for dispatch. | Q4 2023-24 | Delayed - Consumer Benefits |  | OBP has prioritised the delivery of new services such as BM Quick Reserve and so delayed integration with DAP. OBP and DAP are now working on integration and designs.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Delivered functionality for Unit Pre-qualification, Contracts, registration in OBP. Predicted Generation Forecasting functionality in OBP. Provision of Meter, Market, Network, and constraints data for improved situational awareness in OBP. Integration with Ancillary Services Dispatch (ASDP): Ability for Open Balancing Platform to send and receive data via ASDP APIs to control points. | Q1 2024-25 | Delayed - Consumer Benefits |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme enduring engagement events for our balancing transformation roadmap plan we have completed the deliverables against our existing plan. Following prioritisation Interface to SMP and IEMS is due Q2 2024-25 Migration of ASDP will be in 2025
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Release of new National Optimiser (Modern Dispatch Algorithm (MDA)), reducing energy balancing costs. | Q3 2024-25 | Delayed - Consumer Benefits |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme enduring engagement events for our balancing transformation roadmap plan we are on track against our existing plan. In Q3 2024-25, We will deliver functionality to enable go-live of BM quick Reserve and we will bring forward a requirement as part of a staged set of activities to be able to issue manual instructions to enable more efficient architectural design of our suite of Balancing products. Delivery of MDA has therefore been reprioritised for the above activities and is now planned for delivery in Q1 2025-26.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Full integration with the training simulator, increasing effectiveness in the Control Room (note this is ongoing as new functionality in delivered in OBP it is added to the simulator). | Q4 2024-25 | On track |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme ensuring engagement events for our balancing transformation roadmap plan we are on track against our existing plan. OBP lite released in Q3 2023-24 has been integrated with the training simulator. Full integration of OBP strategic with the training simulator is on track for Q4 2024-25. In Q4 2024-25 additionally, we will delivery functionality to enable additional storage parameters to represent the energy available of these limited energy assets, build rule based Dispatch capability for Wind BM Units, Constraint Management and bulk-dispatch bid/offer instruction capability for Pumped Storage BM Units.
1 | Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Requirements Reports | Integrate inertia data with Data and Analytics Platform | Q4 2023-24 | Complete | Q3 2023-24 | Improvements to the DAP platform ingesting inertia data have been made enabling enhanced displays to be created as additional operational data is integrated into DAP. This milestone should have aligned with that shown in Annex 4 (DDT) of BP2 which is March 2024 and has delivered the improved integration ahead of this date. Continued enhancements will be made to dashboards to increase benefits to operational users.
1 | Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Requirements Reports | Integrate tools created with network control tool Inertia monitoring tools integrated with DAP and enhanced balancing capability | Q4 2024-25 | On track |  | These integrations are likely to be via DAP or Data Fabric and final delivery will align with the end project (OBP and Network Control / User console) priorities and timelines.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Look Ahead Iteration 1 / VSAT/OSA hosted in new DCs | Q1 2024-25 | Delayed - Internal Reasons |  | Delay is due to the vendor being unable to provide a build to ESO to install in our ESO Data Centres. As a mitigation sample Input Look Ahead data has been developed, work is ongoing with vendor to map this data for use in the Look Ahead toolset. VSAT/OSA environment strategy has been completed and procurement of necessary hardware is underway.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Look Ahead functionality running in Development Environments | Q2 2023-24 | Delayed - Internal Reasons |  | Dates to be revised to align with new Data Centre delivery dates. Not expected to knock-on to any other milestones
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Commence Build of Voltage Stability Analysis Tool (VSAT) and Online Stability Assessment (OSA) Tool Environments | Q3 2023-24 | Complete | Q3 2023-24 | Complete - awaiting Data Centre delivery.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Shadow Control Centre established Initial Data and Analytics Platform (DAP) integration | Q4 2023-24 | Delayed - Internal Reasons |  | Shadow Control facilities to be developed as part of the training suite for new NCMS with the option to develop further into a proposed FSO Contingency Control Centre post-project completion. DAP integration PoC due in Q3 24-25 and NCMS training simulator due Q4 24-25. The delivery plan for this milestone has been revised to accommodate the re-baseline of DAP and NCMS delivery plans and also to consider the new requirements for an FSO Contingency Control Centre
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | NGET receiving RTU Data DAP & balancing integration | Q2 2024-25 | Delayed - Consumer Benefits |  | NGET SCADA delivery has been delayed and the need for NGET to receive RTU Data has now been re-prioritised to Q1 2025-26 to align with NGET revised plan. DAP integration proof of concept is underway with a target date of Q3 2024-25. The timeline for this has moved to align with the NCMS GridOS pivot plan. Sample files have been received from Balancing – with a revised integration target date Q4 2024-25 to align to the latest plan Consumer benefit is realised by re-baselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Serial RTU connections removed | Q3 2024-25 | On track |  | RTU PoC in progress with third parties, expected outcome Jan 24 - this milestone delivery will be dependent on both ESO and NGET progress with their respective SCADA replacement deliveries. April 24 - The RTU PoC is still ongoing (was delayed whilst Vodafone engagement took place) This PoC is now expected to complete in August 2024.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Deliver integrated network control tool (inc VSAT & Look Ahead OSA), including its specific digital twin | Q4 2024-25 | Delayed - Consumer Benefits |  | Date to be changed to October 25 following a rebase line of plan that has taken place to understand the impact of GE product pivot to new GridOS technology. Consumer benefit is realised by re-baselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process.
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Common Information Model (CIM) Integration Requirements Complete | Q3 2023-24 | Complete | Q2 2023-24 | CIM model integration requirements completed and aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Integrate with enhanced balancing tool | Q4 2023-24 | Delayed - Internal Reasons |  | Reviewed against latest NCMS and Balancing delivery plans and integration target date is now September 2024. No anticipated knock-on to other milestones. Delay is caused by a few internal factors: - - NCMS Pivot to GridOS - the focus on the pivot to GridOS from an NCMS perspective has meant the integration work with OBP (enhanced balancing tool) has been re-prioritised. - Due to the complexity of both the NCMS and OBP toolsets, requirement development for the interfaces and functionality to be shared between the two tools has taken longer than expected and is still ongoing in a number of areas (for example Constraint Visualisation). A high level plan for delivery of the integrations between NCMS and OBP are now in place.
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Common Information Model (CIM) Integration Complete | Q3 2024-25 | On track |  | CIM model integration aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Integrate with Network Control Management System (NCMS) | Q4 2024-25 | On track |  | Integration aligned with NCMS product delivery plan.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Complete UI/UX requirements for ENCC Operator Console | Q1 2023-24 | Complete | Q1 2023-24 | User requirements completed and design is now underway.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Design Phase | Q2 2023-24 | Complete | Q2 2023-24 | User requirements completed and conceptual solution architecture is complete and now informing the procurement of the solution
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Build | Q3 2023-24 | Complete | Q3 2023-24 | Awaiting outcome of procurement activities
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Scope requirement and start design of video walls | Q4 2023-24 | Complete | Q4 2023-24 | User Requirements have been gathered and EPRI work has been completed. Solution procurement strategy now identified with design work underway.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Solution Testing | Q1 2024-25 | Delayed - Internal Reasons |  | User requirements completed and now entering procurement phase for new hardware and software. PQQ in final draft. Proof of Concept Desk deployed
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | ENCC Operator Console build complete. Move to implementation and enhanced testing | Q3 2024-25 | On track |  | User requirements completed and now entering procurement phase for new hardware and software. PQQ in final draft. Proof of Concept Desk deployed
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Development and testing of user experience tools and video walls | Q4 2024-25 | On track |  | User requirements completed and now entering procurement phase for new hardware and software. PQQ in final draft. Proof of Concept Desk deployed
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Enhanced Balancing data discovery & ingestion | Q3 2023-24 | Delayed - Internal Reasons |  | Regular consultations being held with the OBP team to align each team's roadmap. After re-prioritisation both teams have committed to new dates. Due to industry demands the OBP team is committed to delivering BM reserve in Summer 2024 causing the Audit data for DAP to move to later in the year. This work is now in design by the DAP team with an initial connection test completed in June and Ingestion of an initial test dataset expected later in the Summer 2024.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with enhanced balancing tool | Q4 2023-24 | Delayed - Internal Reasons |  | Regular consultations being held with the OBP team to align each team's roadmap. After re-prioritisation both teams have committed to new dates. Due to industry demands the OBP team is committed to delivering BM reserve in Summer 2024 causing the Audit data for DAP to move to later in the year. This work is now in design by the DAP team with an initial connection test completed in June and Ingestion of an initial test dataset expected later in the Summer 2024.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Network Control tool data discovery & data ingestion | Q3 2024-25 | On track |  | Discussions held with Network Team in May. A POC is underway which will include a connection to DAP. Architecture designs are being developed, work is ongoing to set up the POC.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with new network control tool | Q4 2024-25 | On track |  | Plan and integration details of new network control tool are in discovery with architecture work ongoing.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q1 2023-24 | Complete | Q1 2023-24 | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q2 2023-24 | Complete | Q2 2023-24 | The TAC meetings are continuing to happen quarterly as planned. We had the first in person TAC this quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q3 2023-24 | Complete | Q3 2023-24 | THE TAC meetings are happening quarterly as planned. Both the control room of the future sub group and the new Digital and data strategy met in this quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups Publication of annual report into the TAC's work and "you said we did" | Q4 2023-24 | Complete | Q4 2023-24 | "You Said We Did" has been published as part of the meeting slides. TAC's is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. All discussions in the last session and published in the slides on the ESO website.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q1 2024-25 | Complete | Q1 2024-25 | The TAC quarterly meeting happened 7th June, we also had both sub group meetings in the last quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q2 2024-25 | On track |  | TAC is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. The main TAC recently hired a new chair after the previous one resigned and he was in attendance at the last meeting.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q3 2024-25 | On track |  | TAC is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. The main TAC recently hired a new chair after the previous one resigned and he was in attendance at the last meeting.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups Publication of annual report into the TAC's work and "you said we did" | Q4 2024-25 | On track |  | TAC is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. The main TAC recently hired a new chair after the previous one resigned and he was in attendance at the last meeting.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Initiate operational input into project scoping to enable operational visibility of DER (aligned with D15.8.2) | Q1 2023-24 | Complete | Q1 2023-24 | Operational input initiated with internal ESO stakeholders. We have now performed test despatches with NGED based DERs and the system is now live.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into technical standards (aligned with D15.8.2) | Q2 2023-24 | Complete | Q2 2023-24 | The standards and discussion with MWD and NGED complete, we are still discussing some finer points with UKPN as they want to do something slightly different, but effectively the discussions are complete, what we are now discussing is small details in terms of how the process will work.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into IT discovery phase (aligned with D15.8.2) | Q3 2023-24 | Complete | Q3 2023-24 | This is complete for NGED and UKPN. Further discussions are now required on next developments.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into IT discovery phase (aligned with D15.8.2) | Q4 2023-24 | Complete | Q3 2023-24 | This is complete for NGED and UKPN. Further discussions are now required on next developments.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into requirements and design phase to enable operational visibility of DER (aligned with D15.8.2) | Q1 2024-25 | Complete | Q1 2024-25 | Linked to OBP project
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into delivery of DER data into the Control Centre | Q4 2024-25 | On track |  | Tied to OBP project
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into IT discovery phase (as ref in 15.8.3) | Q1 2023-24 | Complete | Q1 2023-24 | Operational input has been provided into MW dispatch project - implemented with NGED, and advanced discussions with UKPN.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into completion of IT discovery phases and costs (as ref in 15.8.3) | Q2 2023-24 | Complete | Q2 2023-24 | Operational input has been provided into MW dispatch project - implemented with NGED, and advanced discussions with UKPN.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into primacy rule enhancements and further use cases. Provide operational engagement with DER service providers on operational impact of primacy rules. | Q4 2023-24 | Complete | Q1 2024-25 | Now supporting DER visibility manager along with connecting to DNO control room managers to widen debate.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into primacy rule enhancements and further use cases. Provide operational engagement with DER service providers on operational impact of primacy rules. | Q4 2024-25 | Continuous activity |  | Now supporting DER visibility manager along with connecting to DNO control room managers to widen debate.
1 | Operational coordination with DER and DSO | D1.5.3 | Development of RDP and LCM functionality into real-time environment | Continue to provide operational input into LCM and RDPs | Q4 2023-24 | Complete | Q4 2023-24 | LCM is still in early development stages but trials are proceeding. We are now live and LCM is being embedded into ENCC process
1 | Operational coordination with DER and DSO | D1.5.3 | Development of RDP and LCM functionality into real-time environment | Continue to provide operational input into LCM and RDPs | Q4 2024-25 | On track |  | LCM is now live, and being embedded into ENCC process
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Establish a forum and ToR for operational flexibility service coordination with DSOs | Q1 2023-24 | Complete | Q1 2023-24 | Operational forum established with DNOs to facilitate operational discussions, bilateral discussions take place on specific service co-ordination issues (for example LCM/MW dispatch)
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Deliver new meetings | Q2 2023-24 | Complete | Q3 2023-24 | Complete - continue to update for next quarter
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Continue with regular meetings | Q4 2024-25 | Continuous activity |  | In progress
1 | Minimising Balancing Costs | D1.6.1 | Constraint boundary optimisation | Achieve coverage of additional constraint management role in Control Centre | Q3 2023-24 | Delayed - Internal Reasons |  | Discussion ongoing as to how best to incorporate this role into the ENCC, as part of a new DAS team. The ESO is assessing the benefit and feasibility of adding more resources into ENCC.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Programme plan shared | Q1 2023-24 | Complete | Q1 2023-24 | Balancing Costs Strategy has been shared with Incentives Performance Panel and Ofgem.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q3 2023-24 | Complete | Q3 2023-24 | Balancing Costs Strategy has been shared but more detail to be added following stakeholder engagement.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q1 2024-25 | Complete | Q1 2024-25 | We plan to continue to develop and add detail to our balancing costs strategy.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q3 2024-25 | Complete | Q3 2023-24 | We are continuing to develop and add detail to our balancing costs strategy.
1 | Minimising Balancing Costs | D1.6.3 | Stakeholder Engagement on Minimising Balancing Costs | Regular sessions with stakeholders to discuss opportunities to minimise balancing cost. | Q2 2023-24 | Complete | Q2 2023-24 | We hosted a workshop last year in July 2023 on our Balancing Costs analysis and strategy that we developed last year. There was a lot of engagement from industry participants. We are also about to publish an annual report on balancing costs with updated analysis and an identification of key decisions that need to be made to reduce Balancing Costs. It is expected to be published in May 2024.
1 | Minimising Balancing Costs | D1.6.3 | Stakeholder Engagement on Minimising Balancing Costs | Continuing Stakeholder Engagement forum on Balancing Cost Minimisation | Q4 2024-25 | On track |  | In progress - continuing with holding Stakeholder Engagement forums.
1 | Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | Fully staffed ENCC rota. Redesigned training schemes to facilitate needs of future ESO capabilities. New recruits direct entry from academia. | Q4 2023-24 | Complete | Q4 2023-24 | The external recruitment campaigns have resulted in a FTE of 121 with additional offers being made imminently. This meets the ENCC budget headcount for 2023 and lines us up for success to meet the 2024 headcount which is increased to meet the changing needs of the business including the introduction of flexible working within the control rooms.
1 | Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | Fully staffed ENCC rota. Redesigned training schemes to facilitate needs of future ESO capabilities. New recruits direct entry from academia. | Q4 2024-25 | Continuous activity |  | Training schemes continue to be redesigned to meet new ESO Capabilities, with whole energy being central to all. We have had Graduates and Apprentices join directly from Academia in March 2024, with more planned for September 2024.
1 | Ongoing activities | D2.1.2 | Incident analysis and investigations of abnormal events, implementing improvements where needed. | The recommendations and actions from the incident investigation will help the ESO to operate the system more efficiently and securely. All root causes will be identified, and measures put in place to mitigate against any reoccurrence. Learnings shared with system users where applicable. | Q4 2024-25 | Continuous activity |  | On track – ESO has been consistently reviewing any significant incidents that had operational impact or significant near-miss events/incidents. Where applicable shared learnings are circulated with relevant parties.
1 | Ongoing activities | D2.1.3 | Monitoring and reporting of system performance to regulatory bodies. | All regulatory reports are created to time and quality. | Q4 2024-25 | Continuous activity |  | On track - System Performance Reports: All regulatory reports have been published on time. GC105 and GC151 monthly System Incidents are reported on the ESO website. ESO has recently published the annual report of C17 NETS Performance, ICS (Incident Classification Scale), LFC (Load-frequency Control) and CEP (Clean Energy Package) Article 13 - Redispatching. https://www.nationalgrideso.com/industry-information/industry-data-and-reports/system-performance-reports
1 | Ongoing activities | D2.1.4 | Guidance on operational policies for use in the control centre produced. | The guidance is unambiguous and the information are kept up to date. | Q4 2024-25 | Continuous activity |  | On track - Control Centre has the most accurate information readily available, is unambiguous and information are kept up to date.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Deliver work based placement years | Q1 2023-24 | Complete | Q1 2023-24 | 12 one year Industrial placements have been issued. 5 for power system engineering, 3 for commercial analysts and 4 for data scientist. All are due to start with the ESO in from July 2023 and come from a wide range of UK universities.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Deliver reviewed modules and year 3 placement opportunities defined | Q2 2023-24 | Delayed - Internal Reasons |  | We have formed a University Steering group headed up by our Chief Engineer. We have 8 Industrial Placement students who will be joining NESO in July of this year.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Delivery of placement opportunities | Q3 2023-24 | Complete | Q3 2023-24 | We have 12 Industrial Placement students currently placed in the ESO.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Delivery of modules and receive feedback on placement opportunities | Q4 2023-24 | Delayed - Internal Reasons |  | Due to resourcing challenges in the operational teams we have been unable to continue the work we had started with academia. We have also seen a marked reduction in students studying power system management with some universities no longer offering the course.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Review and update summer placements for 2024 | Q1 2024-25 | Delayed - Internal Reasons |  | Summer placements - we are not in a position to offer these currently. They have been built into the early careers strategy for 2025 as they will support the feeder pipeline for apprenticeships.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Update placement opportunities for one year placements | Q3 2024-25 | On track |  | Work is underway on this milestone and we remain on track to complete on time
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Refresh and run existing courses | Q4 2024-25 | Delayed - Internal Reasons |  | Due to resourcing challenges in the operational teams we have been unable to continue the work we had started with academia. We have also seen a marked reduction in students studying power system management with some universities no longer offering the course.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Further develop cross industry secondments | Q1 2023-24 | Complete | Q1 2023-24 | We have discuss with some industry parties future cross industry secondments and found there to be little interest at this stage. The reason being stated are the constant resource challenges many are facing. We will continue to work with our current secondment organisations such as CORESO and BEIS whilst we explore this option further.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Engage with selected DNOs with potential cross simulator training options | Q2 2024-25 | On track |  | Work is underway on this milestone and we remain on track to complete on time.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Develop requirements for connectivity of training simulators | Q4 2023-24 | Delayed - Internal Reasons |  | Training Simulation environments are expected to be delivered for UAT however the ability to connect to DNO's will be delayed. We are prioritising the stakeholder engagement with the DNO's to understand their technical requirements and how we connect together in the future.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Trial training DNOs in simulators | Q4 2024-25 | On track |  | Work is underway on this milestone and we remain on track to complete on time.
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Initial NCMS Training Simulator Stood Up | Q2 2023-24 | Complete | Q1 2024-25 | GE delivered a Training Simulator for NCMS into the AWS cloud environment in April 2024. This Training Simulator will now also be deployed to future On-Prem environments as and when they are deployed
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Complete Requirements for Joint Training Simulator | Q4 2023-24 | Delayed - Internal Reasons |  | ESO project mandate is now raised. Requirement gathering is now taking place along with Business and technology vision. Due Q2 24-25
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Commence Dev/Test Phase | Q2 2024-25 | Delayed - Consumer Benefits |  | Re-baseline of plan against NCMS and OBP plans to align for delivery. GridOS pivot requires new milestone dates to be set for all corresponding Future Training Simulator milestones. Consumer benefit is realised by rebaselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process.
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Training Simulator Move to Implementation | Q4 2024-25 | Delayed - Consumer Benefits |  | Re-baseline of plan against NCMS and OBP plans to align for delivery. GridOS pivot requires new milestone dates to be set for all corresponding Future Training Simulator milestones. Consumer benefit is realised by rebaselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | An initial suite of learning packages built | Q1 2023-24 | Complete | Q1 2023-24 | A number of learning packages have been designed and developed with more planned for Q2. This includes an increase in on-line training material and the use of simulated scenarios for Energy Balancing training. Including technical role training for Transmission roles which have been difficult to recruit to.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | Learning packages tried and tested on trainees and amended where necessary | Q2 2023-24 | Complete | Q2 2023-24 | Training resources and material have been tried and tested on a number of new trainees with positive results. New training courses have been delivered for operational and non-operational staff. Feedback has been positive.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | All staff requiring access to the training packages have easy access 24/7 | Q4 2023-24 | Complete | Q4 2023-24 | Training packages created and stored in an area accessible to all staff. Used daily as part of the operational training courses.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | A full comprehensive suite of learning packages available and new ones added regularly | Q1 2024-25 | Complete | Q1 2024-25 | Work is complete on the learning suite and will be reviewed quarterly to ensure it is up to date and relevant
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | All staff requiring access to the training packages have easy access 24/7 and are able to use simulation training remotely | Q4 2024-25 | Delayed - Internal Reasons |  | The new training simulators will not have been delivered in time for this action. However it is anticipated that staff will be able to access offline training packages remotely.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Delivery of Automated System and Mobile App | Q1 2023-24 | Complete | Q1 2023-24 | Phase 3 is currently being assessed by internal and external IT providers with a number of future developments in the pipeline. The new automated system has now replaced the old manual system and the mobile app is being used by all operational staff.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Develop document management and rota improvements | Q4 2023-24 | Delayed - Internal Reasons | Q4 2023-24 | All documentation and requirement specifications for Phase 3 have completed and workshops are now planned to create a solution to meet our requirements. This has been delayed due to slow engagement of our Supplier.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Agile system that allows the user to register for training and receive training when it suits them | Q1 2024-25 | Delayed - Internal Reasons |  | Development of of the Agile training system for operational training is being scoped to understand the business requirements as we move towards NESO
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Implement document management and rota improvements | Q4 2024-25 | On track |  | Development of document management and rota improvements have started with UAT for some functionality currently underway.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Annual review of Training Plans | Q1 2023-24 | Complete | Q1 2023-24 | Annual review has been carried out on all the training plans associated to operational roles within the ENNC. They have been updated to include a skills matrix and links to newly delivered on-line learning.,
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Ad hoc review of training plans | Q2 2023-24 | Complete | Q2 2023-24 | All training plans and associated documents have been reviewed and updated to include links to online training and supporting documentation.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Ad hoc review of training plans | Q3 2023-24 | Complete | Q3 2023-24 | All operational training plans have been reviewed and updated with a detailed skills matrix and links to newly designed training packages.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Personalised training plans in place with continued gap analysis | Q4 2023-24 | Complete | Q4 2023-24 | Personal training plans issued to all trainees and a detailed skills matrix/ gap analysis carried out between trainee, trainer and line manager.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Created automation of training plans | Q1 2024-25 | Delayed - Internal Reasons |  | Due to the time taken to sanction Phase 3 this work will be delayed however we are still confident that it will be delivered within 12 months.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | User testing of automation system for training plans | Q2 2024-25 | On track |  | Work is underway on this milestone and we remain on track to complete on time
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Roll-out of automated training plans for Operational training | Q4 2024-25 | On track |  | Work is underway on this milestone and we remain on track to complete on time
1 | Ongoing activities | D3.1.1 | Control Centre has fully tested skills, processes, plans and tools to support incident management and disaster recovery. | Fully meeting existing requirements. Future scope needs to be confirmed, following the publication of the Electricity System Restoration Standard. | Q4 2024-25 | Continuous activity |  | On Track to meet requirements.
1 | Ongoing activities | D3.1.2 | Restoration plans for GB with the necessary stakeholders, developed, maintained and validated. | Following the publication of the Electricity System Restoration Standard, first Assurance framework approved by Ofgem. Continue maintaining and validating fit for purpose Restoration Plans. | Q4 2024-25 | Continuous activity |  | On Track
1 | Ongoing activities | D3.1.3 | Engage and collaborate with industry to plan and develop the new GB restoration standard, including the annual assurance framework, consistent with our licence obligations. | Code Admin Consultation sent out to industry Draft Final Modification Report and Issued to Ofgem | Q1 2023-24 | Complete | Q2 2023-24 | FMR issued to Ofgem in September
1 | Ongoing activities | D3.1.4 | Advice and oversight of Restoration and restoration strategy for the future provided. | Following the publication of the Electricity System restoration Standard, first Assurance Framework approved by Ofgem. | Q4 2024-25 | Continuous activity |  | On Track
1 | Ongoing activities | D3.1.5 | Fully competitive Restoration procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | In 2023/24 technical evaluation and assessment of SE and Northern tenders. Award contracts for SE and Northern (and Wind) restoration services. | Q4 2023-24 | Complete | Q4 2023-24 | 4 Live Tenders in 2023 - 2024 (different stages): - South East Tender - Contracts awarded in December 2023. - Wind Tender - completed with no contracts awarded. - Northern Tender: final stages of evaluation progressing and contracts expected to be awarded by no later than Q1 2024-2025. - South West and Midlands Tender: launched in January 2024. Across all Tenders we have received a very wide range of technologies for all services that Restoration is seeking to procure from the market, namely: Primary Restoration Service Providers, Top Up Services and Distributed Restart Type Projects..
1 | Ongoing activities | D3.1.5 | Fully competitive Restoration procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | In 2024/25 new Tenders to meet requirements for ESRS implementation. | Q4 2024-25 | On track |  | On Track
1 | Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance framework for Electricity System Restoration | Review, update (if required) and submit for Ofgem's approval the annual Assurance Framework | Q1 2023-24 | Complete | Q1 2023-24 | Assurance Framework for 2023/24 was submitted to Ofgem on 14 April 2023
1 | Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance framework for Electricity System Restoration | Review, update (if required) and submit for Ofgem's approval the annual Assurance Framework | Q1 2024-25 | Complete | Q1 2024-25 | Assurance Framework for 2024/25 was submitted to Ofgem on 27 March 2024.
1 | Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. | Electricity System Restoration will become a much more agile process, featuring swift methodical power supply recovery and a whole system approach with the appropriate system control, simulation and decision making tools in place. | Q4 2024-25 | Continuous activity |  | On Track
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Update regulatory framework following Ofgem's approval of regulatory changes | Q1 2023-24 | Complete | Q4 2023-24 | All approved regulatory framework are now up to date and published on ESO's website
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry to ensure progress with network changes. | Q2 2024-25 | On track |  | Following approval of regulatory framework which is published on ESO's website, There has been extensive stakeholder engagement with industry including but not limited to DNOs, TOs, Generators, CUSC parties, IDNOs with regards to meeting the ESRS requirement via various forums and by organising workshops, subgroups, presentations in forums such as ENA, STG, ETG to ensure progress with ESRS implementation.
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry during tender process to secure restoration service providers | Q3 2023-24 | Complete | Q3 2023-24 | There has been extensive stakeholder engagement on the Tenders launched in 2023
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry for training and upskilling. | Q3 2024-25 | On track |  | The ESRS and Restoration teams have provided continuous training to upskill SSE, SPT and ESO ENCC staff through workshops and practical sessions during September 2023 and May 2024. More training sessions are planned for spring of 2025 to include NGET.
1 | Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations and licence obligations. | Tool available for integration with Network Control programme | Q3 2024-25 | Delayed - Internal Reasons |  | There is a risk that Vodafone may not configure the hardware required for delivery of ENWL ICCP link within the required time due to unavailable resource to conduct site survey, deliver low level design and procurement delay therefore impacted the initial estimated delivery of June 2024 and the subsequent revisited delivery date for August. Lack of Business Analyst resourcing and delays with RFP Gate1 approval has introduced delays to the delivery of the RDST
1 | Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations and licence obligations. | Further tool testing and continuous development. | Q4 2024-25 | On track |  | Delay with RFP launch and Vendor selection due to internal delay in approval of RFP launch
1 | Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types in the Distributed ReStart innovation project. | Third Power Engineering live trial (including testing of Distributed Zonal Controller) | Q3 2023-24 | Complete | Q3 2023-24 | Third Power Engineering trial successfully delivered (Redhouse trial). https://www.nationalgrideso.com/document/289876/download
1 | Innovation project in restoration | D3.3.2 | Subject to industry adoption, Distributed ReStart proof of concept findings implemented and new system and communication methods implemented | We will fully understand Distributed ReStart's final recommendations and their implications. | Q1 2023-24 | Complete | Q1 2023-24 | Recommendations from Distributed ReStart are being implemented as part of ESRS
1 | Innovation project in restoration | D3.3.2 | Subject to industry adoption, Distributed ReStart proof of concept findings implemented and new system and communication methods implemented | We will have made decisions on which recommendations will be implemented in future (subject to industry adoption) | Q3 2023-24 | Complete | Q3 2023-24 | Selected recommendations from Distributed ReStart are being implemented as part of the tender process
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2023-24 | Complete | Q2 2023-24 | Published 6 July 2023 after a short delay to ensure content is complete and up to date.
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2023-24 | Complete | Q3 2023-24 | We have reviewed activities across the ESO to identify those which contribute to the ongoing delivery of transparency for the ESO and produced the revised ESO Transparency Roadmap, published 21st December.
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2024-25 | Complete | Q1 2024-25 | Actions required have been diarised to avoid another delay. We are on track to publish an updated version of the transparency roadmap for FY24/25 at the end of June 2024.
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2024-25 | Continuous activity |  | Actions required have been diarised to avoid another delay.
1 | Ongoing activities | D17.6 | ESO Operational Transparency Forum (OTF) | Weekly OTF held to provide timely operational insight and an opportunity for question from industry. Positive stakeholder feedback received. | Q4 2024-25 | Continuous activity |  | The OTF continues to be held weekly with active participation from industry stakeholders. in December we issued a survey to all external and internal stakeholders . We asked how well the current approach meets their needs and what changes they would like to see. This will identify and drive continuing improvements to these events. We provided high level feedback at the OTF in January 2024. We will publish the full survey outcomes in June 2024 and also to present summary outcomes at the OTF.
1 | Ongoing activities | D17.7 | Proactively driving transparency in ESO decision-making through identification, prioritisation and publication of more datasets and insight communicated through the Transparency Roadmap | Provides industry with greater transparency of our decisions in areas of high significance to stakeholders. | Q4 2024-25 | Continuous activity |  | We continue to engage with stakeholders to explain how the ESO makes dispatch decisions and to respond to queries arising from the data published each week. On 2 June we held our first Online Dispatch transparency event attended by over 300 stakeholders. We have also presented at the Balancing Programme Quarterly event on 15 June and engaged with customers bi-laterally. In cooperation with the work on Enhancing Flexible Storage in the Balancing Mechanism we are investigating opportunities to make the Dispatch Transparency dataset more accessible to ensure analysis and insights can be made to identify potential improvements for ESO processes and customer business models.
1 | Ongoing activities | D17.8 | Digital Engagement Platform (DEP) continued phased deployment | The DEP will make the experience of engaging with the ESO more intuitive and user friendly by providing a single sign on for all ESO services and a personalised user experience with access to information, data and other services including markets, connections and codes. | Q4 2024-25 | Continuous activity |  | Our approach has been to front-load work on our programme early on by increasing resources through standing up of an additional skilled team. This larger collaborative team created the ability to deliver foundational capabilities and features ahead of expected timelines but still in line with budget. Release 1: ESO website infrastructure (Acquia) made independent of National Grid website. Release 2: added user based authentication (CIAM single-sign-on) for ESO website (DXP). Plus, encouragement for user to sign on Release 3: Progressing vision of creating a more seamless customer experience across ESO digital properties. Data portal pages brought within DXP. Removal of front-end of data.nationalgrideso.com for CKAN data portal. CIAM integration with SMP for Markets registration and authentication. CIAM integration with Auctions users and APIs. CIAM integration with connections portal and added Multi Factor Authentication. CIAM integration with ENAMS and EGAMA. Improvements to Maps in terms of scope and functionality. Improvements to ESO back-end admin functionality. Search improvements for Data Portal and CMS. Release 4: personalisation of My ESO account and Data Portal Subscription enhancements. Personalisation of My News Carousel and My Events Carousel (select your topics of interest). Users able to filter My Events by type. As part of this release. we also upgraded our security around CIAM single-sign on, integrated with Connections 360, DCM and Operational Forms to bring about a more seamless UX with an iterative project on shared global components / web wrapper. Release 5 will be primarily focused on re-branding the ESO website (design, content and URL changes) for the change to NESO. DEP was previously forecast to integrate with the Data and Analytics Portal. However DAP has been delayed until 2026. Therefore a change request has been raised to safeguard money intended for DEP/DAP integration this year. This work is now due to complete by Q1 FY26.
1 | Ongoing activities | D17.9 | Open Data Catalogue | Provides external users with a view of ESO Data and enables internal users to develop their own data products to benefit consumers. | Q4 2024-25 | Continuous activity |  | Initial integration of DAP with Purview 1.0 catalogue tool complete. Internal DAP catalogue user interface POC release in May 2024. Further Internal Catalogue UI development underway. Work on the migration from Purview 1.0 to Purview 2.0 being planned to align with the new NESO azure tenancy. This will include a roadmap for scanning all NESO data sources and migration of metadata.
1 | Ongoing activities | D18.1.1 | Daily analysis of Market activity and transaction data | Robust process for analysing data in a timely manner, which allows us to identify any suspicious behaviour. | Q4 2024-25 | Continuous activity |  | The market monitoring team have a daily process established to review dynamic data, prices, and physical notifications of all balancing mechanism units. All potential suspicious activity or inconsistencies in data are logged and reviewed by the team to determine the next steps of an alert or investigation. Across FY24, the team has managed an innovation project working on producing sophisticated anomaly detection to generate additional alerting for the team to review on an on-going basis. The outputs from these work packs of this project have been implemented into the team's daily processes and adapted to meet newly introduced licence conditions (IOLC). The team continue to update and improve analysis dashboards and data analytics to support identification of and reporting against potential breaches of REMIT whilst also increasing outward engagement with market participants to improve understanding of technical capabilities and reasons for anomalies whilst also increasing tool sophistication.
1 | Ongoing activities | D18.1.2 | Detection of suspicious behaviour and submission of Suspicious Transaction Reports (STR) to Ofgem | The continuous submission of detailed STRs to Ofgem, in a timely manner over the course of BP2 | Q4 2024-25 | Continuous activity |  | Alongside the data based alerts via the automated tool assessing balancing mechanism data and Power BI dashboards, the team have established communication channels via email .box's to receive both internal to the ESO and external queries or tip-offs regarding potential suspicious activity. Every alert is assessed against REMIT and market rules and where there is reasonable grounds of suspicion of a breach of REMIT following an investigation, a suspicious transaction report (STR) will be created and shared with Ofgem's REMIT team. Similarly, where there is suspicion of a breach of market rules, a market incident report (MIR) is created. Across FY24 the team has submitted 7 STRs to Ofgem and four MIRs. All timings of STRs are tracked with and are aimed to be submitted within ACER's 28 day guidance. Ongoing discussions are had across the year on process improvements for timely submission.
1 | Ongoing activities | D18.1.3 | Undertake independent review of our Market Monitoring compliance activities against our PPAT and licence obligations alongside emerging market services. | This process includes a review of the original risk assessment and additional risk assessments of new market products and services. | Q4 2024-25 | Continuous activity |  | The team commissioned an independent external review of the design and operating effectiveness of the team's processes to identify strengths and areas of improvement. This review has been completed with a report produced sharing the findings and opportunities for the future. The report expressed that the market monitoring team had attained a high standard of practice in a short period. The market monitoring team has assessed each of the recommendations and determined a corresponding action with the majority of actions produced being implemented within FY24. The market monitoring team undertakes a continual risk-based approach to the expansion of its monitoring processes and the services to which they apply, using a data driven assessment of ancillary services and prioritising higher risk products. This approach ensures that all ESO markets have proportionate monitoring with a yearly refresh to update for new products and services or changes to existing ones. The balancing services risk assessments and trend analysis will undergo a refresh in early FY25 to reassess each of the balancing services for risk of market manipulation and help the team assess how to allocate monitoring resource and capability across the difference services.
1 | Ongoing activities | D19.1.1 | Data and Analytics (D&A) Operating Model | Our D&A operating model brings together people, process and technology to enable the continuous development and enhancement of D&A tools across the ESO & ongoing publication of data to external stakeholders via our Open Data Portal. The Operating Model is comprised of i) a "Hub" team, setting the "rules and tools" for data product development and includes Data Governance, Data Operations & Data Stewardship, and ii) business "Spoke" teams, who work with the Hub team on our DAP platform to create new data products in a self-serve manner. | Q4 2024-25 | Continuous activity |  | Continuous development is being undertaken to implement the operating model with the features of an upgraded architecture starting to be rolled out from April 2024 onwards. Major initiative to develop demand process and governance policies articulating roles and responsibilities between hub and spoke is underway.
2 | Manage existing balancing services and markets | D4.1 | We manage an end-to-end process to ensure that balancing services are procured to deliver security of supply to lowest cost to consumers. | continued management of end-to-end processes | Q4 2024-25 | Continuous activity |  | this is an ongoing activity
2 | Manage existing balancing services and markets | D4.1.1 | Frequency management strategy | Delivery of FRCR report with enhanced look-ahead. | Q4 2023-24 | Delayed - Internal Reasons |  | Update on 28 Feb - Reviewed project delivery plan has been agreed within ESO. New completion date (and submission to Ofgem) is 28 June 2024. Industry consultation will be between 8 April to 16 May with a webinar proposed on 25 April. New plan will be communicated to SQSS Panel on 11 March. Ofgem will be communicated too. We will communicate to the industry when the consultation and webinar dates are approaching via OTF and emails to SQSS distribution list. Update on 25 March - Revised plan was presented to and agreed with Ofgem on 8 March 2024. Updated plan was communicated to SQSS Panel on 11 March 2024. No objections from Ofgem or SQSS Panel. Project is progressing well in line with revised schedule. Consultation is planned to launch on 8 April. Update on 08 May - FRCR 2024 report was launched for industrial consultation on 10 April with an aimed completion date of 17 May 2024. The ESO also ran a webinar on 1 May to go through the key recommendation of FRCR 2024 policy and answered live questions from industrial attendees. We will publish the webinar materials and Q&A document towards the end of the consultation period. We will further engage with Ofgem and SQSS Panel to update feedback from industry. Update on 20 June - FRCR 2024 is on track in line with the revised project delivery plan. The report is with SQSS panel for approval before submitting to Ofgem by end of June. Intensive engagement has been carried out this year to reach out to industry.
2 | Manage existing balancing services and markets | D4.1.1 | Frequency management strategy | Delivery of FRCR report with enhanced look-ahead. | Q4 2024-25 | On track |  | Scoping for this years version progressing well. FRCR 2025 hasn't started but shall not be affected by the delay from 2024 project.
2 | Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | Annual Report published | Q1 2023-24 | Complete |  | Report published
2 | Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | Annual report published | Q1 2024-25 | Complete | Q3 2024-25 | Report on track for 24/25 Final draft scheduled for June 24 Final draft prepped and reviews, minor changes. Expected to be delivered first week July 2024. Published first week of July 2024.
2 | Power Responsive | D4.2.2 | Regular and specific metrics, and publications for multi sector approaches focusing on opportunities for household, community energy, small business participation, zero carbon technologies, and electrification of heat in Demand Side Flexibility (DSF). | Successful delivery of sector specific events and engagement to raise the awareness of ESO/DSO flexibility markets with the demand side community | Q4 2024-25 | Continuous activity | Q2 2024-25 | Update 15/12/2023 Power Responsive ran our annual event in august which we feel was very successful. Average BI score 8.3 with lots of good feedback. We also attended both BigZero and EMEX, at the latter we sponsored and controlled the large stage where we discussed various key topics. on 11th Dec we held our follow up Operational metering group where we were able to share the news on the extension of the Live Small Scale aggregated asset trial live in BM. We continue to support industry on the MIR challenge and have also started the I&C review. Annual Report kick off scheduled for April24. 20/06/2024 Power Responsive Summer event was delivered in June 24 with a great success (BI score of 8.7) lots of wonderful feedback. FlexAssure Roadshow scheduled for 24th June. Annual report due to be released shortly (JULY 24) A number of smaller events are being held with the Power Responsive team including a summer event which is being held in London in July. 21/09/2023 PR have atteneded multiple external events and also held our PR Annual event on 18/09/2023 Update 15/12/2023 Power Responsive ran our annual event in august which we feel was very successful. Average BI score 8.3 with lots of good feedback. We also attended both BigZero and EMEX, at the latter we sponsored and controlled the large stage where we discussed various key topics. on 11th Dec we held our follow up Operational metering group where we were able to share the news on the extension of the Live Small Scale aggregated asset trial live in BM. We continue to support industry on the MIR challenge and have also started the I&C review. Annual Report kick off scheduled for April24. 20/06/2024 Power Responsive Summer event was delivered in June 24 with a great success (BI score of 8.7) lots of wonderful feedback. FlexAssure Roadshow scheduled for 24th June. Annual report due to be released shortly (JULY 24)
2 | Deliver an efficient frequency market | D4.3.3 | New reserve products - development and introduction of a new suite of products to provide reserve to the Control Centre | Launch Firm market for nBM providers (dependency on D4.3.5) | Q3 2023-24 | Delayed - Internal Reasons |  | A nBM market for Quick & Slow Reserve will be delivered after the OBP Strategic nBM functionality is released. This is planned to be Q2/Q3 25/26. Continued engagement with industry is ongoing to seek stakeholder feedback on the proposed design of the services, including webinars and the offer of 1-2-1 sessions
2 | Deliver an efficient frequency market | D4.3.3 | New reserve products - development and introduction of a new suite of products to provide reserve to the Control Centre | Launch Firm market for BM providers (dependency on OBP delivery) | Q4 2024-25 | On track |  | BM Market for Quick Reserve will be delivered in Q2/3 24/25 once the functionality has gone live on the OBP with Slow Reserve planned for delivery in Q2/Q3 25/26. Engagement with industry is ongoing with webinars held in Q4 23/24 to seek stakeholder feedback on the Quick Reserve design along with a number of 1-2-1 sessions. Based on feedback received we have increased recovery time to 3 minutes to facilitate greater participation and further engagement on the service design and implementation is planned for Q1 24/25 before we finalise requirements for formal consultation later in Q1 24/25. EBR Article 18 Consultation for the Quick BM only service was launched on 27th July. Reserve Engagement with industry on Slow Reserve is planned for Q2 2024
2 | Deliver an efficient frequency market | D4.3.4 | Delivering an efficient frequency market | Created longer-term procurement strategy which spans response and reserve looking at how the products interact with each other operationally and commercially, and the wider market. | Q4 2024-25 | Continuous activity |  | The go live of our response services has been positively received by industry allowing new functionality such as stacking and splitting as well as enhanced bidding options like negative pricing. Balancing Reserve Service now being added to the Enduring Auction Platform. This service will go live on the EAC platform early March 2024. Work also being done to support BM QR launch on the EAC platform. Following challenges with the Response 2 submission we are incorporating learning from this into our refreshed project for A18 planning and submissions.
2 | Deliver an efficient frequency market | D4.3.5 | Auction capability | Implementation of the enduring auction capability and transition of the newly introduced services of BP1 onto the platform. | Q4 2024-25 | Continuous activity |  | Balancing Reserve Service now being added to the Enduring Auction Platform. This service will go live on the EAC platform early March 2024.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | In line with our new approach to annually consult on the new response services, we expect to formally engage with industry through the EBR Article 18 process in summer 2023-24. | Q2 2023-24 | Complete | Q2 2023-24 | Release 2 (2023-24) Electricity Balancing Regulation (EBR) consultation launched in Summer 2023 and was submitted to Ofgem end of September 23. Following challenges in the submission the ESO re-submitted and received approval in Mar-24. Key topics of focus for 2023-24 include removing barriers to Data-derived metering (baselining), clarity on topics such as State of Energy, updates to ramp rates, as well as a range of changes to tools and improvements to enable the Control Centre to operate the electricity transmission system securely.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | We expect to publish updated service terms towards the end of Q3 2023-24. These changes will then feed into the C16 consultation process. | Q3 2023-24 | Complete | Q4 2023-24 | Service terms will be updated and published following Ofgem approval (expected in Q4). Delay due to amendments required in drafting of revised Release 2 - resubmitted and approved in Q4 23/24
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | Working on the assumption that the annual cycle is welcomed by industry we expect to be consulting via the EBR Article 18 process on response services in Q2 2024-25. | Q2 2024-25 | On track |  | In Q2 will be launching the Response Release 3 consultation. Key topics will be the removal of the maximum ramp rate restriction, further clarity on the availability policy and significant changes to monitoring and reporting which will provide more robust performance management. All of these topics have been key service provider pain points identified through previous engagement. These changes are expected to remove barriers to participation, increasing liquidity and provider confidence in fair market.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | If we consult in Q2 2024-25, we expect to publish updated service terms towards the end of Q3 2024-25. These changes will then feed into the C16 consultation process. | Q3 2024-25 | On track |  | Subject to approval we will publish updated service terms and implement new systems and processes in support of those.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Initial integration with Enduring Auction Capability | Q2 2023-24 | Complete | Q1 2023-24 | SMP has delivered initial integration with the Enduring Auction Capability in Q1 to facilitate market trials in September and go live of EAC in October 2023
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Query Management process aligned with wider ESO digital process | Q3 2023-24 | Delayed - Internal Reasons |  | SMP will support a consistent query management process across the ESO. The Digital Experience team (DEP) showcased their latest design in the SMP Show and Listen Event on 15 June 2023 but the delivery of this process into production has been delayed past Q3, likely into Q1 or Q2 2024/25. The wider "Query Management" and "Help Centre" architecture will now be implemented from a central ESO Salesforce project rather than DEP. The DEP project will govern the delivery to drive consistency for users across multiple platforms. Change in approach to Salesforce has resulted in delay in starting dev work. Awaiting approved solution prior to estimation & scheduling.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Integration with Settlements system | Q4 2023-24 | Delayed - Internal Reasons |  | SMP has integrated at a high level with the new STAR system through the provision of direct contract information from November 2023. This milestone however was targeting greater integration from Q4 2023/24. This work was initially delayed due to a code freeze linked to the FSO split and we are now targeting work in 24/25. In the SMP Show and Listen event on 07 September 23 we canvassed opinion from the industry on what they want NGESO to focus on initially. Access to invoice information on an enduring basis through STAR will not be achievable till 2025, however SMP is working on an interim solution that is looking to access existing Sharepoint data during Q3
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Enhance the wider BM registration process | Q2 2024-25 | Delayed - Internal Reasons |  | Recoverable in BP2. Due to complexity the initial move of the existing process into SMP will now be in Q3. Enhancements to BM Reg Team process from Q4 onwards
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | All balancing services procured through SMP | Q4 2024-25 | On track |  | SMP is currently hosting the 3 dynamic frequency response products (DC, DM and DR), Static FFR, DFS, Balancing Reserve and 2 RDP products. We are working on the integration of future Quick and Slow Reserve. This is based on the strategy to prioritise day ahead and enduring products that are consistent and repeatable that lend themselves to a self serve digital experience. We believe that this represents an appropriate approach to service integration but are investigating where SMP can add value to the user experience in other services
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Supported the development of a proof of concept for industry asset register | Q2 2023-24 | Complete | Q3 2023-24 | ESO is actively working with UKPN and Electralink to develop a proof of concept that will see both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data will inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. We conducted the PoC in Q4 2023/24 and provided feedback and learnings to the industry afterwards. This work will feed into the wider "DER Visibility" project within the ESO.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Participation in proof of concept for industry asset register | Q4 2023-24 | Complete | Q4 2023-24 | ESO has actively worked with UKPN and Electralink to develop a proof of concept that will see both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data will inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. This PoC ran operationally in February and learnings will feed into the wider "DER Visibility" project within the ESO.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Integrate SMP with industry asset register (subject to it being available) | Q2 2024-25 | Delayed - External Reasons |  | The reason that these milestones are delayed is that delivery is dependent on multiple parties. Ofgem is having discussions with various parties to understand how Common Asset Register can be delivered industry-wide. These features are impacted by wider Ofgem work on an Industry Asset Register and we cannot deliver these milestones until Ofgem have determined the direction that will be taken. The second milestone is also impacted by discrete DER Visibility project (to which SMP is central to a number of use cases). We have actively worked with UKPN and Electralink to deliver a proof of concept that saw both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data could inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. This PoC ran operationally in February and we will provide feedback and learnings into the wider "DER Visibility" project within the ESO. SMP is also supporting the work up of a regular report that can be shared with DNOs to understand MPAN / balancing services pre-qualification risk of conflicts. The SMP team is also actively engaging with Ofgem on responding to "common asset registry" work. It is still to be determine how this would be achieved and what role SMP could have in it (if it is even proven through an impact assessment to be scalable)
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Improved DER asset visibility within SMP and / or wider NGESO platforms | Q4 2024-25 | Delayed - External Reasons |  | The reason that these milestones are delayed is that delivery is dependent on multiple parties. Ofgem is having discussions with various parties to understand how Common Asset Register can be delivered industry-wide. These features are impacted by wider Ofgem work on an Industry Asset Register. SMP is actively involved in the discussions alongside DDT and Flexibility Market Development team, but we cannot deliver these milestones until Ofgem have determined the direction that will be taken on a Common Asset Register. The second milestone is also impacted by discrete DER Visibility project (to which SMP is central to a number of use cases). We have actively worked with UKPN and Electralink to deliver a proof of concept that saw both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data could inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. This PoC ran operationally in February and we will provide feedback and learnings into the wider "DER Visibility" project within the ESO. SMP is also supporting Distributed Flexibility team to work up a regular report that can be shared with DNOs to understand MPAN / balancing services pre-qualification risk of conflicts. The SMP team is also actively engaging with Ofgem alongside the Markets Flexibility team and DDT on responding to "common asset registry" work. It is still to be determine how this would be achieved and what role SMP could have in it (if it is even proven through an impact assessment to be scalable)
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.3 | Reforming markets to facilitate future growth of Distributed Flexibility technologies and models | Develop an ESO strategy to facilitate the growth of Distributed Flexibility. It will aim to understand the capabilities of distributed flexibility, their unique challenges in entering our markets, a defined vision for distributed flexibility in 2035, and a set of actions to reform our markets to facilitate their growth and participation. | Q4 2023-24 | Complete | Q4 2023-24 | Flexibility Strategy is under co-creation with industry parties. We have defined ESO’s vision, desired 2035 strategic objective and 2028 outcomes, as well as the roadmap of actions. The key focus of this quarter is testing our proposal with various industry colleagues via workshops and bilateral conversations. Based on the feedback received from industry, we changed our delivery approach. A Call for Input will be launched to make our engagement more effective and inclusive.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.3 | Reforming markets to facilitate future growth of Distributed Flexibility technologies and models | Align actions with Markets Roadmap and market reforms. Continue to refine the strategy, including further deep dives on specific issues as technologies and markets evolves. | Q4 2024-25 | Continuous activity |  | To ensure we’re heading in the right strategic direction and able to achieve our aims, a Call For Input has been launched to test our proposal with industry colleagues and invite their feedbacks. We believe that demand side flexibility has a key role to play in operating a secure, low cost, zero carbon system, but demand side flexibility is currently underrepresented across our services due to market rules, policy, and regulatory barriers. Alongside the Flex Strategy Call for Input, we also launched the Routes to Market Review for Demand Side Flexibility. It is a part of the Flexibility Market Strategy workstream 2, to remove barriers and pain points for flexibility across ESO services and markets.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.4 | Facilitating market access for Distributed Flexibility | Understand the key technical and commercial barriers to distributed flexibility today and deliver prioritised short-term changes as per ESO strategy. Progress towards the delivery of SMP (as per A4.4). | Q4 2023-24 | Complete | Q4 2023-24 | We continue to engage with the market and stakeholders and evolving our strategy around the development of flex markets including the delivery of SMP. The flexibility strategy will propose the direction we will be taking. Included in this is a review of stacking and key service requirements. We continue to progress this with industry stakeholders and have made some progress with the DNO's over a PoC for coordination/primacy rules.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.4 | Facilitating market access for Distributed Flexibility | Continue to identify and deliver changes required to faciliate distributed flexibility participation and coordinate with long-term Distributed Flexibiltiy Strategy. | Q4 2024-25 | Continuous activity |  | MPAN visibility has been identified as a blocker for FSP to move seamlessly between ESO and DSO markets. SMP team have actively worked with UKPN and Electralink to deliver a proof of concept that both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data could inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. As part of the Flexibility Market Strategy Call for Input, we also launched a "Route to Market" review work inviting industry colleagues to help us better understand the barriers demand side flexibility resources are currently facing to current ESO markets. The output of this review will be feed into further development of SMP.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.5 | Ensure co-ordination of markets across the whole electricity system | Locational data available for all providers of flexibility services to facilitate DSO awareness. Further consideration on how flexibility should be coordinated across ESO-DSO for contractual and procurement processes. | Q1 2023-24 | Delayed - Internal Reasons |  | While the DER Visibility programme seeks to achieve visibility and exchange of all locational data, services that have migrated to the Single Markets Platform have captured locational data. We are working with the DNO's to devise the appropriate data sharing mechanism of this information to the relevant networks to inform risk of conflict reporting and operational coordination.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.5 | Ensure co-ordination of markets across the whole electricity system | Continue to identify and deliver changes to support market coordination. | Q4 2024-25 | On track |  | We have taken an active role in the Open Networks programme this year, leading on several workstreams to drive coordination. Our Flexibility Strategy Call for Input was launched in May with a dedicated workstream on DSO coordination, and our DFS design proposal launched on 16th June directly addresses concerns raised by DNO's on the ability to stack the services with distribution services.
2 | Balancing and ancillary services market reform | D4.6.1 | Development of competitive approaches to procurement of stability. | Long-term procurement: Implement the findings of innovation project and build on learnings from pathfinders, develop the details of implementing enduring long term market based on the output from BP1. Short-term market: Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2023-24 | Complete | Q4 2023-24 | • On progressing the mid-term (Y-1) Stability Market, we have now opened an Invitation to Tender (ITT) for market participants who wish to bid for the first Mid-term (Y-1) Stability Market delivery year, commencing 1st October 2025. The EOI closed on 26th January 2024 where providers expressed an interest and received an invitation to tender. Feedback from the informal consultation on service design, contract terms and technical eligibility criteria which we ran alongside the EOI process has been taken on board for the final design of the Mid-term (Y-1) market. Market participants are now preparing technical and commercial submissions for the first delivery year. The deadline for submitting these is 26th April 2024, following which ESO will assess bids against both technical and commercial criteria. We held two further industry webinars on Monday 5th and Tuesday 6th February 2024 to walk through the most important information as part of the ITT stage and offer an opportunity for industry to ask questions. We have also held 121 calls with every provider who is participating in the ITT for the first time. • In parallel, we are reviewing Y-4 and D-1 markets and engaging the relevant teams in ESO to understand what will be required to deliver these markets, and in what timescales this can be achieved. We are working closely with the Centralised Strategic Network Planning team to ensure that new system studies through CSNP are aligned and co-ordinated with the Long-term (Y-4) Stability Market, so this can be signalled accordingly when a requirement emerges. In our 2024 Markets Roadmap, we also shared plans to explore an optional Short-term (D-1) Stability Market in advance of the full delivery of an automated D-1 auction. We will be engaging with industry further on this. Our delivery plans will be updated through the recently introduced Markets Roadmap monthly delivery plan updates.
2 | Balancing and ancillary services market reform | D4.6.1 | Development of competitive approaches to procurement of stability. | Continuous improvement of long-term market design based on industry feedback. Run procurement process, if required depending on the system needs, so that the market participants have sufficient time to make informed business decisions on possible solutions and bidding approach. Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project | Q4 2024-25 | On track |  | • On progressing the mid-term (Y-1) Stability Market, we have now closed the Invitation to Tender (ITT) for the first Mid-term (Y-1) Stability Market delivery year, commencing 1st October 2025. Market participants have submitted technical and commercial submissions for the first delivery year which we are now assessing against both technical and commercial criteria. This process will continue over the summer ahead of awarding contracts by October 2024. We are also beginning to prepare for the second delivery year (2026/27) of the Y-1 market which will undergo the same process (EOI->ITT) commencing later in 2024. • In parallel, we are continuing to finalise the Y-4 and D-1 initial market design and beginning to engage the relevant teams in ESO to understand what will be required to deliver these markets, and in what timescales this can be achieved. We are working closely with the Centralised Strategic Network Planning team to ensure that new system studies through CSNP are aligned and co-ordinated with the Long-term (Y-4) Stability Market. Furthermore, we are undertaking some analysis to derive the expected value through a Short-term (D-1) Stability Market to ensure it can be appropriately prioritised by ESO in the roadmap for ancillary service and system developments. Our delivery plans will be updated through the recently introduced Markets Roadmap monthly delivery plan updates. Alignment with ESO’s new balancing, auction, and settlement systems will be a fundamental enabler.
2 | Balancing and ancillary services market reform | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Long-term procurement: Implement the findings of innovation project and build on learnings from pathfinders, develop the details of implementing enduring long term market based on the output from BP1. Short-term market: Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2023-24 | Complete | Q4 2023-24 | Following the reprioritisation activity ahead of winter 22/23, work on a Reactive Power market was paused. This work is now being re-started with a new timeline and deliverables being planned. The next steps for developing reactive markets were identified through the work in 2023 which is to prioritise the implementation of long term market, and continue review the benefit and impact for mid and short term markets.
2 | Balancing and ancillary services market reform | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Continuous improvement of long-term market design based on industry feedback. Run procurement process, if required depending on the system needs, so that the market participants have sufficient time to make informed business decisions on possible solutions and bidding approach. Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2024-25 | On track |  | We have completed our work on the long-term market and plan to launch the first tender when the right opportunity presents itself. Implementing the long-term market will drive locational investment and enable greater competition in the delivery of reactive power service provision. 2029 is the earliest year for which there may be a requirement to be covered by the long-term market, subject to a firm requirement being identified and the long-term market being selected by ESO as the preferred delivery route. We are continuing to assess the consumer benefit impact that a mid-term reactive market would provide by procuring reactive power closer to the delivery year. There are some design questions to be further analysed before progressing with a mid-term market, so we will continue to review the value and impact of a mid-term market and will update the latest progress through newsletter and webpage. On the short-term market, further analysis is required to determine the value of a day ahead service. This work will also consider the output from the review of the Obligatory Reactive Payment Service (ORPS).
2 | Balancing and ancillary services market reform | D4.6.3 | Maximise participation in ancillary services | Exploring barriers to entry across the ESO ancillary services markets, identifying mitigating actions and working with industry to implement the changes needed to facilitate routes to market, and increase participation and liquidity of our markets | Q4 2024-25 | On track |  | This project is identifying barriers to entry for renewable generators and Interconnectors for Frequency Response and Reserve markets. The objective is to identify opportunities to remove barriers so that assets can join these markets when conditions allow. A new project team has been set up to lead on this. Phase 1 of external engagement has been completed. As of Q4, the draft project report is completed. This is now undergoing refinement in advance of further engagement on findings in advance of publication in Summer 2024.
2 | Balancing and ancillary services market reform | D4.6.4 | Local Constraints Market reform | Assess whether LCM should be rolled out across other zones. Assess whether other services should be rolled out on the 3rd party flexibility platform | Q4 2023-24 | Complete | Q4 2023-24 | Assessment of LCM continues following commencement in 2023. Fixes to enable the market to encourage all types of participant will be the focus in shorter term.
2 | Balancing and ancillary services market reform | D4.6.4 | Local Constraints Market reform | Assess whether LCM should be rolled out across other zones. Assess whether other services should be rolled out on the 3rd party flexibility platform | Q4 2024-25 | Continuous activity |  | On track with some successful bids and dispatch. We will launch a C16 consultation over the Summer to allow greater participation by aggregators (subject to Ofgem approval)
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Publish co-created guidance covering any rule changes and system and operational improvements, in collaboration with Ofgem, BEIS and industry, within 4 weeks of rules being set. | Q1 2023-24 | Complete | Q1 2023-24 | CM: > Guidance is being updated with: > specific focus on areas of feedback > a new section of “new for this year” to assist parties with understanding Rules changes. > slides requested by DESNZ to aid in policy conversations to ensure consistent messaging cross-party in response to emerging focus of questions. > EMR DB have published the Operational Plan and circulated to over 3,000 parties on 12 June 2023 > EMR customer events are scheduled to take place on 19 July (in-person) and 25th July (online) to launch this year’s CM process, with a focus on prequalification and rule changes. > The EMR DB team have been working to update the process for query management to achieve quicker SLAs, and undertaken cross training of team to enable more rounded advice. CfD: > The EMR DB published CfD guidance prior the application window opening for Allocation Round 5. The guidance included: > How customers should complete the application form if applying for a private network CfD agreement > How Floating Offshore Wind applicants should provide the supply chain plan > How Solar PV applicants should entered their Initial Installed Capacity Estimate. > Clear steps on how applicants could view their Allocation results (e.g. examples were added of how applicants can check for confirmation of an action in the system being completed). > Overall formatting of the guidance documents were updated to ensure there was a clear flow through of each section related to the CfD Allocation process. > Guidance changes were refined in consultation with Delivery Partners, DESNZ and Ofgem and draft guidance documents were reviewed by a select group of customers. > The EMR DB also engaged through: > An auction scenarios video distributed to customers shortly after the budget notice being for Allocation Round being published > The CfD Launch Event and the EMR DB led applicant readiness webinar in early 2023.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Commence the pre-qualification process, with customers benefitting from enhanced guidance | Q2 2023-24 | Complete | Q3 2023-24 | CM: Prequalification application window closed on 19 September. The team is busy providing support to Applicants, including responding to queries. During 7/8 September, the Portal was running very slowly - the DB identified the root cause, correct it and issued comms to stakeholders on 8 September.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Conclude the pre-qualification and disputes processes and prepare for the auctions | Q3 2023-24 | Complete | Q3 2023-24 | CfD: Ofgem upheld the DB's decision on all of the disputes submitted to them. We recognise however that Ofgem did not uphold the DB's position on every matter included in the disputes. CM: The Tier 1 disputes process finished on 28 November 2023. The Tier 2 process is currently happening, with a small number of disputes raised to Ofgem for decision.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Deliver the auctions and post-auction activities, including capturing key learning points with industry | Q4 2023-24 | Complete | Q4 2023-24 | CfD: The DB has successfully completed the Auction Round 5 auction process. AR5 results were released to industry on 8 September 2023 CM: On 20 February 2024, the EMR DB ran the T-1 Auction and on 27 February 2024, the EMR DB ran the T-4 Auction. The Auction Monitor Reports for both auctions have been published by DESNZ, confirming that the Auctions were run in accordance with the CM Rules and Regulations. Following the Auction processes, the EMR DB has had lessons learned sessions internally and with DESNZ.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Publish co-created guidance covering any rule changes and system and operational improvements, in collaboration with Ofgem, BEIS and industry, within 4 weeks of rules being laid. | Q1 2024-25 | Delayed - External Reasons |  | CfD: The CfD team published updated guidance in advance of AR6 opening, reflective of feedback following AR5 and other improvements identified by the team. These including moving to a Word format and reducing a very long guidance document by nearly half to make it more accessible to users. CM: This milestone is dependent on decisions regarding Rule changes, which the Delivery Body is actively supporting the Government and Ofgem with developing, and learnings from the 2024 Auctions. In readiness for the PQ submission window opening for the 2025 Auctions, we are updating our guidance to reflect proposed policy changes and then will be able to issue it once the new rules are laid by DESNZ.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Commence the pre-qualification process, with customers benefitting from enhanced guidance | Q2 2024-25 | On track |  | CfD: The prequalification period has now finished and we are now awaiting advice from Ofgem if any unsuccessful applicants are going to dispute to them. CM: the team has been updating guidance, published Operational Plan and developing the new Portal being launched on mid-June in readiness for the prequalification window opening (currently planned for late July).
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Conclude the pre-qualification and disputes processes and prepare for the auctions | Q3 2024-25 | On track |  | Delivery of these milestones is sequential and so this milestone will commence after the preceding one has concluded.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Deliver the auctions and post-auction activities, including capturing key learning points with industry | Q4 2024-25 | On track |  | Delivery of these milestones is sequential and so this milestone will commence after the preceding one has concluded.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Develop a clear process for capturing and assessing policy, rule and process improvements which draws on operational experience and industry feedback and feed this into CMAG and other relevant BEIS and Ofgem processes. | Q1 2023-24 | Complete | Q1 2023-24 | The EMR DB has developed and shared with Ofgem a process for how they will identify and undertake initial assessment of proposals and then progress them through CMAG. Further work is being undertaken internally to develop a standardised approach for impact assessments, based on experience with changes to date, which will then be discussed with delivery partners for their input.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Q2-4: Once established, we will run the improvement process on an ongoing basis, with key outputs timed to meet BEIS, Ofgem and CMAG timelines. | Q4 2023-24 | Complete | Q4 2023-24 | The DB has identified potential changes that could be made to the CM Rules to improve clarity, processes and operations. However, in many cases the changes require greater clarity around the original policy intent and whether that continues to be appropriate, and so the DB is now working closely with other delivery partners to review these areas in more detail, before they become detailed change proposals. Now that REMA consultation 2 proposes to retain CM as an Optimised CM, the EMR DB are working with DESNZ and Ofgem to understand how this will influence potential operational and policy changes.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Undertake informal review of the improvement process with industry, BEIS and Ofgem to identify ways to refine the approach. | Q1 2024-25 | Complete | Q1 2024-25 | The improvement process has been successful in identifying 'pain points' through review of customer queries, operational experience and review of the Rules. However, as identified above, this is now being further developed through a holistic process across all delivery partners.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Q2 - Q4: Implement process refinements and run refined improvement process from Q2 onwards | Q4 2024-25 | On track |  | This milestone is dependent on the outcomes of the one above relating to process improvements.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Production of 2023 ECR | Q1 2023-24 | Complete | Q1 2023-24 | Report submitted to the Department of Energy Security and Net Zero on 31 May 2023.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Develop further enhancements to security of supply modelling to support the transition to net zero (e.g. impact of weather, limited-duration technologies, DSR, and European modelling) | Q4 2023-24 | Complete | Q4 2023-24 | This milestone represents a well-established annual cycle of work. This year's projects are now complete and will be reported in the 2024 Electricity Capacity Report in line with the well-established process.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Production of 2024 ECR | Q1 2024-25 | Complete | Q1 2024-25 | Report submitted to DESNZ on 31 May 2024
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Develop further enhancements to security of supply modelling to support the transition to net zero (e.g. impact of weather, limited-duration technologies, DSR, and European modelling) | Q4 2024-25 | On track |  | This milestone represents a well-established annual cycle of work. The 2024/25 projects will be considered once the 2024 Electricity Capacity Report has been completed.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements following first study published in 2022 | Q1 2023-24 | Complete | Q1 2023-24 | We published our first 2035 resource adequacy study in December 2022 in collaboration with AFRY. We have since invited input and feedback from expert stakeholders via in-person / virtual round tables and bilateral discussions. We are now on track to set out our next steps for these studies and how feedback has informed this. This will be published on our Resource Adequacy website.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements following first study published in 2022 | Q4 2023-24 | Complete | Q4 2023-24 | We are committed to engaging with stakeholders in this work. We have already offered opportunity for stakeholders to provide input following the first study. We published an update in July 2023 and have set up an expert group to work with us on this. This represents continuous engagement activity.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Production of capacity adequacy study | Q1 2024-25 | Delayed - Internal Reasons |  | We published our first study assessing resource adequacy in the 2030s in December 2022 in collaboration with AFRY. We have since invited input and feedback from expert stakeholders via in-person / virtual round tables and bilateral discussions. We published the next steps on our website in July 2023. We established a team in the ESO to undertake further studies that would enable us to deliver on our BP2 commitment of producing a revised resource adequacy study at least every 2 years. The BP2 milestones were put in place before the new team was established. We have now worked through the details of the modelling approach, which has proved to be very complex, and has given us greater clarity on our timings. We now working on the modelling and expect the next study to be produced in autumn 2024 (still within 2 years of the previous study). We are continuing to work with stakeholders, notably through our expert group, and have also published a couple of spotlights on areas of particular focus.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements | Q4 2024-25 | On track |  | We are committed to engaging with stakeholders in this work. Following the publication of the second study in 2024, we will continue to engage and work with stakeholders.
2 | Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of nationally driven regulatory change through the open governance process. | Other code changes identified by the ESO or raised by 3rd parties and RCRC | Q4 2023-24 | Complete | Q4 2023-24 | We have started analysing the refreshed RCRC data and plan to produce a recommendation in 2024. Grid Code: GC0117 - CBA is complete and in our view is positive for consumers. The workgroup vote is taking place in january. Expect to meet 2027 implementation timeframe CM088 - the STC modification that followed on from GC0141 (9th August Power Disruption) has now been approved. Completing all the post 9th August changes that were requested. CMP330/374/CM079 Contestable connections – sent to authority in Q3 2023 awaiting Ofgem decision Winter 2023/24 programme of work delivered to ensure appropriate changes are in place across the codes and frameworks where necessary (eg GC161) GC161 and GC162 have now been implemented. CUSC mods CMP413 - we continue to work proactively the workgroup to develop a solution and the WACMs that have been raised. CMP392 - this is currently with Ofgem for a decision. CMP376(Queue Management) – WACM7 has been approved and has been implemented. CMP330/374/414 (connection competition) – no change as awaiting Ofgem decision. Following stakeholder engagement the ESO identified a way to progress the change more quickly and has reflected this in its consultation response. CMP425 – we worked collaboratively with the workgroup and proposer to support developing a solution under urgent timescales and this is on track to be submitted to Ofgem at the time of writing. We have presented on an issue related to zoning at TCMF, and this has been raised as a formal CUSC modification (CMP419) and has started workgroups. A number of modifications have been raised in the past quarter and we continue to support development of these through the workgroup process.
2 | Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of nationally driven regulatory change through the open governance process. | Progress further code modification proposals as required in addition to wider programme projects | Q4 2024-25 | Continuous activity |  | There are number of live code modification in flight, with a number of new Modifications expected through the year.
2 | Code management / market development and change | D6.1.1 | Enable major net zero programmes - Offshore Coordination | Delivery of code modifications associated with implementation of the offshore project dependent on progression of offshore coordination programme | Q4 2023-24 | Delayed - External Reasons |  | The Sub-group to support the Electricity System Operator (ESO) in developing changes to the Transmission Network Use of System (TNUoS) charging methodology in relation to the OTNR was launched early 2023 and has now concluded. The overall focus of the group was to consider, discuss and provide input into developing the charging principles and subsequent methodology changes to support the ESO in creating a set of code modifications to facilitate offshore coordination and there are 3 live modifications currently in the formal governance process and 1 new modification being raised in the near future. There are a number of CUSC modifications in flight and this action will be closed once they concluded and the Authority has made their decision. CMP402 - raised in response to Ofgem’s final decision on Anticipatory Investment (AI) - to introduce changes to the current User Commitment provisions within Section 15 of the CUSC (currently at workgroup stage). CMP411 - raised to introduce Anticipatory Investment (AI) and a mechanism for the recovery of AI costs within the Section 14 of the CUSC (currently at workgroup stage). CMP419 – raised to review the existing generation zoning methodology to incorporate offshore assets connected as part of the Holistic Network Design (HND) to enable the wider tariff to be applied to offshore generators.
2 | Code management / market development and change | D6.1.2 | Enable major net zero programmes - Onshore Competition | Delivery of code modifications associated with implementation of onshore competition dependent on progression of onshore competition | Q4 2023-24 | Delayed - External Reasons |  | CATO modifications are in flight and at an advanced stage. These modifications introduce the concept of Competitively Appointed Transmission Owners (CATOs) for the purposes of introducing Early Competition for the design, build and ownership of Onshore Transmission assets. CATO legislation was approved by Parliament in Autumn 2023 (which was initially causing delays to this deliverable). The intention is to bring all CATO mods to Ofgem for them to review in summer 2024 (Grid Code, CUSC, STC and SQSS CATO mods). The Final Modification Reports have been submitted to Ofgem for STC mods (CM086 and CM087), CUSC mods (CMP403 and CMP404), SQSS (GSR031), with Grid Code mod (GC0159) at Draft Final Modification Report stage pending resolution of a query on CATO Licencing which is currently under discussion with Ofgem and Legal Counsel.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Delivery of code modifications to set equipment specifications | Q1 2023-24 | Complete | Q1 2023-24 | ESRS Modifications have now all been approved and are in the process of being implemented, this was complete by Q4 23/24 so behind schedule due to process taking slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - approved and being implemented STC modification - CM089 - CM089 : approved and being implemented.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Completion of code changes | Q2 2023-24 | Complete | Q2 2023-24 | ESRS Modifications have now all been approved and are in the process of being implemented, this was complete by Q4 23/24 so behind schedule due to process taking slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - approved and being implemented STC modification - CM089 - CM089 : approved and being implemented.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Code changes implemented for ESRS to facilitate licence compliance which is required by Dec 2026 | Q4 2024-25 | Complete | Q4 2023-24 | ESRS Modifications have now all been approved and are in the process of being implemented, this was complete by Q4 23/24 so behind schedule due to process taking slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - approved and being implemented STC modification - CM089 - CM089 : approved and being implemented.
2 | Code management / market development and change | D6.1.4 | Enable zero carbon operation - Stability | GC0137 'Grid Forming' Grid Code modification - guidance document delivery | Q1 2023-24 | Complete | Q1 2023-24 | The Grid Forming best practice guide is now on the ESO website.
2 | Code management / market development and change | D6.1.5 | Lead charging reform | Raise TNUoS modifications to facilitate charging reform | Q1 2024-25 | Complete | Q1 2024-25 | TNUoS Taskforce is currently working through a number of sub groups regarding identified issues. The 'sub groups' are now in the process of clearly articulating the defects and creating solutions. To date 2 Modifications have been raised with a further one to be raised in Q1 2024. It is expected that a number of further Modifications will follow throughout 2024. Scaling Factors was presented at the Taskforce and has now been raised as a formal CUSC modification (CMP424) which started workgroup in January 2024. Generation reference nodes has also been raised as a formal modification following development by the Taskforce, raised by SSE (CMP423). In addition CMP413, raised by EDF is progressing through workgroups and ESO are fully engaged in this process. The TNUoS 10year projection has also been developed alongside this modification to aid industry in making investment decisions. This was an extra piece of work that the ESO have done on top of the obligations within the CUSC.
2 | Code management / market development and change | D6.1.5 | Lead charging reform | Identify required code changes | Q4 2023-24 | Complete | Q4 2023-24 | This action is complete but a resulting CUSC modification is still in flight. CMP408 (amending the notice period) is awaiting a decision from Ofgem alongside CMP415 which looks at the fixed period following the analysis carried out through the CMP408 workgroup and the Enduring Fixed BSUoS subgroup. This sub-group is now on pause as it was agreed to wait for a decision on the aforementioned modifications and collect further data before raising any more modifications. This sub-group has received really positive feedback for the discussion it provided across industry, and the analysis that was shared. CMP420 was raised by industry and we are working with the workgroup to support the proposer developing a solution.
2 | Code management / market development and change | D6.1.6 | Support Market Wide Half Hourly Settlement | Code modifications concluded | Q1 2024-25 | Delayed - External Reasons |  | A revised MHHS Programme plan with associated milestones was approved by Ofgem following extensive industry consultation in 2023. This will implement MHHS Code change in March 2025. Ofgem have confirmed that CUSC Modifications should be managed outside the scope of the MHHS Programme and Settlement Reform SCR. CUSC Modifications (CMP430 and 431) have been raised in February and will be progressed to an urgent timeline to ensure Ofgem are able to make a decision by September 2024 for implementation in April 2025. Workgroup meetings are progressing well and in accordance with the timeline agreed as part of the urgency request. The Final Modification Report in on track to be submitted to Ofgem for decision following August CUSC Panel. ESO has fed back on code drafting under the BSC that impacts on ESO processes as part of the MHHS code drafting consultation process. This will follow MHHS Programme timescales to be approved by the Cross Code Advisory Group in August 2024 and then the subsequent SCR process.
2 | Code management / market development and change | D6.1.6 | Support Market Wide Half Hourly Settlement | Produce required CUSC legal text and modifications raised | Q2 2023-24 | Delayed - External Reasons |  | A revised MHHS Programme plan with associated milestones was approved by Ofgem following extensive industry consultation in 2023. Ofgem have confirmed that CUSC Modifications should be managed outside the scope of the MHHS Programme and Settlement Reform SCR. CUSC Modifications (CMP430 and 431) have been raised in February and will be progressed to an urgent timeline (subject to Ofgem granting urgent status) to ensure Ofgem are able to make a decision by September 2024 for implementation in April 2025. Proposed legal text will be complete for inclusion in the Final Modification Report which will be submitted to Ofgem following August CUSC Panel.
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Regulatory priorities, system maintenance and functional backlog implemented | Q1 2023-24 | Complete | Q1 2023-24 | 22/6: Q1 regular system maintenance and backlog management in place
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Enduring team established to maintain new system (Q2), System maintenance and backlog management (Q3), Regulatory priorities and customer improvements implemented (Q4) | Q4 2023-24 | Complete | Q4 2023-24 | 22/3: BAU team established, Q4 regular system maintenance and backlog management in place, regulatory changes and enhancements implemented
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | System maintenance, regulatory priorities, customer enhancements and functional backlog management | Q1 2024-25 | Complete | Q1 2024-25 | 20/06 - The STAR business as usual team is set up to perform regular system maintenance activities. The STAR project teams works with relevant teams across ESO to track emerging regulatory changes and customer feedback alongside prioritising its functional backlog. Reprioritisation and review of the Roadmap and this backlog occurs on a regular basis.
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | System maintenance, regulatory priorities, customer enhancements and functional backlog management | Q2 2024-25 | On track |  | 18/07 - The STAR business as usual team is set up to perform regular system maintenance activities. The STAR project teams works with relevant teams across ESO to track emerging regulatory changes and customer feedback alongside prioritising its functional backlog. Reprioritisation and review of the Roadmap and this backlog occurs on a regular basis.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | High Level Discovery | Q2 2023-24 | Complete | Q2 2023-24 | Impact Assessment completed for Market-wide Half Hourly Settlement (MHHS) changes required to the data file (TUoS Report or P0210) provided from Elexon to the ESO for TNUoS and BSUoS forecasting and billing.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Impact Assessment & Agree Approach | Q3 2023-24 | Delayed - Internal Reasons |  | Approach to receipt of data for TNUoS Charging agreed under the sign-off of MHHS Change Request 32. Approach and timing of testing for this to be agreed between MHHS Programme, Elexon and ESO. Approach to process for management of disputes relating to BOAs agreed and solution will be reflected in MHHS BSC Legal Text. Impact Assessment for direct impacts of MHHS has been baselined. A full impact assessment of consequential impacts of MHHS has not been completed yet. For example, changes to Supplier Time of Use Tariff offerings and therefore consumer behaviour and their associated impacts to system balancing have not been fully impact assessed. This will be developed and monitored across the months up to MHHS migration (Apr-25) and across the MHHS Migration period (Apr-25 to Oct-26).
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and implement | Q4 2023-24 | Delayed - External Reasons |  | MHHS Programme milestones re-baselined. Design and test activity to be undertaken by the ESO on track and in line with Ofgem-approved MHHS Programme baselined plan. ESO participation in industry System Integration Testing scheduled for MHHS Programme cycle 2, currently September 2024. ESO is continuing to work with the MHHS Programme and Elexon under MHHS governance.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q1 2024-25 | Delayed - External Reasons |  | MHHS Programme milestones re-baselined. Design and test activity to be undertaken by the ESO on track and in line with Ofgem-approved MHHS Programme baselined plan. ESO participation in industry System Integration Testing scheduled for MHHS Programme cycle 2, currently September 2024. ESO is continuing to work with the MHHS Programme and Elexon under MHHS governance.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q2 2024-25 | Delayed - External Reasons |  | MHHS Programme milestones re-baselined. Design and test activity to be undertaken by the ESO on track and in line with Ofgem-approved MHHS Programme baselined plan. ESO participation in industry System Integration Testing scheduled for MHHS Programme cycle 2, currently September 2024. ESO is continuing to work with the MHHS Programme and Elexon under MHHS governance.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q3 2024-25 | On track |  | MHHS Programme milestones re-baselined. Design and test activity to be undertaken by the ESO on track and in line with Ofgem-approved MHHS Programme baselined plan. ESO participation in industry System Integration Testing scheduled for MHHS Programme cycle 2, currently September 2024. ESO is continuing to work with the MHHS Programme and Elexon under MHHS governance.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q4 2024-25 | On track |  | MHHS Programme milestones re-baselined. Design and test activity to be undertaken by the ESO on track and in line with Ofgem-approved MHHS Programme baselined plan. ESO participation in industry System Integration Testing scheduled for MHHS Programme cycle 2, currently September 2024. ESO is continuing to work with the MHHS Programme and Elexon under MHHS governance.
2 | Industry revenue management | D6.3.2 | TNUoS reform | High Level Discovery | Q1 2023-24 | Delayed - External Reasons |  | ESO Revenue team has shortlisted defects (considered by Task Force) for review, and have allocated these to categories (to progress as packages of work), we are aiming to create a workstream plan using the categories. The general delay against the business plan, is related to the complexity and volume of work contained within the Task Force, there is still on going analysis to determine if there are any further modifications that need to be raised to achieve the TNOUS Task Force objectives, until all modifications have been raised and significantly progressed through the code governance process, the ESO can not confidently conduct technical system discovery work to progress to plan.
2 | Industry revenue management | D6.3.2 | TNUoS reform | Impact Assessment & Agree Approach | Q2 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone High level Discovery (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q3 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q4 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q1 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q2 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q3 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q4 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | We are working on our internal capability to ensure we set ourselves up best to be a code manager. This includes: • Working on Code Digitalisation to improve the usability and navigation of our codes • Further proactive engagement with industry parties proposing changes to the codes we administer, seeking to ensure these are clear and value adding / raised at the optimum time" • Further enhancing our chairing and project management capability to ensure we maximise the value of all our stakeholder engagements notably at modification Workgroups and code Panels • Continuous improvements to our reporting, ensuring this is clear and understandable | Q4 2023-24 | Delayed - External Reasons |  | We have begun a programme to design a process for the ESO to fulfil the role of code manager. We have presented to OFGEM on our thoughts and ideas around the code manager process and how we feel we could facilitate this change. This includes - strategic road map of ideas and process flow -presentation to OFGEM -feedback requested on our thoughts, ideas and process -overlaying our new process with some previous modifications to demonstrate the difference that would have been made if followed -presentation to CUSC and GC panel on our thoughts and ideas of code manager -Specific relevant training courses for the team provided by external facilitators - Further embedding on the job training and internal processes - Breakdown of the current code and team process and review areas for further improvement - Customer and Stakeholder engagement and feedback to further improve communication
2 | Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | We are working on our internal capability to ensure we set ourselves up best to be a code manager. This includes: • Working on Code Digitalisation to improve the usability and navigation of our codes • Further proactive engagement with industry parties proposing changes to the codes we administer, seeking to ensure these are clear and value adding / raised at the optimum time" • Further enhancing our chairing and project management capability to ensure we maximise the value of all our stakeholder engagements notably at modification Workgroups and code Panels • Continuous improvements to our reporting, ensuring this is clear and understandable | Q4 2024-25 | On track |  | we have responded to two consultations led by Ofgem discussing the transition from code administrator to code manager and energy code reform. We have views on code consolidation and what the process would mean to be a code manager and have responded accordingly. we await further feedback from Ofgem on the next steps with our engagement around our thoughts and ideas on this subject.
2 | Work with all stakeholders to create a fully digitalised Whole System Technical Code by 2025 | D6.5 | Develop a single technical code for distribution and transmission that is focused on providing minimum standards to allow safe and secure operation of the electricity systems. | Prioritise and raise modifications as identified through example work | Q4 2023-24 | Complete | Q4 2023-24 | Grid code modification focused on the the simplification and rationalisation of section OC2 of the grid code has been submitted and is a live modification. The digitalisation side of the project is currently progressing to plan.
2 | Work with all stakeholders to create a fully digitalised Whole System Technical Code by 2025 | D6.5 | Develop a single technical code for distribution and transmission that is focused on providing minimum standards to allow safe and secure operation of the electricity systems. | Progress modifications | Q4 2024-25 | On track |  | Following extensive engagement with stakeholders, a clear scope for the Grid Code digitalisation project was defined. The project team worked to create a simple and accessible Grid Code. Ongoing feedback was sought, along with User Acceptance Testing at key stages of the project. The Minimum Viable Product was successfully released in May 2024, with additional enhanced features being added iteratively post go-live. Creation of a more efficient, simplified Code is in flight. ESO worked with industry experts via an ad-hoc working group, as well as with the dWSTC steering group, which is an industry wide team of experts that provides strategic direction to this work. The groups prioritised sections of the Grid Code that could benefit from simplification and rationalisation. An industry survey was also carried out to canvas industry views. One modification (GC0164) to simplify and rationalise Operating Code Nr.2 (OC2) of the Grid Code has been raised and is currently out for workgroup consultation. Preparatory work on modifications to the Data Registration Code (DRC), Balancing Codes 4 (BC4) and 5 (BC5) is being progressed. Modifications to the latter could be progressed in Q3 of 2024. This is on the back of regular engagement with industry at ESO and industry forums to gather input on proposed solutions and reporting on project progress. Further work on consolidation should be descoped due to Energy code reform.
2 | Fixed BSUoS tariff setting | D6.7 | Enhanced delivery of the recommendation from the BSUoS taskforce around reducing the volatility of BSUoS forecasting. | Continued investment in our forecasting capability and build on our existing capability for BSUoS forecasting. | Q4 2024-25 | Continuous activity |  | Following on from the work that we did last year with the Hartree Centre, to investigate whether state-of-the-art machine learning techniques could be employed to improve our forecast of balancing costs, we implemented the prophet model into the BSUoS forecasting system in April. We ran a webinar on the 17th April 2024 to present the changes and this was well attended and well received by a range of industry parties. We received positive feedback on both the changes being made and the webinar.
2 | Digitalisation of codes | D6.8 | Implementation of digital solutions | Implementation has commenced | Q4 2023-24 | Complete | Q4 2023-24 | There were slight delays to the project due to the project experiencing several challenges with correctly provisioning suitable testing environments within our chosen technology stack, Azure 2.0. To ensure that this con be resolved effectively we are therefore moving our go-live date to no later than 15th May 2024. Whilst these issues are being resolved we continue to work on Phase 2 of the project, including GenAI and Workflow management which in turn should help with the time delays in completing this early. The Digital Code management (DCM) project delivers the ESO the technology capability to make industry codes accessible and consumable for customers. It will transform customer experience for the code management process through: - Digitalisation of codes - Contextual guidance and relevance for customers - Provision of enhanced navigation capabilities - Greater clarity on relevant sections using metadata tagging, document and workflow management tools Project Progress to date: - Project setup/stakeholder engagement - Scoping - Industry Engagement & User Research - Requirement definition - Conceptual Solution Design
2 | Digitalisation of codes | D6.8 | Implementation of digital solutions | Implementation is complete | Q4 2024-25 | On track |  | There are slight delays to the project due to the project experiencing several challenges with correctly provisioning suitable testing environments within our chosen technology stack, Azure 2.0. To ensure that this can be resolved effectively we are therefore moving our go-live date to no later than 15th May 2024. Whilst these issues are being resolved we continue to work on Phase 2 of the project, including GenAI and Workflow management which in turn should help with the time delays in completing this early. The Digital Code management (DCM) project delivers the ESO the technology capability to make industry codes accessible and consumable for customers. It will transform customer experience for the code management process through: - Digitalisation of codes -internal workflow for internal procedures and code updates to mitigate compliance risks - Contextual guidance and relevance for customers - Provision of enhanced navigation capabilities - Greater clarity on relevant sections using metadata tagging, document and workflow management tools Project Progress to date: - Project setup/stakeholder engagement - Scoping - Industry Engagement & User Research - Requirement definition - Conceptual Solution Design
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Full assessment delivery areas | Q2 2024-25 | On track |  | Initial areas for assessment identified and early plans developed. We are seeking to align this work with key strategic industry objectives to drive most value from this process. Some areas of assessment are already being progressed based on alignment with other key priorities as part of BP2 e.g. DER Visibility and MHHS. Work in these areas are driven by individual separate project/programme timelines.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Establish team to deliver assessment of frameworks | Q3 2023-24 | Complete | Q3 2023-24 | Team members started Nov-23 with one remaining vacancy to be filled in Q4 23-34 in line with resource requirements.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Detailed workplan and stakeholder engagement | Q4 2023-24 | Delayed - Internal Reasons |  | Whilst we have established the Whole System Framework Team, the onboarding process took slightly longer than expected resulting in a delay to creating the detailed workplan and stakeholder engagement activities. Potential areas for assessment and inclusion in the team workplan have been identified and some high level information was shared at the Markets Forum in May. Further delays to more detailed stakeholder engagement activity has been caused by resource working on other urgent priorities under BP2. More detailed stakeholder engagement is now planned for Q2 24/25. Work has already begun on assessment of some of the areas that will be set out in the detailed workplan, based on priorities in other areas of BP2.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Identify and raise or recommend changes | Q4 2024-25 | On track |  | Activity not yet due to start. Assessment of framework areas that is an input into this activity is on track.
2 | Net zero market reform programme | D20.1 | Net Zero Market Reform programme | Be a trusted Partner to BEIS, Ofgem and the wider industry in this space. Ensuring the right market reforms to achieve net zero efficiently is a hugely complex challenge, with many interdependencies and a raft of future uncertainties. | Q4 2024-25 | Continuous activity |  | We continue to be a trusted partner to DESNZ and Ofgem in the REMA process. ESO is a formal partner in the REMA programme, leading on the REMA 'dispatch' workstream and feeding into multiple others, including zonal and national pricing, cross-border trading, CFD and CM reform, cross-cutting strategy and implementation. Our dispatch workstream will reach a recommendation for the July REMA programme board, to then be taken into consideration in wider REMA market design packaging that will be modelled over the summer. This work has undertaken significant industry engagement.
2 | Setting the net zero cross border landscape | D21.1 | Cross-border strategy development | First phase of implementation fully initiated | Q2 2023-24 | Complete | Q2 2023-24 | By modelling the cross border conditions for a number of future scenarios, ESO better understands how the needs of the GB net zero power system can be supported by interconnection, which is expected to significantly increase in capacity. This analysis identified future risks and opportunities that create value specifically in term of adequacy, operability and system adequacy. These areas of work have been prioritised so the highest value items can be focused upon. The output includes the identification of further research and development work packages needed to further define the final solutions to implement. A final draft for comment was shared with Ofgem and DESNZ in September 2023.
2 | Setting the net zero cross border landscape | D21.1 | Cross-border strategy development | Conclusions and recommendations reviewed to check if they are still relevant | Q4 2024-25 | On track |  | Delivery plan defined and initial drafting and internal engagement started.
2 | Setting the net zero cross border landscape | D21.1.1 | Strategic Engagement with EU | UK/ EU TSO cooperation channels will be fully opened and functioning well | Q1 2023-24 | Delayed - External Reasons |  | Until the Trade and Cooperation Agreement Working Arrangements is approved by the EC and DESNZ, it cannot be implemented by ENTSO-E and GB TSOs. The Working Arrangements agreement will allow the formal re-engagement between GB TSOs and the EU TSOs. However, in the interim informal engagement is underway with ENTSO-E and EU TSOs in a number of key areas including North Sea Cooperation (inc Offshore and MPIs), interconnector ramping limits, operational harmonisation and IC flow control tools.
2 | Setting the net zero cross border landscape | D21.1.1 | Strategic Engagement with EU | Engagement established with new EU stakeholder groups | Q1 2024-25 | Complete | Q1 2024-25 | Outside ENTSO-E channels, EU engagement and cooperation channels have been established with a range of EU organisations such as CORESO and the Renewable Grid Initiative. Bilateral channels have been developed with interconnected TSOs such as EirGrid, Statnett, RTE, TenneT and 50 Hertz. ESO has also commenced active support for the North Sea Energy Cooperation via support for the Ostend Declaration works. Prior to formal approval is given for the TCA Working Arrangements, pre-emptive EU/ GB engagement has been undertaken by ESO via a number of ENTSO-E groups including Inter Synchronous Area sub group (GB - EU operational interactions) and the Regional Group North Sea (Offshore and onshore Network planning).
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Draft Interconnector Framework shared with industry | Q1 2023-24 | Delayed - Internal Reasons |  | The ESO has released and RFI on interconnector frameworks External engagement will take place ahead of industry consultation. This was re-prioritised to allow other work within the team take place earlier this year such as NTC and DFS derogation.
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Ramping solution is SOGL compliant | Q2 2023-24 | Complete | Q4 2023-24 | The ESO has been working with an external consultant (Baringa) to carry out a CBA for interconnector ramping. This CBA has helped shape the ESO recommendation, which is to reduce interconnector ramp rates from 100MW/Min to 50MW/Min. This recommendation has been presented to the workgroup. The workgroup will propose an alternative. Process steps outlined below. Delay to original timeline is due to interconnector requests for other areas to be considered. Workgroup consultation July 2023 Workgroup report September 2023 Code Administrator Consultation October 2023 Modification Report December 2023. Report to be issued to Ofgem Dec 23- await a decision from Ofgem. Decision date to be confirmed and will update ticket to reflect this. Work group work is complete as it stands. Estimated decision date is 3rd March 2024> Decision date 15th March- Ofgem advised to implement 100MW/min - WACGM1. ESO is SOGL compliant
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Interconnector framework consulted upon | Q3 2023-24 | Complete | Q3 2023-24 | Interconnector Framework RFI is now out, closing 7th December. Reviewing responses and carrying out workshops internally and externally to develop scope
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Long-term ramping solutions are investigated | Q4 2023-24 | Delayed - Internal Reasons |  | Following the GC154 workgroup we will continue to work with the interconnector owners and EU TSOs to identify longer term arrangements as well as investigating improvements to Ramping across the GB networking.
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Interconnector Framework implementation plan agreed Long-term ramping solution implementation started | Q4 2024-25 | On track |  | Interconnector framework implementation plan to follow from consultation phases i n 23/24 when further stakeholder engagement has taken place. Long term ramping solutions following the GC0154 workgroup will start. To support this and future implementation - will work with impacted industry stakeholders.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Agreed UK Position on Day ahead, actively negotiating with EU TSOs Agreed Interim solution to cross border balancing at UK and EU level. Increased amount of engagement with EU TSOs | Q1 2023-24 | Delayed - External Reasons |  | Day Ahead Capacity Calculation (DACC) delayed due to limited engagement from EU TSOs on Capacity Calculation. EU TSOs likely to need a definitive steer from the Specialised Committee of Energy (SCE) in order to commit resources to DACC. The focus of the SCE steer during 2023 was in relation to MRLVC (Multi Region Loose Volume Coupling), which is Day Ahead Capacity Allocation. The next direction from the SCE / DESNZ is likely to be around further work on MRLVC. Interim Cross Border Balancing (CBB): On hold due to limited appetite from EU TSOs for such a product. RTE (the French TSO) has indicated they do not have resources for this.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Draft UK Position on Intraday and Long Term. Continued development of Day Ahead arrangements | Q3 2023-24 | Delayed - External Reasons |  | Delayed due to limited engagement from EU TSOs on Capacity Calculation. UK and EU TSOs will prioritise Day Ahead timeframes over other timeframes (i.e. Intraday and Long Term).
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | UK position on enduring balancing options agreed with all relevant parties | Q4 2023-24 | Complete | Q4 2023-24 | Cost Benefit Analysis of CBB options completed. Agreed plan with DESNZ and Ofgem over summer 2023 for industry engagement to publish results. Held CBB industry webinar on 19th October 2023 to disseminate results, which was well attended. Finalising internal close-down reports on this activity.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Interim solution being implemented pending recommendation from the specialised committee on energy | Q1 2024-25 | Delayed - External Reasons |  | Interim Cross Border Balancing (CBB): On hold due to limited engagement from relevant TSOs.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Noticeable step change in ESO to EU TSO relationships | Q2 2024-25 | On track |  | Initiation of EU Harmonisation meetings (ISA or Inter-Synchronous Area) - monthly meetings alternately in-person and online, including Amsterdam in October 2023. Next planned in-person meeting in Brussels April 2024. These meetings provide a forum for ESO to raise issues of concern / interest from our side, and understand concerns and developments from connected EU TSOs. Feb 2024 ESO raised the issue of Grid Forming requirements on cross-border interconnectors; EU TSOs pleased that we raised this as an issue for mutual discussion. Bilateral meeting in Dublin between ESO and EirGrid in November 2023, following the UK-Ireland MOU on energy transition. Subsequent meeting took place online in March 2024. Recent EU-UK TSO cooperation on MRLVC (Multi Region Loose Volume Coupling) technical questions (Feb - June 2023). Awaiting further direction on MRLVC following Specialised Committee of Energy (SCE) meeting in November 2023. ESO representatives attended the 9th annual energy cross-border trading and balancing market forum in Berlin in Feb 2024.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Technical UK position agreed and negotiating with EU TSOs Enduring solution agreed at UK Level, ongoing negotiations with EU | Q4 2024-25 | On track |  | Awaiting further guidance following CBB CBA results.
2 | Enhancing cross border frameworks and markets | D21.2.3 | Enhancing interconnector operations and access to Great Britain markets | A review of existing interconnector operations in light of the transition to a highly interconnected system. Consider cross border roles within future GB ancillary services markets. | Q4 2024-25 | Continuous activity |  | In October 2023, ESO ran an industry workshop looking at the results of a cost benefit analysis , completed by Compass Lexecon, for potential cross-border balancing solutions under a range of plausible future scenarios.
3 | Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Undertake enhancements to ETYS Annual Report in response to stakeholder feedback. | Q1 2023-24 | Complete | Q1 2023-24 | The Annual ETYS consultation was completed on 15th May 2023 and we submitted the proposed Form of ETYS 2023 to Ofgem on 1st June 2023. This includes proposed improvements to the document based on feedback received over the past year.
3 | Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | ETYS Annual Report Published part of the Transitional Centralised Strategic Network plan Year-round Thermal needs published in ETYS Voltage screening results in ETYS | Q4 2023-24 | Complete | Q4 2023-24 | ETYS 2023 was successfully published on 29th August 2023. For the first time this year we have successfully brought forward publication of core content to allow our stakeholders more time to review system needs in advance of the Cost Benefit Analysis. The publication includes year-round thermal analysis and our voltage screening results in line with our commitment to expand our system needs. On 30th November we published ETYS appendix A (Existing Network diagrams), E (Fes charts), F (Contracted Generation), G (Nodal Demand), H (further information) and I (Transmission losses). Remaining elemnts were publicshed with the TCSNP2 in March 2023 - ETYS technical appendices B, C, D which contain future network data to align with the TCSNP2.
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | Start Engagement with Ofgem on the long-term requirement for Interconnector Analysis | Q1 2023-24 | Complete | Q1 2023-24 | We have started ongoing engagement with Ofgem in relation to our interconnector analysis for both the NOA and Cap & Floor Window 3.
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | Approval of Revised NOA Methodology | Q3 2023-24 | Complete | Q3 2023-24 | The draft methodology submitted to Ofgem on the 30th June 2023 has been has now been approved by Ofgem. This is now complete
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | NOA Annual Report Published, part of the Transitional Centralised Strategic Network plan | Q4 2023-24 | Complete | Q4 2023-24 | The NOA report has been subsumed within the Beyond 2030 report published on the 19th March 2024.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Review LOTI Process with Ofgem and Stakeholders to learn from the first two years of undertaking assessments | Q1 2023-24 | Complete | Q3 2023-24 | We have consulted with Ofgem and the Transmission Owners on how the first two years of LOTI cost-benefit analysis has gone. This yielded an average customer satisfaction score of 7.8 out of 10. Key commentary is summarised below. Positives: - The reports are clearly laid out, well presented and completed on time. Technical concepts, such as Least Worst Regret are well explained and outcomes are accompanied by suitable justification. This allows the TOs to comment in a meaningful way on the ESO report. - The ESO is open on analysis methodologies and approaches ensuring appropriate analysis is done for each study. Likewise the report is flexed to pull out study specific insights. Potential enhancements: - Expand the analysis to include social-economic and carbon benefits [ESO: This has been implemented for CNSP since the LOTI process was introduced] - A simpler exec summary as the technical content, while well explained, is still difficult for all readers to understand. - It is not clear from the report whether the ESO is challenging the TOs input. ESO could add text to the report on any engagement it had with the TOs where assumptions were challenged or changed.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q2 2023-24 | Complete | Q2 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q3 2023-24 | Complete | Q3 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q4 2023-24 | Complete | Q4 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q1 2024-25 | Complete | Q1 2024-25 | We continue to undertake LOTI cost-benefit analysis as and when required. This quarter we have been approached by the TOs in regards to a number of projects and have helped scope the studies. Economic analysis for these are expected in June, July and August.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q2 2024-25 | On track |  | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q3 2024-25 | On track |  | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q4 2024-25 | On track |  | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | EC5 tender run | Q3 2023-24 | Delayed - Internal Reasons |  | Enduring tender now launched to the market, and is expected to conclude in September 24, for service to begin in April 25. The delay was due to the review of the service design to ensure we considered the range of possible solutions i.e. DNO connected and offshore assets, to increase competition and achieve best value for consumers. Time from tender completion until service start is for contracted generators to be connected to the tripping scheme by NGET, which relies on NGET having completed any necessary upgrade works to the substations and circuits where works are required.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | Constraint Management Pathfinder B6 year 3 tender | Q3 2023-24 | Delayed - Internal Reasons |  | We have utilised the one year extension option from the B6 year 2 tender which will ensure that the current service will be in place until September 2026. This is so that we can prioritise a review of the outcome of the ongoing tCSNP studies to determine any future constraint requirements, and focus on regions that will deliver most consumer benefit i.e. regions with high forecast constraint costs.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | Constraint Management Pathfinder B6 year 2 service start date | Q3 2024-25 | On track |  | This service is on schedule to start on time.
3 | Early Competition | D8.4 | Early Competition | Majority of commerical model elements delivered to Ofgem for approval (TRS, PPWCA) | Q1 2023-24 | Complete | Q2 2023-24 | Commercial model submitted to Ofgem.
3 | Early Competition | D8.4 | Early Competition | First generic tender documents and processes delivered to Ofgem to be approved | Q2 2023-24 | Delayed - External Reasons |  | Revised timetable agreed with Ofgem based on their inputs to the project.
3 | Early Competition | D8.4 | Early Competition | Early Competition contract completed and aligned with relevant licence obligations | Q3 2023-24 | Delayed - External Reasons |  | No longer required. agreed with Ofgem
3 | Early Competition | D8.4 | Early Competition | Implementation complete Project identified for first competition | Q4 2023-24 | Delayed - External Reasons |  | Revised timetable agreed with Ofgem based on their inputs to the project.
3 | Early Competition | D8.4 | Early Competition | Launch the first Early Competition tender | Q4 2024-25 | Delayed - External Reasons |  | Revised timetable agreed with Ofgem based on their inputs to the project.
3 | Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Integration with our network assessment tools | Q3 2023-24 | Complete | Q3 2023-24 | We have refreshed the economic assessment tools that we use to interact with our pan-European market dispatch model. This was done alongside the deployment of our new pan-European market dispatch model. The new model gave us new opportunities to enhance and integrate our tools, for example, by developing them in Python and integrating them with the pan-European dispatch tool via its API.
3 | Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Full integration with Data and analytics platform complete, enabling a joined- up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | On track |  | We have started to update our economic assessment tool so that it can be used to undertake more types of analysis across the end to end strategic energy planning process. This includes data and model enhancements to allow the delivering of the Spatial Strategic Energy Plan the result of which will feed in to the Central Strategic Energy Plan. By using a consistent economic assessment tool we will be able to use it for joined up analysis across different network needs and at multiple levels of granularity as appropriate for each ESO deliverable.
3 | Implement probabilistic modelling | D11.2 | Improved identification of network needs | Developed and implemented digital experience platform. This will provide an interactive platform to allow stakeholders to view network needs and see the impact selected generic options will have on addressing those needs from a technical perspective. | Q4 2023-24 | Complete | Q4 2023-24 | We have transformed the way we publish our probabilistic results. This year we have published our results on the ETYS portal with interactive plots and maps. We are continuously working to improve the way we publish our results and findings to engage our stakeholders more effectively.
3 | Implement probabilistic modelling | D11.2 | Improved identification of network needs | Full integration with Data and analytics platform complete, enabling a joined-up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | On track |  | Our in-house tool, POUYA, has gone live and we have started working closely with DAP for the full integration.
3 | Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Implemented VO tool and identified further enhancements. | Q4 2023-24 | Complete | Q4 2023-24 | We have successfully launched the first version of the tool on cloud meeting all BP2 requirements. We have collected improvement idea and new requirements and are planning to release incremental updates with additional capabilities.
3 | Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Full integration with Data and analytics platform complete, enabling a joined- up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | On track |  | We have started working with the DAP team for the full integration.
3 | Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Proof of concept for a stability screening tool | Q4 2023-24 | Complete | Q3 2023-24 | We have completed the POC on the stability screening tool.
3 | Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Implement stability screening tool | Q4 2024-25 | On track |  | We have started development of the solution and the delivery is on track.
3 | Identify solutions | D12.2 | Potential solutions identified and direction established | Based on the prioritised list of issues, changes are initiated for the high-priority items and potential solutions are developed. | Q1 2023-24 | Complete | Q1 2023-24 | The list of SQSS changes have been reviewed and discussed with relevant stakeholders, new priorities have been established to all the topics.
3 | Identify solutions | D12.2 | Potential solutions identified and direction established | Based on the prioritised list of issues, changes are initiated for the low-priority items and potential solutions are developed. | Q3 2024-25 | On track |  | Modification on system resilience has been approved. CATO GSR031 has been submitted to ofgem for approval. P2 alignment, MITS and offshore modification are ongoing, and potential solutions are being identified.
3 | Implement changes to the SQSS | D12.3 | Key changes to SQSS made or in progress | Based on the prioritised list of issues, changes are made or in progress for the high-priority items. | Q3 2023-24 | Complete | Q3 2023-24 | A few modifications are going, and potential solutions are being identified.
3 | Implement changes to the SQSS | D12.3 | Key changes to SQSS made or in progress | Based on the prioritised list of issues, changes are made or in progress for the low-priority items. | Q4 2024-25 | On track |  | Modification on system resilience has been approved. CATO GSR031 has been submitted to ofgem for approval. P2 alignment, MITS and offshore modification are ongoing, and potential solutions are being identified.
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Summer Outlook Report Publication of Winter Review & Consultation | Q1 2023-24 | Complete | Q1 2023-24 | 2022 Summer Outlook Report published on 13 April. 2022/23 Winter Review and Consultation published 15 June alongside an early view of winter 2023/24
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of FES suite of documents (including data) | Q2 2023-24 | Complete | Q2 2023-24 | 2023 FES was published on the 10th July.
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Winter Outlook Report | Q3 2023-24 | Complete | Q2 2023-24 | 2023/24 Winter Outlook Report expected to be published on 28 Sep
2 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Summer Outlook Report Publication of Winter Review & Consultation | Q1 2024-25 | Complete | Q1 2024-25 | Summer Outlook published April 2024; Winter Review published June 2024
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of FES suite of documents (including data) | Q2 2024-25 | On track |  | Launch date delayed to July 15th following pre-election period
2 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Winter Outlook Report | Q3 2024-25 | On track |  | 2024/25 Winter Outlook expected to be published in Q3 2024-25 in line with well-established annual processes
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2 | Update pan-European and country level electricity and energy demand models | Update electricity our supply and demand data for several European countries to reflect the changes within the EU as they continue to evolve their economies to meet net zero decarbonisation. The European countries to model include those that are interconnected to the GB market in addition to a number of additional countries which, whilst further away, still have an impact on the GB market. Data to be benchmarked against the latest Ten Year Network Development Plan from ENTSO and incorporated within our pan-European dispatch model so that the FES, EMR and NOA analysis benefit from it. | Q4 2024-25 | Continuous activity |  | Due in 2025
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Starting to work with Local Authorities to understand the feedback loop between FES / Distribution scenarios / Local Area Energy Plans. Starting to work with gas networks to agree the granular breakdown of FES scenarios (Natural Gas and Hydrogen) | Q1 2023-24 | Complete | Q1 2023-24 | Work has started to understand the Feedback loop between FES / DFES and Local Area Energy Plans and the granular breakdown of FES scenarios (Natural Gas and Hydrogen) Engagement with the network companies has commenced through the network forum and bilateral discussions. The Call for Evidence for FES 2023 requested stakeholder views on the feedback loop and the regional breakdown of our gas and hydrogen pathways which included engagement with both network companies and local authorities. A project has been kicked off to understand the potential role for the FSO as Regional System Planner. This has included direct engagement with Local Authorities.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Whole system regional data and insights provided alongside FES in July Enhanced visualisation launched. Regional data and visualisations added to our Website throughout the year as a appropriate and alongside the annual FES launch User configurable FES view available for Electricity supply and Demand | Q2 2023-24 | Complete | Q2 2023-24 | FES 2023 was launched on July 10th which included regional data and insights. Our visualisation platform was updated alongside the FES and included a user configurable interface for Electricity supply and demand.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Whole system regional data and insights provided alongside FES in July Enhanced visualisation launched. Regional data and visualisations added to our Website throughout the year as a appropriate and alongside the annual FES launch User configurable FES view available for Electricity / Gas / Hydrogen supply and Demand | Q2 2024-25 | On track |  | Regional data, insights and visualisation to be published alongside the FES ahead of the September BP2 deadline
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q1 2023-24 | Complete | Q1 2023-24 | Launch date communicated early with Ofgem and in line with previous years. Launched on 10 July as agreed.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES suite of documents (including data) | Q2 2023-24 | Complete | Q1 2023-24 | Complete - Launched 10th July 2023
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q3 2023-24 | Complete | Q3 2023-24 | On track and forms part of our ongoing engagement plan Published additional changes document in September.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q4 2023-24 | Complete | Q3 2023-24 | Complete - Stakeholder Feedback Document submitted to Ofgem and formal acceptance received that it meets licence condition. Minor updates agreed following further feedback.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q1 2024-25 | Complete | Q1 2024-25 | Published framework development document
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES suite of documents (including data) | Q2 2024-25 | On track |  | Launch date delayed to July 15th following pre-election period
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q3 2024-25 | On track |  | On track and will form part of our engagement plan for the year
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q4 2024-25 | On track |  | On track and will form part of our engagement plan for the year
3 | FES: Bridging the gap to net zero | D13.4 | Bridging the Gap - produce evidence-based recommendations to support development of net zero policy | Delivery of a stakeholder informed report with recommendations for near term actions for net zero. | Q4 2023-24 | Complete | Q4 2023-24 | Focussing on enablers and dependencies for accelerating heat decarbonisation - closing webinar 28th Feb
3 | FES: Bridging the gap to net zero | D13.4 | Bridging the Gap - produce evidence-based recommendations to support development of net zero policy | Delivery of a stakeholder informed report with recommendations for near term actions for net zero. | Q4 2024-25 | Milestone no longer valid |  | Decision taken to focus on Advisory role over this activity in 24/25
2 | FES: Integrating with other networks and supporting DNOs to develop their own DFES processes | D13.5.3 | Enhance our energy modelling to reflect stakeholder feedback and changes to the credible pathways to net zero | Development plan in place | Q4 2023-24 | Complete | Q4 2023-24 | Our energy modelling has been updated for FES24 to enhance our ability to reflect H2 supply locations. We are continuing to work through the modelling requirements to support CSNP with internal and external stakeholders.
3 | Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.1 | Managing an increasing volume of connection offers for customers | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | On track |  | Ongoing activity
3 | Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.2 | Contract management of connection agreements | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | On track |  | Ongoing activity
3 | Ensure Grid Code compliance of new connections | D14.2.1 | Compliance monitoring of new connections in accordance with Grid Code provisions | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | On track |  | Ongoing activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Run a new type of meeting as part of Connections process with DNOs and TOs focused on review of new connections still being processed by DNOs and suitability of DER as an option [at this point DER as a solution needs to be understood by all] | Q1 2023-24 | Complete | Q3 2023-24 | The ESO team is working seamlessly with the DNO community to push solutions forward for generation and demand sites that want to connect at a lower voltage level. We have a dedicated Demand team which has a sepcific account manager for each DNO, who is there to support in providing solutions to DER customers, in tandem with the relevant DNO. We have also increased resource to facilitate the work through the ENA led Strategic Connection Group, to help deliver greater capacity at a DNO level by assessing 'Technical limits' across the T/D interface. This is providing material benefit for DER applicants.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q2 2024-25 | On track |  | As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Request feedback from Customers and DNOs | Q3 2023-24 | Complete | Q3 2023-24 | This has been done in tandem with DNO colleagues through the SCG work. Furthermore, we run monthly webinars with the industry, which offers an opportunity to discuss their experiences and questions around our activities in the Connection space. We also look to host twice yearly, customer seminars - which brings the wider industry together.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q4 2024-25 | Complete | Q3 2023-24 | Complete - As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously deliver on the use of DER, learn lessons and implement improvements | Q1 2024-25 | Complete | Q3 2023-24 | Complete - As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q3 2024-25 | Complete | Q3 2023-24 | Complete - As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q1 2023-24 | Complete | Q1 2023-24 | Complete - seminars held with over 200 attendees
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q2 2023-24 | Complete | Q2 2023-24 | Complete - seminars held with over 200 attendees
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q3 2023-24 | Complete | Q3 2023-24 | Complete - seminars held with over 200 attendees
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q4 2023-24 | Complete | Q4 2023-24 | Complete - seminars held with over 200 attendees.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q1 2024-25 | Complete | Q1 2024-25 | Complete - seminars held with over 200 attendees.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q2 2024-25 | On track |  | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q3 2024-25 | On track |  | On Track - forum dates published on ESO website.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q4 2024-25 | On track |  | On Track - forum dates published on ESO website.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Submit IT investment paper through internal governance process and obtain approval of scope and expenditure Engage with customers on ways to improve connections journey and ways of enhancing the portal | Q1 2023-24 | Complete | Q1 2023-24 | Future releases of the Connections portal are planned and the functionality backlog has been agreed. Sessions with industry stakeholders are ongoing with some smaller targeted sessions with specific groups of stakeholders already held and larger stakeholder events planned for the end of July 2023.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Further develop concept of new register, platform and connection with other systems [salesforce and customer portal]; Liaise with relevant internal stakeholders to verify concept and requirements | Q2 2023-24 | Complete | Q2 2023-24 | The functionality for the Connections portal is constantly being developed, with more functionality being added every 2-3 months throughout the BP2 period. The functionality being added is underpinned by stakeholder feedback.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Further development and testing - engage with relevant focus groups | Q3 2023-24 | Complete | Q3 2023-24 | This is an ongoing activity. We are currently carrying out feature development sessions with industry parties such as; consultants, DNOs and TOs to enhance portal functionality.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Implementation of updates to ESO Portal | Q4 2023-24 | Complete | Q4 2023-24 | Complete as phase 1 is delivered.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Obtain feedback on the new platform from internal and external stakeholders | Q1 2024-25 | Complete | Q1 2024-25 | Stakeholder feedback sessions planned for July 2023 and functionality being introduced directly into the portal to obtain customer feedback.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q2 2024-25 | On track |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q3 2024-25 | On track |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q4 2024-25 | On track |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.5 | Improving our internal processes | Improved customer feedback indicating customers welcome changes to connections processes | Q4 2024-25 | Continuous activity |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.6 | Proposing future policy and code improvements | ESO has identified helpful policy and code changes, including ENA guidance and new ESO policies, which are supported by relevant stakeholders. Industry code modifications proposed. | Q4 2023-24 | Complete | Q4 2023-24 | We have completed all of our CAP (connections action plan) actions that were due before the end of Q4 2023-24. We continue to develop policies and tactical solutions to improve connections in line with the wider connections reform project. In addition we continue to support the policy and code changes that are being developed in conjunction with the ENA to help distribution projects
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.6 | Proposing future policy and code improvements | ESO has identified helpful policy and code changes, including ENA guidance and new ESO policies, which are supported by relevant stakeholders. Industry code modifications proposed. | Q4 2024-25 | Continuous activity |  | Ongoing Activity - We continue to develop policies and tactical solutions to improve connections in line with the wider connections reform project. In addition we continue to support the policy and code changes that are being developed in conjunction with the ENA to help distribution projects
3 | Facilitate development of the customer connections portal | D14.4.1 | Implement first phase of the ESO connections portal, including online account management and integration with other network organisation websites | Deliver changes based on customer feedback | Q1 2023-24 | Complete | Q1 2023-24 | Two further releases have been implemented since the launch of MVP in March 2023 including new functionality for calculation of application fees as well as other front end and back end enhancements.
3 | Facilitate development of the customer connections portal | D14.4.1 | Implement first phase of the ESO connections portal, including online account management and integration with other network organisation websites | Deliver changes based on customer feedback | Q2 2023-24 | Complete | Q2 2023-24 | Complete as phase 2 is delivered. We released specific features based upon customer feedback.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Submit revised IT investment paper through internal governance process and obtain approval of scope and expenditure | Q1 2023-24 | Complete | Q1 2023-24 | IT investment paper submitted
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Further develop concept of phase 2 deliverables and identify different stages of deliverables along with key stakeholders to work with | Q2 2023-24 | Complete | Q2 2023-24 | Future releases of the Connections portal are planned and the functionality backlog has been agreed. Sessions with industry stakeholders are ongoing with some smaller targeted sessions with specific groups of stakeholders already held and larger stakeholder events planned for the end of July 2023.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Development of concept designs | Q3 2023-24 | Complete | Q3 2023-24 | Complete as phase 2 is delivered.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Development of concept designs | Q4 2023-24 | Complete | Q4 2023-24 | Complete as phase 2 is delivered.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Review and UAT for scheduled deliverables in Q3 & Q4 | Q1 2024-25 | Complete | Q1 2024-25 | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Continuous development of further elements for later delivery | Q2 2024-25 | On track |  | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Delivery of elements of the phase 2; Continuous development of further elements for later delivery | Q3 2024-25 | On track |  | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Delivery of elements of the phase 2; Continuous development of further elements for later delivery | Q4 2024-25 | On track |  | Ongoing activity
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q1 2023-24 | Complete | Q1 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation and Grid Forming are ongoing, it will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q2 2023-24 | Complete | Q2 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, it will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q3 2023-24 | Complete | Q3 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q4 2023-24 | Complete | Q4 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q1 2024-25 | Complete | Q1 2024-25 | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q2 2024-25 | On track |  | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q3 2024-25 | On track |  | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q4 2024-25 | On track |  | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | Identify and initiate new innovation project | Q4 2023-24 | Complete | Q4 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | New innovation project delivered and learning has been captured in developing of SOF | Q4 2024-25 | On track |  | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14 | Q4 2024-25 | Continuous activity |  | Once the policy changes have been approved, they are reflected into the connection offers and agreements
3 | Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14 | Q4 2024-25 | Continuous activity |  | Once the policy changes have been approved, they are reflected into the connection offers and agreements
3 | Assess the technical implications of framework developments and implement changes into business procedures and systems | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one to another | Q4 2024-25 | Continuous activity |  | Once the policy and framework changes have been approved, they are reflected into the business procedures and process
3 | Assess the technical implications of framework developments and implement changes into business procedures and systems | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one to another | Q4 2024-25 | Continuous activity |  | Once the policy and framework changes have been approved, they are reflected into the business procedures and process
3 | Manage our operational data and modelling requirements | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | Delivery ETYS and NOA models | Q3 2023-24 | Complete | Q3 2023-24 | All 2023 ETYS Winter models completed (Years 1, 2, 4, 7, 9, 12) and released by 1st September 2023. Summer minimum Year 1 model released on 15/09/2023.
3 | Manage our operational data and modelling requirements | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | Delivery ETYS and NOA models | Q3 2024-25 | Continuous activity |  | Prepare for new requirements needed in 2024 ETYS Model
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q1 2023-24 | Complete | Q1 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q2 2023-24 | Complete | Q2 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q3 2023-24 | Complete | Q3 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q4 2023-24 | Complete | Q4 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q1 2024-25 | Complete | Q1 2024-25 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q2 2024-25 | Continuous activity |  | All legislative requirements fulfilled to the required standard
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q3 2024-25 | Continuous activity |  | All legislative requirements fulfilled to the required standard
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q4 2024-25 | Continuous activity |  | All legislative requirements fulfilled to the required standard
3 | Manage our operational data and modelling requirements | D15.4.3 | Automation of data exchange mechanism and preparation for CIM implementation | Identify initiative which will automate the data exchange mechanism Commence preparation for data exchange enhancements with network organisations | Q4 2023-24 | Complete | Q4 2023-24 | Woking on developing a new exchange node interface platform to facilitate interface points between Transmission Owner and DNO network data exchange with the help of DD & T. The extraction mechanism needs to be automated such that any change can be captured using an automated importing link into the offline toolsets.
3 | Manage our operational data and modelling requirements | D15.4.3 | Automation of data exchange mechanism and preparation for CIM implementation | Implementation of data exchange automation Prepared for data exchange enhancements with network organisations | Q4 2024-25 | On track |  | On track for delivery
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Testing and commissioning of first GEMS pilot boundaries | Q1 2023-24 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Design and integration of GEMS functionality with SPD ANM scheme. | Q2 2024-25 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland. This is expected to be covered by RDP6
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Expansion of functionality to further boundaries on a system needs basis. | Q4 2023-24 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Commissioning of first DER onto combined GEMS and SPD ANM functionality. | Q4 2024-25 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland. This is expected to be covered by RDP6
3 | Develop Regional Development Programmes (RDPs) | D15.5.2 | RDP2 of RIIO-2 (MW dispatch, South East, UKPN) | IT implementation phase complete | Q2 2023-24 | Complete | Q4 2023-24 | All MWD enabling IT implementation complete.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Working with the DNO, continue to undertake IT requirements and design for new operability functionality | Q1 2023-24 | Complete | Q4 2023-24 | Product Backlog prioritisation, requirements gathering and design commenced.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete IT requirements and design | Q2 2023-24 | Complete | Q1 2024-25 | Complete - now in build.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete enhancements to new service and final implementation | Q4 2024-25 | On track |  | Knocked on due to delay of RDP1. Product Backlog prioritisation, requirements and design underway and progressing. Expect this milestone to be delivered in BP2 as planned.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete IT development and testing; ongoing implementation of solution | Q1 2024-25 | Delayed - External Reasons |  | Did not complete in Q1 2024/25 due to delayed start of this RDP. Targeting completion in Q3 2024/25 to allow whole RDP to complete in BP2 timescales.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Assess enhancements to new service in accordance with operability needs and customer feedback | Q2 2024-25 | On track |  | Service enhancements agreed and driven by stakeholder and customer input to ensure delivery of value add scope items.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Working with the DNO, continue to undertake IT requirements and design for new operability functionality | Q1 2023-24 | Complete | Q4 2023-24 | Product Backlog prioritisation, requirements gathering and design commenced.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete IT requirements and design | Q2 2023-24 | Complete | Q1 2024-25 | Complete - now in build.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete enhancements to new service and final implementation | Q4 2024-25 | On track |  | Expected to be delivered in BP2 in line with milestone date commitment.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete IT development and testing; ongoing implementation of solution | Q1 2024-25 | Delayed - External Reasons |  | Did not complete in Q1 2024/25 due to delayed start of this RDP. Targeting completion in Q3 2024/25 to allow whole RDP to complete in BP2 timescales.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Assess enhancements to new service in accordance with operability needs and customer feedback | Q2 2024-25 | On track |  | Service enhancements agreed and driven by stakeholder and customer input to ensure delivery of value add scope items.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Establish enduring process to determine needs at GSPs | Q2 2023-24 | Complete | Q2 2023-24 | Factoring in our ongoing work through the ESO's Five Point Plan to Accelerate Connections, we have now drafted a process to determine a needs case at each GSP. This is currently undergoing final internal approval prior to being shared with stakeholders for review and feedback.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Rollout process and seek feedback from stakeholders | Q4 2023-24 | Complete | Q4 2023-24 | The RDP rollout process has been developed and feedback from stakeholders received and implemented. Process paper published in ESO external website.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Test application of process at one or more sites | Q2 2024-25 | Complete | Q1 2024-25 | We are working with SSEN to trial the process at their Abernethy network. CBA of the options complete with an operational solution recommended. Strategy paper has been finalised and awaiting sign off by SHEPD, SSEN-T and ESO.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Implement enduring ongoing process (BAU) | Q4 2024-25 | On track |  | Following successful test at the nominated sites, BAU processes will be updated to reflect the relevant changes.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Go / No go decision to progress RDP implementation; If yes, commence detailed RDP development | Q1 2023-24 | Complete | Q1 2023-24 | We have identified a number of opportunities where RDP5 can support the roll-out of functionality necessary to support the ESO's Five Point Plan to accelerate connections.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Complete IT requirements and design | Q2 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Complete detailed RDP development ahead of IT build. | Q3 2023-24 | Delayed - Internal Reasons |  | RDP 5 will be implementing GSP technical limits as agreed by ENA Strategic Connections Group work. Scoping discussion with all England and Wales DNOs are progressing. Project initiation documents are shared with all E&W DNOs. NGED and SSEN have signed their project initiation document. This will now allow us to start IT delivery activities.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Commence IT implementation in order to test new service solution. | Q4 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Go / No go decision to progress RDP implementation; If yes, commence detailed RDP development | Q1 2023-24 | Complete | Q1 2023-24 | We have identified a number of opportunities where RDP6 can support the roll-out of functionality necessary to support the ESO's Five Point Plan to accelerate connections.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Complete IT requirements and design | Q2 2024-25 | On track |  | On Track
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Complete detailed RDP development ahead of IT build. | Q3 2023-24 | Delayed - Internal Reasons |  | ESO and SPD agreed to deliver a transmission constraint management service for DERs via RDP6. Originally this was going to be taken via GEMS. However, after the agreement to discontinue with GEMS, a new service need to be designed and implemented to achieve the original intention of SPD ANM integration. We are trying to implement a service similar to MW dispatch. Potential advantages to be gained by using similar design principle and put lessons learned to a good use. This will be another example of scalability of RDPs. Discussions are ongoing with SPD on service terms and technical design. Progress has been made on the commercial framework and technical architecture.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Commence IT implementation in order to test new service solution. | Q4 2024-25 | On track |  | On track
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q1 2024-25 | Complete | Q1 2024-25 | Completed drafting initial design for electricity modelling information data store to facilitate implantation CIM model exchange with DNOs
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q2 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q3 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Grid Code mods progressed or submitted for approval | Q4 2023-24 | Complete | Q4 2023-24 | Progressing through sub group reviews on draft consultation report and legal text through industry engagements with intention to gather review feedbacks and finalise report and legal text in the next quarter. Reforecast required to align with latest information for final code authority sign off in Jan 2025
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q4 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. | Further upgrade to offline modelling tool software / service pack | Q2 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. | Integration of offline modelling tools with Data and Analytics Platform | Q4 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling | Feed findings from deliverable A16.3.2 and any Grid Code modifications into future modelling scoping and development | Q4 2023-24 | Complete | Q4 2023-24 | Through our recent engagement with DNOs and other industry participants via the GC0139 working group review panels, a number of planning code sections of the Grid Code needs modifying and changing to capture more detailed generation technical data within the DNO’s network, definitions and requirements have been reviewed in order to ensure these data meet the latest CGMES profile standards.
3 | Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling | Feed findings from deeper access work into offline network modelling development | Q4 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Learning from NIA projects (such as TOTEM) to define the requirements for EMT modelling work | Q1 2023-24 | Complete | Q1 2023-24 | NIA project TOTEM led by SSEN, provided base case EMT network component model based on ETYS 2021 Year 1. This will be used as base model for ESO to develop GB wide EMT model. The learnings such as dispatch tool requirement to analyse multiple scenarios, computational performance required will be taken forward to build future model building activities. DETECTS is another innovation project, where the SE Coast model with Users model integrated has been obtained. The main learning is on the integration of Users model to wider EMT model. More innovation projects, such as developing tools to analyse the system, are ongoing. Based on these learnings, ESO in discussion with wider industry, to build and maintain the GB wide EMT model for future.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Engage with wider industry and produce a roadmap to develop and maintain EMT models | Q2 2023-24 | Complete | Q2 2023-24 | ESO engaged with all onshore TOs through innovation project such as TOTEM to develop the base case GB wide EMT model. ESO is currently working with SSEN-T on EMT analysis. ESO is working in partnership with NGET on development of co-simulation NIA project. The JPC approved to form JPCMG subgroup on EMT modelling. ESO also having continuous engagement with wider industry (AEMO, G_PST, NERC, ESIG group) on learning and developing GB wide EMT model.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Identify the data requirements and develop process to collect required data and build initial EMT model. | Q4 2023-24 | Complete | Q4 2023-24 | Learnings from all NIA innovation projects are being used by ESO to define these requirements. ESO also engaged with wider industry (AEMO, NERC EMTTF, ESIG) in the world and their learnings also being used to develop these requirements. In addition to the above, CIGRE report and research papers have been used to define the data requirements. Data requirements for different analysis are presented to EMT Modelling JPCMG subgroup and received feedback from TOs.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To carry out initial EMT simulations for the GB network | Q1 2024-25 | Complete | Q1 2023-24 | ESO have already started to carry out EMT simulations for single plants/ HVDC. ESO obtain the initial model from DETECTS innovation project and started the regional analysis on GB.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To define the requirements for full GB system EMT simulation using learning from NIA projects (co-simulation analysis innovation project in D15.6.9) | Q2 2024-25 | On track |  | After completing the feasibility of co-simulation analysis (between PowerFActory and PSCAD) through innovation projects, requirements will be defined. The project team is also looking into the possibility of having reduced EMT network model instead of co-simulation as well as specifying the required areas/ regions for the EMT simulation rather than considering full GB EMT model for simulations. The potential conversion from PF to PSSe and then co-simulation with PSCAD also being investigated.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To carry out EMT simulations to analyse control interactions, system oscillations and power quality studies. Developed plan for ongoing maintenance of EMT model(s). | Q4 2024-25 | On track |  | ESO started to carry out EMT simulations for single plants/ HVDC. ESO obtain the initial model from DETECTS innovation project and developing the analysis skills. Different system analysis with wider GB model, obtained from TOTEM project, will be carried out. Different system analysis with wider GB model, obtained from TOTEM project, will be carried out. ESO started using TOTEM model to investigate the system behaviour, with the available Users models. The methodology such as impedance scan is also used to understand the behaviour of system.
3 | Transform our capability in modelling and data management | D15.6.9 | Co-simulation analysis innovation project | Engage with wider industry (different TOs) to start the potential innovation project for co-simulation works. | Q1 2023-24 | Complete | Q1 2023-24 | Engaged with NGET TO on requirements of co-simulation (between PowerFactory and PSCAD model). ESO is working with NGET to set up a new NIA project called Co-Simulation. Co-simulation NIA project is expected to start in 2 weeks. ESO also engaging with OPAL-RT and other academia on possible NIA projects as well.
3 | Transform our capability in modelling and data management | D15.6.9 | Co-simulation analysis innovation project | Evaluate the feasibility of co-simulation modelling between OLTA (PowerFactory) and PSCAD. | Q4 2023-24 | Complete | Q4 2023-24 | ESO is working with NGET on a NIA innovation project on co-simulation between PowerFactory and PSCAD. Through this innovation, at first the feasibility of co-simulation between PowerFactory and PSCAD has been evaluated. NIA project demonstrated the communication between two tools (PowerFactory and PSCAD) but due to communication delay, error introduced in the analysis. To investigate further on these issues, ESO is also currently exploring on the co-simulation feasibility analysis within PowerFactory (Both RMS and EMT within PowerFactory), through IT project. Engagement with DigSilent on co-simulation within PowerFactory tool is being explored through ONM investment.
3 | Deliver enhanced frequency control by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) first stage roll out. | Phase 1 (non-operational demonstration) implemented | Q3 2023-24 | Delayed - External Reasons |  | Due to the long delay in getting contract signed between parties, the completion of non-operational demonstration date is expected to go beyond the current scheduled date. Currently change Request has been submitted and the expected completion of this milestone is Q2 2024-25. Through CMF process the revised milestone date has been updated. t is expected to be completed within BP2 period. With the Statement of Work has been agreed with GE Digital, the confidence level of completing this milestone is increased to HIGH. Installation of MCS system at Data Centre is completed. Local devices at Warwick office and GE Office location was completed. Establishing the flow of SPEN PMU data to non-prod PDC is ongoing. Non-operational demonstration is expected to start in this month.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Support ESO initiatives to remove technical barriers to ensure whole electricity system coordination & distributed flexibility market participation. | Q4 2023-24 | Complete | Q4 2023-24 | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement on DSO transition to support ongoing developments and transition policy into the relevant codes and frameworks. | Q4 2023-24 | Complete | Q4 2023-24 | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q4 2023-24 | Complete | Q4 2023-24 | Actively engaged on workstreams on Open Networks, Currently co-leading on several to drive forward change and increase pace of change. we have a proposed way forward on Primacy rules and continue to engage with all stakeholders.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Support ESO initiatives to remove technical barriers to ensure whole electricity system coordination & distributed flexibility market participation. | Q4 2024-25 | On track |  | Actively engaged on workstreams on Open Networks, Currently co-leading on several to drive forward change and increase pace of change.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement on DSO transition to support ongoing developments and transition policy into the relevant codes and frameworks . | Q4 2024-25 | On track |  | Our Flexibility Strategy Call for Input was launched in May with a dedicated workstream on DSO coordination, and we are leading on several groups within the Open Networks Programme, including leading the Market Development Workstream.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q4 2024-25 | On track |  | We continue to actively engage with Open Networks and we are leading on several groups within the Programme, including leading the Market Development Workstream.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Initiate project scoping with external stakeholders to enable operational visibility of DER | Q1 2023-24 | Complete | Q1 2023-24 | We have initiated Project scoping with internal stakeholders to identify DER visibility use cases. Identified relevant external stakeholders. Next step to engage externally to produce a high level view of External stakeholders expectations.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Complete project scoping with external stakeholders to enable operational visibility of DER | Q2 2023-24 | Complete | Q3 2023-24 | We have completed work to produce a DER Visibility Roadmap strategy. We undertook a cross functional view to produce detailed user requirements across ESO & external stakeholders as well considering regulatory, data and technology architecture aspects needed to deliver DER visibility. This holistic approach is expected to reduce risk & maximise consumer benefit.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Initiate IT discovery phase to understand impacts on required changes to systems and define change strategy | Q3 2023-24 | Complete | Q3 2023-24 | Digital, Data & Technology (DD&T) Discovery kicked off on 25th March, having been delayed by 2.5 months due to internal scoping. Expected timescales have increased from 3 to 13 months, leading to delays to associated milestones and the wider programme. The programme has been replanned to be rebaselined, which will be approved at the DER Visibility Steering Committee on 5th April 2024 to return to green.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Complete IT discovery phase and identify costs of implementation | Q4 2023-24 | Delayed - Internal Reasons |  | Digital, Data & Technology (DD&T) DER Visibility and Access Discovery has kicked off, but was delayed by 2.5 months and expected timescales have increased from 3 to 6 months which include an expanded scope of also improving the network operator’s access to DERs, leading to delays to associated milestones and the wider programme. The initial Discovery looking at DER assets will complete in July 2024. Programme suggestion is to split this milestone into 2 and capture the increased scope and additional consumer benefits on the new milestone for next Business Plan period.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Commencement of requirements and design phase to develop detailed IT solution to enable DER visibility | Q1 2024-25 | Delayed - Internal Reasons |  | The initial DD&T Discovery looking at DER assets will complete in July 2024, with delivery of captured changes being sanctioned in August 2024. Work on the detailed IT solution for DER assets will kick off in September 2024, meaning that this milestone will be delayed by c 2 months.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Commence building the storage and transfer capability to utilise bigger volumes of data associated with a larger number of operational metering data points | Q4 2024-25 | On track |  | Specific IT solution(s) will be identified in the discovery phase and designed in the design phase. These details will scope how this milestone will be met.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Initiate IT discovery phase for primacy implementation to understand impacts on required changes to systems and define change strategy | Q1 2023-24 | Delayed - Internal Reasons |  | Mandate to initiate the IT discocvery phase for Primacy is currently in development. There were internal delays to data availability to allow discovery, and internal migrations of services onto platforms to allow for implementation, and external delays in use case scoping and rule development.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Complete IT discovery phase and identify costs of implementation | Q2 2023-24 | Delayed - Internal Reasons |  | Mandate to initiate the IT discovery phase for Primacy is currently in development.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Commencement of requirements and design phase to implement primacy rules into operational IT systems | Q3 2023-24 | Delayed - Internal Reasons |  | Mandate to initiate the IT discovery phase for Primacy is currently in development.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Continue to lead on Open Networks work to deliver primacy rules | Q3 2023-24 | Delayed - Internal Reasons |  | Having stepped back from our co-lead role while recruiting, a new team member is now in post and actively supporting the lead.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Initial operational systems developed for primacy co-ordination based on outputs of requirements and design phase | Q3 2024-25 | On track |  | Mandate to initiate the IT discovery phase for Primacy is currently in development and we are working with the DER Visibility team to coordinate required updates to internal systems across business plan commitments and coordinate engagement activities with DNO's.
3 | Net zero operability | D15.9.5 | Provide Early engagement with stakeholders on implementation of technologies required for net zero carbon operation | ESO is supporting stakeholders in implementing new technology developments. Positive feedback from policy makers as applicable | Q4 2024-25 | Continuous activity |  | 22-4-24 We continue to develop opportunities for new technologies to provide system and energy services as we progress towards net zero 2035. We are developing new markets and services to meet future system needs, whilst opening these up to new technologies and benefitting the end consumer. We are introducing new ways to manage thermal constraints, meet system stability needs, and gain access to wider reactive power capability. We are seeking new providers of restoration services on distribution networks and delivering a suite of response and reserve products suitable for new technologies. We are progressing innovation projects and code changes to provide greater visibility and insight into a system dominated by inverter based resources, and finding new ways to access further asset capability. We are working with DESNZ and industry stakeholders to develop standards for EVs and other Energy Smart Appliances that will ensure they can provide flexibility to the electricity system whilst not creating excessive security risks.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | Deliver regional outage programmes | Q4 2023-24 | Complete | Q4 2023-24 | This is the Year Ahead Plan which is delivered on an annual basis. Its part of plan build process. The plan is an iterative process throughout the year at year ahead timescales and is locked down at week 49 then handed over at week 6 the following year.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | Deliver regional outage programmes | Q4 2024-25 | On track |  | This is the Year Ahead Plan which is delivered on an annual basis. Its part of plan build process. The plan is an iterative process throughout the year at year ahead timescales and is locked down at week 49 then handed over at week 6 the following year.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | Q4 2023-24 | Complete | Q4 2023-24 | Continuous Activity - this is business as usual planning in the Network Access Planning department. We are obliged to adhere to the STCP 11-1 mandated timescales for communication with customers if they are impacted. We are also obliged to produce an operational plan for our control room. We have provided this operational plan on 100% of the days that we are obliged to.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | Q4 2024-25 | On track |  | Continuous Activity - this is business as usual planning in the Network Access Planning department. We are obliged to adhere to the STCP 11-1 mandated timescales for communication with customers if they are impacted. We are also obliged to produce an operational plan for our control room. We have provided this operational plan on 100% of the days that we are obliged to.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Stakeholder mapping activities commenced | Q1 2023-24 | Complete | Q1 2023-24 | Started Stakeholder mapping exercise
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Stakeholder mapping activities continued and context communicated to stakeholders | Q2 2023-24 | Complete | Q3 2023-24 | Stakeholder mapping exercise completed. Stakeholders invited to OC2 forum in March, where ESO will present initial concept for discussion.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Organisation of cross industry forum with OC2 attendees to present and hear thoughts | Q3 2023-24 | Complete | Q3 2023-24 | We remain on track for scoping a whole electricity system decision making process. As per the milestone, we delivered an interim OC2 forum in September 2023 and will host a full one in 2024
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | CBA and summary paper written for presentation to industry and ESO senior management | Q4 2023-24 | Complete | Q4 2023-24 | Summary paper written and circulated to ESO Senior Leaders. Provisional CBA produced. To be shared externally in early April.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q1 2024-25 | Complete | Q1 2024-25 | Started Stakeholder mapping exercise.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q2 2024-25 | On track |  | Started stakeholder mapping exercise- 1st milestone complete
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q3 2024-25 | On track |  | Started stakeholder mapping exercise- 1st milestone complete
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Agree framework to facilitate decision making | Q4 2024-25 | On track |  | Started stakeholder mapping exercise- 1st milestone complete
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in D16.3.1 and D16.3.2 | Proposals for draft modifications completed | Q4 2023-24 | Complete | Q4 2023-24 | Scoping and proposal documented.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in D16.3.1 and D16.3.2 | Code modifications finalised for approval | Q4 2024-25 | On track |  | Partner DNO onboard and process design sessions underway. Second potential DNO partner engaged.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Proposals for frameworks, models and processes completed | Q4 2023-24 | Complete | Q4 2023-24 | Scoping and proposal completed.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Frameworks, models and processes completed to facilitate deeper access planning. | Q4 2024-25 | On track |  | Partner DNO onboard and process design sessions underway. Second potential DNO partner engaged.
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Dependent on outcomes of A16.3 deliverables | Q3 2023-24 | Complete | Q4 2023-24 | Work supported by PODE workstream 1. API links between eNAMS outage management app and NGET's NCIS app commissioned both reading and writing data. Delivers resource planning and efficiency savings for the TO. Working with Scottish Power TO on API proof of concept. Exiting Proof of Concept for Conga, an enhanced reporting tool which may enable users to self serve outage queries and analyse outage planning performance. TOs have been provided with access to an ESO outage tracker, the "ROB" (Regional Outage Board) enabling TOs to track the progress of their outage requests through the ESO outage planning process. Activity completed 16 June 2023. Scoping document completed.
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Scoping complete | Q4 2023-24 | Complete | Q4 2023-24 | Duplicate Milestone
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Dependent on outcomes of A16.3 deliverables | Q4 2024-25 | On track |  | Work supported by PODE workstream 1. Activity to deliver ongoing eNAMS improvements underway and ongoing.
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Dependent on outcomes of A16.3 deliverables | Q4 2023-24 | Complete | Q4 2023-24 | Duplicate Milestone.
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Dependent on outcomes of A16.3 deliverables | Q3 2024-25 | On track |  | Work supported by PODE workstream 1. Activity underway and ongoing.
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Whole System Outage Notifications in use | Q4 2024-25 | On track |  | Work supported by PODE workstream 1
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q1 2023-24 | Complete | Q1 2023-24 | The automated stability assessment tool (ASAT) has gone live and we have secured licenses for continuous development and integration (CI/CD). We are working to deliver the same development environment on the cloud.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q2 2023-24 | Complete | Q2 2023-24 | Complete. We will do further enhancements in future and provide with cloud services.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q3 2023-24 | Complete | Q3 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q4 2023-24 | Complete | Q4 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q1 2024-25 | Complete | Q1 2024-25 | We have provided secure, and controlled experimental Sandbox environments. Business users continuously use the platforms for development and testing.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q2 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q3 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q4 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Project delivery timelines and full project plan identified for delivery of contingency analysis automation and automation of multiple cardinal point analysis | Q1 2023-24 | Complete | Q1 2023-24 | We have collaborated with subject matter experts and documented user stories to capture the requirements. Additionally, we have developed a project plan to ensure the delivery of these requirements.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Proof of concept for agreed automation commenced | Q2 2023-24 | Complete | Q2 2023-24 | This part of work is completed.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Proof of concept for automation completed | Q3 2023-24 | Complete | Q3 2023-24 | We have completed the scoping and are preparing for delivery.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training programme for teams in NAP developed and delivery schedule planned | Q4 2023-24 | Complete | Q4 2023-24 | Training has already started with multiple session organized across networks. This will be a continuous activity as planned.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools underway. | Q1 2024-25 | Complete | Q1 2024-25 | Training has already started with multiple session organised across networks. This will be a continuous activity as planned.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q2 2024-25 | On track |  | Training has already started with multiple session organised across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q3 2024-25 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q4 2024-25 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network Planning Review | N/A | Network Planning Review | Development of a centralised strategic network planning methodology is complete. | Q4 2024-25 | On track |  | Development of the CSNP, in collaboration with Ofgem and other key stakeholders continued throughout this period, and is continuing at pace.
3 | Offshore Coordination | N/A | Offshore Coordination | ESO activities in the Offshore Transmission Network Review timeline are delivered to the agreed timescales and quality. | Q4 2024-25 | On track |  | On Track based on the plan
2 | Deliver an enhanced platform for EMR | D5.2 | Deliver an enhanced platform for EMR | User familiarisation completed for initial release, with system go live for CM Process. Using portal and data to increase automation of ESO processes to improve efficiency and information available to industry. Guidance to rule changes are incorporated into Portal. The EMR Portal will allow disputes to be linked directly to relevant Applications | Q1 2024-25 | Complete | Q1 2024-25 | The New Portal was fully implemented for Capacity Market processes on 17th June. User familiarisation was run between mid March to mid April. 63 users representing nearly 300 different companies participated. An integrated guidance platform has been implemented alongside the new portal with guidance accessible via direct links from the system or via a guidance website.. Prioritised improvements have been designed in processes to enable increased automation and enhanced customer journeys. The Prequalification Disputes process has been designed and implemented to enable an improved customer journey for Disputes to be raised and tracked against associated Prequalification Application.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Regulatory changes implemented for annual processes in current EMR Portal. | Q2 2023-24 | Complete | Q2 2023-24 | Changes from the DESNZ consultation were implemented in the portal prior to the Prequalification round opening in July 2023.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Regulatory changes implemented for annual processes. | Q2 2024-25 | On track |  | We have worked with the DESNZ team to assess and agree changes required to deliver items of work included in the scope of their CM2023 Phase 2 consultation. Scope has been updated based on the impact of the election on regulatory approval processes. We implemented functionality to deliver changes to metering processes in accordance with CP373 from the Ofgem CM consultation. Ofgem published their approved decision on 14th June, with CM rule changes to be laid prior to the PQ window.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Deliver planned integration of EMR within the Digital Engagement Platform, considerate of any licensed business separation requirements. Additional improvements to EMR portal to enhance customer experience, following customer feedback. Assessment of delivery options for the Contracts for Difference (CfD) scheme delivery in accordance with REMA proposals. | Q4 2024-25 | On track |  | We are working with the Digital Engagement Platform delivery team to agree a delivery plan and confirm scope. The Delivery Body are designing a prioritisation approach with the dedicated customer user group, to support recommendations for enhanced customer experience. The feedback received in the Customer Familiarisation Window and post go-live will be used as input in to the assessment and delivery plans. Additional customer feedback points will be agreed in line with operational processes run on the New Portal. The Delivery Body continue to monitor REMA proposals to support decisions on future CfD system landscape, with latest indications proposing enhanced pot structures and participation rather than wholesale change to application and allocation framework. We are expecting an updated scope in Q3 2024/25.
3 | Connections Reform | D14.5.1 | Five Point Plan | TEC Amnesty implement terminations. Queue management CUSC mod with Ofgem for a decision. CPA review and non firm offers for storage in progress, working with the TO's to deliver this. | Q2 2023-24 | Complete | Q2 2023-24 | As part of ESO's 5 point plan for connections, we have issued 4.1 GW of contract terminations / TEC reductions in response to customer expression of interest. We submitted CMP376 to Ofgem for decision (recommending adopting queue management milestones to connection contracts).
3 | Connections Reform | D14.5.1 | Five Point Plan | Queue Management: Issue Notice to Industry to start implementation phase. Accelerated non-firm offers for storage: Revised offers issued to 10GW (phase1) | Q3 2023-24 | Complete | Q3 2023-24 | Notice issued 27 November 2023 to all customers with connection dates of November 2025 or later. Customers have 6 months to respond and request a Mod App to delay their connection date or queue management milestones will be applied to their existing agreement. Phase 1 accelerated non-firm offers issued to 20 storage projects (9.3GW) in England & Wales which submitted an expression of interest.
3 | Connections Reform | D14.5.1 | Five Point Plan | Two-step offers: 2nd step offers issued to all participating customers in England & Wales Queue management: Share outcome of CMP376 6-month notice to industry (number of projects / GW seeking to delay connection date versus number of projects / GW to have milestones added to their existing connection agreement. Accelerated non-firm offers for storage: Tranche 2 communicated plan with industry. | Q1 2024-25 | Complete | Q1 2024-25 | All two-step offers were issued by the end-of May to affected customers in England & Wales. Queue management implementation in progress: customers had until 27 May to confirm whether they want to mod app to delay their connection date or have queue management milestones applied to their existing connection date. The number of customers within each of these categories is being shared at the June CDB and CPAG meetings. ESO is working with NGET and SSENT to confirm the customer projects to be included within Phase 2 for delivery by September. SSENT has confirmed the details of the projects to be included. SPT has advised that no projects that submitted an EoI can be accelerated on a non-firm basis.
3 | Connections Reform | D14.5.1 | Five Point Plan | CPAs and Transmission Work Review: revised offers issued to customers seeking acceleration (where studies identify this is possible) Accelerated non-firm offers for storage: Revised offers issued to Phase 2 customers | Q2 2024-25 | On track |  | CPA and transmission works review is underway with each TO for completion by the end of Q2 2024-25. Phase 2 of the accelerated non-firm storage offers is in development. SPT and SSENT have identified customer projects with theoretical potential for acceleration, from a longer list of customer expressions of interest. These are now being studied. NGET are to confirm which projects will be considered for Phase 2 once the current 2-step delivery activity is complete at the end of May.
3 | Connections Reform | D14.5.1 | Five Point Plan | Quantification of the initial impact of CMP376 (queue management) implementation | Q3 2024-25 | On track |  | We are tracking implementation of queue management milestones.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | High-level design options developed and consultation launched including recommended reform option | Q1 2023-24 | Complete | Q1 2023-24 | Connections Reform Phase 2 high level design developed and consultation published in June.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Consultation closed and stakeholder feedback reviewed to refine reform proposal | Q2 2023-24 | Complete | Q2 2023-24 | Consultation closed as scheduled and responses collated and reviewed to refine the reform proposal.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Complete Phase 2 - Final recommendations and indicative implementation plan published | Q3 2023-24 | Complete | Q3 2023-24 | Final recommendations published in December 2023.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Mobilise ESO Connections Change Delivery activity to align with Connections Action Plan. Implement voluntary Letter of Authority Develop transparent/faster process to assess and convey the transmission impacts of distribution connections Flexible connections and management of distribution connections within agreed 'technical limits' across all GSPs Detailed reporting of connections data | Q3 2023-24 | Complete | Q3 2023-24 | Following November publication of the Ofgem/DESNZ Connections Action Plan we mobilised the team and assigned responsibilities for each ESO-assigned action within CAP. We implemented a voluntary Letter of Authority into the Connection Application process. We continued engagement with DNOs through the Strategic Connections Group on the development of a Distribution Forecasted Transmission Capacity approach. Technical Limits Phase 1 completed and a Connection Databook developed for reporting detailed connections data.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Establish plans, instigate workstreams for ESO-led actions. Consult industry stakeholders through CPAG and CDB Deliver CAP Q1 2024 milestones: Letter of Authority Code Mod proposal Further proposals to raise entry requirements Recommendations to improve certainty and progression of customers holding capacity Recommendations to optimise existing network capacity Review scope for improvements in CPAs for optimised planning Review scope of enabling works Recommendations to effectively allocate network capacity released in the short term Signposting a single digital view of network data for connection customers Detailed reporting of connections data. | Q4 2023-24 | Complete | Q4 2023-24 | Workstream established for ESO-assigned actions within CAP with progress updates and papers for review submitted to CPAG and CDB. CPAG met 5 times in Q4 and CDB 3 times. The Letter of Authority code mod was submitted and approved. Options to raise entry requirements and to improve certainty of progression of customers holding capacity both addressed through recommending extending Gate 2 of reformed process to the existing queue. Recommendations for improvements to CPAs for optimised planning and to review the scope of enabling works presented to CPAG as part of Package 2 recommendations. Recommendation for capacity reallocation developed and presented to CPAG and CDB. ESO's 'Connections 360' tool to provide a single digital view of the network for connections customers developed and shared at CPAG and CDB. Detailed reporting of connections data continues on a monthly basis. Detailed reporting of connections data continued through the monthly Databook.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Deliver CAP Q2 2024 milestones: Consider further letter of authority actions Recommendations for longer-term approach to allocate capacity complementing strategic network planning Detailed reporting of connections data Develop delivery plans and mobilise activity according to outcome of the Q4 (2023-34) milestones and recommendations | Q1 2024-25 | Complete | Q1 2024-25 | Connections Reform and Change Delivery activity continues to deliver CAP milestones. The Letter of Authority Phase 2 proposal went to Connections Delivery Board in May, who provided a steer and next steps are in delivery. We continue to work with Ofgem, DESNZ and TOs to consider recommendations for 2025 and beyond that go beyond TMO4+ and look to align more closely with strategic network planning. Monthly connections data reporting continues. We have worked with ENA, Ofgem and DESZ to revise the CAP delivery plan in light of the outcome of the March 2024 milestones. The revised plan was presented to the May CDB meeting.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Detailed reporting of connections data Continued delivery of activity according to outcome of Q4 (2023-24) milestones and recommendations | Q2 2024-25 | On track |  | Monthly connections data reporting continues. We have worked with ENA, Ofgem and DESZ to revise the CAP delivery plan in light of the outcome of the March 2024 milestones. This will be further reviewed as projects progress and key milestones are reached.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Detailed reporting of connections data Continued delivery of activity according to outcome of Q4 (2023-24) milestones and recommendations | Q3 2024-25 | On track |  | Monthly connections data reporting continues. We have worked with ENA, Ofgem and DESZ to revise the CAP delivery plan in light of the outcome of the March 2024 milestones. This will be further reviewed as projects progress and key milestones are reached.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Detailed reporting of connections data Continued delivery of activity according to outcome of Q4 (2023-24) milestones and recommendations | Q4 2024-25 | On track |  | Monthly connections data reporting continues. We have worked with ENA, Ofgem and DESZ to revise the CAP delivery plan in light of the outcome of the March 2024 milestones. This will be further reviewed as projects progress and key milestones are reached.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Indicative implementation plan developed | Q2 2023-24 | Complete | Q2 2023-24 | Indicative implementation plan developed and published within consultation document.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Implementation Phase begins. Process mapping and detailed design underway | Q3 2023-24 | Complete | Q3 2023-24 | We mobilised the Implementation Phase as soon as the Phase 2 Final Recommendations were published in December 2023.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Identify licence and code changes required for agreed reforms. | Q4 2023-24 | Complete | Q4 2023-24 | Code Changes identified for the agreed reforms. We also shared our recommended strategy for the structure of the required code modifications with the Connections Process Advisory Group. Licence change assessment ongoing into Q1 2024-25
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Complete detailed design and process mapping for the reforms to be implemented Raise code changes at Code Panel(s) | Q1 2024-25 | Complete | Q1 2024-25 | End-to-end process mapping developed for the reformed connections process and under internal review. Code changes for TMO4+ raised in May and Ofgem has granted use of the urgency process.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Code changes progressing through working groups. | Q2 2024-25 | Delayed - External Reasons |  | Code change workgroups are progressing, but the scale of issues being explored mean that additional workgroup meetings need to be scheduled before the workgroup consultation is released, which will have a knock-on impact on completion of the code modification process / Ofgem decision - impacting the Q3 and Q4 milestones that follow this.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Code changes progressing through working groups. Licence changes complete | Q3 2024-25 | Delayed - External Reasons |  | Code change workgroups are progressing, but the scale of issues being explored mean that additional workgroup meetings need to be scheduled before the workgroup consultation is released, which will have a knock-on impact on completion of the code modification process / Ofgem decision and the Licence changes to enable TMO4+.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Reformed connections process goes-live. First connection application window opens. | Q4 2024-25 | Delayed - External Reasons |  | Low confidence of go-live 01 January 2025 due to the scale of issues the code change workgroups are considering, which require an extension to the code change workgroup schedule. This will have a knock-on impact on the schedule for Ofgem to determine the outcome of the code change processes and related licence changes. This also means ESO and other network licensees need to reschedule the final preparatory actions, post-code changes before the reforms can go-live.