## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | DG | Provide views to ESO on potential anomalies in charging methodology | Update provided within slides 7/8 of the Workgroup Meeting 3 Papers | WG3 | Closed | WG3
2 | WG1 | NP | Investigate with Revenue as to whether implementation date can be moved forward, or provide justification if not | Implementation agreed to be moved to 01 April 2026. | WG2 | Closed | WG2
3 | WG1 | NP | Investigate who is responsible for Governance of ETYS boundaries and how many new boundaries have been created in the past 10 years | No specific no codes or formal governance for ETYS boundaries but: - JPC discuss ETYS boundaries with the TO, which has subgroups including Investment Planning, Modelling and ETYS - STC governs the discussions and the relationship between the ESO and the TOs. In the last 10 years one boundary has been created approximately every 2 years. | WG2 | Closed | WG2
4 | WG1 | NP | Investigate potential effect on boundaries if constraints are removed by the bootstrap. Also look into expected trajectory of constraints. | Update provided within slides 9 of the Workgroup Meeting 3 Papers | WG2 | Closed | WG3
5 | WG1 | NP | Circulate a document which provides an overview of the ETYS Boundaries and ETYS Zones | Shared within Workgroup Meeting 2 Papers - Document provides detail in pages 4 and 6 | WG2 | Closed | WG2
6 | WG1 | ML | Create Microsoft Form for Workgroup members to feed interactions into | Link shared in WG1 Summary | WG2 | Closed | WG2
7 | WG2 | NP | Clear usable map illustrating ETYS zones (Shape file, zoomable, more interactive the better). | Update provided within slide 9 of the Workgroup Meeting 3 Papers | WG3 | Closed | WG3
8 | WG2 | NP | ETYS boundaries and zones on one map. | Update provided within slide 9 of the Workgroup Meeting 3 Papers | WG4 | Closed | WG3
9 | WG2 | AH | Circulate CMP324/325 documentation links with Workgroup. | CMP324/325 Modification page | WG5 | Closed | WG3
10 | WG2 | AH | Circulate “Approach to understanding generation rezoning” document link | “Approach to understanding generation rezoning” document link | WG6 | Closed | WG3
11 | WG2 | NP | ESO Revenue team to attend WG4 and present analysis. | Analysis will not be available until March and will be circulated to the Workgroup when available | WG7 | Open
12 | WG2 | NP | Look at CUSC 14.15.12 and investigate if this could be used. | Update provided within slide 10 of the Workgroup Meeting 3 Papers | WG8 | Closed | WG3
13 | WG3 | PA | Confirm the Authority position around policy and workgroup work |  | WG5 | Open
14 | WG3 | NP/RP | ESO to liaise with the TOs to obtain coordinates for each transmission node | Update provided on slide 11 of the Workgroup Meeting 4 Papers | WG4 | Open
15 | WG3 | NP | Share list of the transmission nodes and the ETYS zone they sit in with the Workgroup | Will be provided before the next workgroup in March. | WG5 | Open
16 | WG3 | NP | Confirm with Revenue Team that the analysis will: - Be inclusive of data until the end of RIIO3 - show the existing generation zone and the new generation zone as per the proposal under CMP419 for each generator (including a table similar to CMP324 on the TEC Register) - show how the reactance has been calculated for HVDC circuits - demonstrate the changes to the model required for CMP419 (to allow replication) | Update provided on slide 12 of the Workgroup Meeting 4 Papers | WG4 | Closed | WG4
17 | WG3 | NP | Confirm that alongside the published analysis a copy of the transport and tariff model will be provided to WG members | Update provided on slide 13 of the Workgroup Meeting 4 Papers Follow up Action: SC to check if the Workgroup could be done on a mass NDA? | WG4 | Open
18 | WG3 | NP | Confirm whether it is possible to share a list of nodal prices for all generators by generation zone, or whether the ESO only have a price per ETYS zone | Update provided on slide 13 of the Workgroup Meeting 4 Papers | WG4 | Closed | WG4
19 | WG3 | NP | Confirm whether the methodology and assumptions being used as part of the analysis will be available to share with the Workgroup ahead of the analysis taking place | Will be provided before the next workgroup in March. | WG5 | Open
20 | WG3 | All | Share any potential alternative requests | There are currently no potential alternative requests | 2024-01-09 | Closed | WG4
21 | WG4 | TE/SC | After receiving examples of inconsistencies between the July and December Transport Models (TE) provide feedback on changes (SC) |  | WG5 | Open
22 | WG4 | SC | Look into interactive nodal 10-year map |  | WG5 | Open
23 | WG4 | SC | Confirm whether requested elements can be included in analysis: - Connectivity matrix - Year and non year-round split - Cost reflectivity |  | ASAP | Open