## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | PM | To share further data is shared in relation to the transmission queue | Link to ENA webpage | TBC | Closed | WG7
2 | WG1 | JH/PM | To clarify if it is the modification is intending to cover a demand application at the distribution level which causes a transmission reinforcement. |  | WG2 | Closed | WG4
3 | WG1 | JH | Tighten up the language RE: User Commitment Methodology/ Final Sums | Will be answered within the consultation | TBC | N/A
4 | WG1 | JH/RW | Revise Terms of Reference based on Workgroup feedback | Covered in WG4 | TBC | Closed | WG4
5 | WG1 | JH | Changing the wording from ‘change the Network Charging arrangements’ to ‘Network use of system Charging arrangements’ are out of scope |  | TBC | Closed | WG4
6 | WG2 | JH | Clarification slide on what is BAU regarding the GSP process | Covered in WG4 | WG4 | Closed | WG4
7 | WG2 | JH | Explain the interaction of CMP434 with GC0117, consider the potential impact if GC0117 approved such as a need for an additional code modification (Chair to put in consultation) | Will be answered within the consultation | TBC | N/A
8 | WG2 | AP | Consider the definition of Relevant Embedded Small/Medium Power Station and whether the codified definition needs to be changed or if the ESO is to provide guidance to DNO’s outside of the energy codes on what is considered as relevant to the transmission network | Closed due to DNO obligations being outside of the scope of CMP434 or CM095 | TBC | Closed | WG7
9 | WG2 | AP | Slide on Large Embedded for clarification | Closed due to DNO obligations being outside of the scope of CMP434 or CM095 | WG4 | Closed | WG7
10 | WG2 | DD | Tabulate Minor and Major Changes at Gate 1 and 2 for a clearer distinction | Covered in WG4 | WG4 | Closed | WG4
11 | WG2 | All | Add agenda time to respond to papers provided by Workgroup members | Ongoing | WG4 | Closed | WG25
12 | WG2 | JH | ESO to speak to the policy team and consider how the ‘Allowable Changes’ policy being drafted would interact with CMP434, would all of the policy need to be codified or does the concept of the policy need to be codified? | Proposer clarified the intention for this not to be codified. | WG4 | Closed | WG7
13 | WG2 | ALL | Workgroup to propose what they think could change in their application between Gate 1 and Gate 2 | Moved on form this | TBC | Closed | WG13
14 | WG4 | JH | Clarification of new GSPs for iDNOs and DNOs | Will pick up DFTC part | TBC | Closed
15 | WG4 | JH | Consider alignment of crown estate invitation to tender and auction timing | Out of Scope | TBC | Closed | WG13
16 | WG5 | RW/GL | Look into where STC changes for CNDM should be located within main body of STC and STCPs | Legal Text slides presented at WG13 | TBC | Closed | WG13
17 | WG5 | FP | Are the duplication checks at Gate 2 against projects who are within the gate 2 applicants pool of that period, gate 2 applicants that are yet to accept their offer, or/and applicants who have accepted their Gate 2 offer | Presented at WG11 duplicate check | TBC | Closed | WG13
18 | WG6 | RE/MO | Share table and/or visual outlining the difference between the ESO/TO costs covered by an application fee and the TO costs covered by the proposed capacity holding security. |  | TBC | Closed | WG7
19 | WG6 | RE/MO | Share a worked example of how the capacity holding security would (in theory) be apportioned between directly connected and relevant small and medium embedded generation projects, using a hypothetical £1/MW value. |  | TBC | Closed | WG7
20 | WG6 | JN/AQ | Consider legal perspective on NESO designation |  | TBC | Closed | WG25
21 | WG6 | MO | Update/develop slides presented based on Workgroup feedback | Update/develop slides presented based on Workgroup feedback | TBC | Closed | WG13
22 | WG6 | JH | Consider if an impact assessment by the ESO on the proposed solution is achievable within the current timescales | The necessary analysis will be provided to Ofgem as and when they require it but this will be outside of the code process | TBC | Closed | WG23
23 | WG7 | LH | Clarify the ESO Position as to why the capacity reallocation process is out of scope for CMP434 | Add narrative into Workgroup Report | TBC | Closed
24 | WG7 | MO | Consult ESO legal team to consider using existing legal definitions for clarification (substantial modification) and reconsider terminology being used (material/significant/allowable) |  | TBC | Closed | WG25
25 | WG7 | LH/SG | Update on the Technology Change Policy Paper and consider request to share prior to consultation | Draft paper has been circulated. | TBC | Closed | WG13
26 | WG7 | SMEs | Provide a list of policy documents envisaged for TMO4+ and for which details are not within scope of CMP434 (e.g.CNDM). Also provide a list of their contents/principles the documents are using if not available for the WG consultation | WG consultation includes those relevant – replaced with action 49 | TBC | Closed | WG18
27 | WG9 | AP/KS | Take Workgroup feedback to ENA regarding the name of the DFTC methodology document – consider renaming to provide clarification | Draft ENA document shared, and title changed to guidance after WG feedback. | TBC | Closed | WG13
28 | WG9 | AP/KS | DFTC document – Provide answers to the following questions – Who approves the document, who can change it, who follows it and who can challenge it (the route to challenge specifically) | ENA members, DNO’s, TO’s, ESO (iDNO’s can join ENA) | TBC | Closed | WG13
29 | WG9 | MO/AQ | In terms of the 3 year long stop cancellation of sites/capacity provide detail to what element of the CUSC is being referenced and how this is envisaged to work? | No longer being proposed | TBC | Closed | WG18
30 | WG9 | AQ | To explain how the dispute process will fit into the statutory approach (legal route) | De-scoped | TBC | Closed | WG18
31 | WG9 | MO | More detail requested by Workgroup to make a judgement on Connection Point and Capacity Reservation (including offshore) |  | TBC | Closed | WG25
32 | WG10 | MO | Clarify TO/ESO in terms of CNDM and what would got into the Gate 1 offer | Within WG consultation | TBC | Closed | WG18
33 | WG10 | KS | To clarify, if the ESO decides not to have forward-looking milestones after M1, would DNO’s change there’s or will they continue to be forward looking for all the others | If CMP434 is approved. EVA will look to make changes to their queue milestones. | TBC | Closed | WG13
34 | WG10 | PM | Review the four slides to address points from GG (clarity and colouring of text suggestions) and TC to review the dates are correct |  | TBC | Closed
35 | WG10 | AC/AQ | ESO to confirm whether additional uncertainty clauses (which have been appearing in offers recently) will remain |  | TBC | Open
36 | WG10 | AC/AQ | ESO to consider doing duplication checks on LoAs given info received today on G1 offers, to avoid buying LoAs off each other. | Not proposing to do LoA duplication checks​ | TBC | Closed | WG18
37 | WG10 | AC/AQ | To confirm Gate 1 contracts are formal binding contracts and clarify terminology accordingly | Yes in relation to content​ | TBC | Closed | WG18
38 | WG11 | MO | Updated Action: To expand on licence change conditions/obligations, including any suggested changes to the Licensed offer timescales | ESO decision to not draft licence text suggestions | TBC | Closed | WG25
39 | WG11 | MO | To share ESO suggested Licensed offer timescales changes from 3 months with the Workgroup | Combined with action 38 | TBC | Closed | WG18
40 | WG11 | RF | To share licence changes programme timescales with Workgroup | No longer part of CMP434 | TBC | Closed | WG25
41 | WG12 | PM | To share analysis/feedback which informs the Gate 2 period offer acceptance to submission of application for Planning Consent | SME view – DNV analysis did not add anything further, no public data available. Credible data sources were timings provided by WG and consultation respondents | TBC | Closed | WG23
42 | WG12 | JH | To provide an update of the action log at Workgroup 13 |  | WG13 | Closed | WG13
43 | WG16 | DH/GL | Investigate whether changes are required to STCP 18-7 based on the CMP434 solution | Changes not considered to be required to STCP 18-7 | ASAP | Closed | WG23
44 | WG16 | DH/GL | Consider whether an update is required to the STC Panel on timings of STCP modifications and approval route | An update will be provided to the STC Panel Representatives via email circulation. | ASAP | Closed | WG18
45 | WG16 | RW | Provide narrative within Workgroup Consultation on Connection Point and Capacity Reservation | Within Workgroup Consultation for review | 45492 | Closed | WG16
46 | WG16 | AL | Provide narrative within Workgroup Consultation relating to CATOs |  | 45492 | Closed | WG16
47 | WG16 | MO | Amend ‘Why Change’ and ‘Interactions’ sections of Workgroup Consultation document |  | 45492 | Closed | WG16
48 | WG16 | LT | Amend Proposer’s solution section within Executive Summary | Within Workgroup Consultation for review | 45492 | Closed | WG16
49 | WG17 | MO | Updated action: SMEs to share a short summary of the methodologies and the underlying principles of this modification. This should include a plan for development of methodologies, including timescales and engagement with stakeholders. | Ongoing discussion with Ofgem | TBC | Open
50 | WG18 | AQ | Provide the ESO view on the legal position associated with Element 1 of the Proposal in the context of the Ofgem decision-making process on code change | Draft Legal Text provided | TBC | Closed | WG23
51 | WG18 | HM | Provide further explanation/evidence on the perceived flexibility / timing differences between changing the content of a methodology and changing the content of a code. | Methodologies content not included as part of the Proposal except the extent of inclusion in the draft legal text | TBC | Closed | WG25
52 | WG18 | MO | Review consultation responses from directly connected Demand Users, and provide an update on intentions for Element 3 | Reviewed - whilst concerns noted plan to keep Directly Connected Demand in scope. (Can be closed.) | TBC | Closed | Red line text sent
53 | WG18 | DD/SG | Clarify whether developer requested changes within a Significant Modification Application could potentially be so significant that they result in an application having to be restarted or having the contract terminated, etc | Some requests could be so significant that, if accepted, the project would not retain their contracted ‘queue’ position | TBC | Closed | WG23
54 | WG18 | RPa/AP | Clarify whether the ESO will still be providing indicative dates to DNOs Pre-Gate 2 | As part of the update ESO solution, DFTC has been descoped from CMP434. As Gate 1 is only optional, under this modification, we aren't proposing a solution to provide indicative dates pre-Gate 2 under CMP434. ESO view is that we would like to have indicative dates but we will need to work with DNO, iDNOs and TO's to decide a way forward. As mentioned before, we are currently exploring forecast information for small/medium REPs forming part of Week 24 data under Grid Code. We need to understand where this lands and likely implementation date of any Grid Code change and are suggesting that we have a decision point at the end of Q1 2025, to understand if we need to progress work in this area prior to the implementation of a Grid Code change. Assumption is that if this is required, it will be outside CMP434. | TBC | Closed | Red line text sent
55 | WG18 | DD | Re-review consultation feedback specific to the ESO position on any Non-GB Projects (as consulted on within the WG Consultation) and either confirm that the position still remains unchanged or confirm new position to the Workgroup. | SME – amended position is within the redline text | TBC | Closed | WG23
56 | WG18 | MO | Confirmation of when the financial instruments modification will be raised. | ESO are currently performing an options assessment, and outcome of that (i.e. the specific option we proceed with) will dictate the timelines that we will need to follow. | TBC | Open
57 | WG18 | AQ | Consider Innova response and confirm whether ESO feels that Element 9 is consistent with Electricity Regulations in terms of discrimination. | Draft Legal Text provided | TBC | Closed | WG23
58 | WG18 | PM | Clarify whether anything in Proposal could allow the Gate 2 criteria to be amended and applied retrospectively i.e. with a Gate 2 project then no longer being a Gate 2 project, even where it is complying with its ongoing compliance obligations. | Legal Text Circulated does not allow the Gate 2 criteria to be amended and applied retrospectively | TBC | Closed | WG25
59 | WG19 | PM | Element 11 – Produce examples to provide clarification to the Workgroup (slide 25) on how using installed capacity could work in practice | To be added to the QM guidance (as relates to ongoing land compliance requirement) – follow up required to decide if ‘installed capacity’ is the correct term | TBC | Open
60 | WG19 | PM | Element 11 – Consider Workgroup Member request to provide analysis to show which projects could benefit from the Proposals (slide 26) to have a milestone adjustment ability for ESO e.g. where a developer asks for an earlier date and gets a later date, or asks for and gets a later date (but this is due to a normal programme timescales e.g. mega projects) to avoid unintended outcomes. | Ongoing – PM to reach out to EB | TBC | Open
61 | WG19 | RPa/MO | Element 17 - To confirm BEGA application information i.e. in relation to what happens where a relevant small or medium EG project gets a different GSP to what they expected (as a result of the Gate 2 process and via the DNO) (Garths question) | GG content with RPa email response? | TBC | Closed | WG23
62 | WG19 | RPa | Element 17 – To provide a pictorial representation of BEGA/BELLA process as proposed | Update provided in WG22 | TBC | Closed | WG23
63 | WG19 | Rpa | Element 17 – Create an additional swimlane/s for chevron diagram for BEGA/BELA | Update provided in WG22 | TBC | Closed | WG23
64 | WG20 | Rpa | Element 17 - To produce prescribed timelines/timescales (Garths request as per slide 13) for both small and large | Update provided in WG22 | TBC | Closed | WG23
65 | WG19 | PM | To update forward looking milestone examples (provided in Annex 1) | Completed | TBC | Closed | Post WG 19 need to be sent to WG
66 | WG19 | MO | More information on timeline on CP30 plans/impacts to be shared once the are available (to compare to the code change programme, including voting timetable). | Connection reform event slides shared with members | TBC | Closed | WG25
67 | WG20 | PA/JI | Offline discussion regarding Alternative Request 3 proposal | Considered but declined – request info from members land/planning experts or raise Alternative to suggest different time sales | TBC | Closed | WG23
68 | WG20 | MO | Consider workshops to allow discussion time for forward looking milestones and expectations for planning | Considered but declined – request info from members land/planning experts or raise Alternative to suggest different time sales | TBC | Closed | WG23
69 | WG20 | CG | To reach out to ESO to consider Alternative Request 7 raised and what further information would be required from the Proposer to respond to questions raised in WG20 with regards to novel technologies. | Reached out to ESO | TBC | Closed | WG21
70 | WG20 | CG | A request from a Workgroup member to share CPAG minutes from 22 July 2024 | Sent in WG21 Papers | TBC | Closed | WG21
71​ | WG21​ | AP​ | ESO to confirm whether in practice new GSPs (related to DNOs or Transmission connected iDNOs) will ever not have relevant EG associated with them in future​ | Update from AP WG22 | TBC | Closed | WG23
72​ | WG21​ | TE/CH​ | Amend Alternative Request Proposal 22 and feedback to Workgroup​ |  | TBC | Closed | WG25
73​ | WG21​ | LH​ | Provide analysis/evidence of the impact of Alternative Request 23 (NGED) and consider alternative ways of solving the issue e.g. more windows (PY comment)​ |  | TBC | Closed | WG25
74​ | WG21​ | LH/HS​ | Proposers of Alternative Requests 8 and 23 to liaise and consult on whether proposals may be merged​ | Agreed to retain two separate requests but amended to be more aligned | TBC | Closed | WG23
75​ | WG21​ | AQ/LH​ | RE – Alternative Request 23 - To consult legal teams as to whether a 10- or 20-day obligation is most appropriate within the CUCS or in the licence​ |  | TBC | Closed | WG25
76​ | WG21​ | MO​ | Provide Workgroup feedback to the ESO Policy and Change team on the absence of wider industry consultation on the Technology Change Guidance Paper​ | Feedback has been provided to the team who are considering it | TBC | Closed | WG23