## Grid Code Prioritisation
Grid Code - Prioritisation Stack
Mod Number | Previous Priority No: | Priority No | Panel Comments on Prioritisation | Proposer Name | Proposer Organisation | Proposal raised | Complexity | Importance | Urgency | Estimated number of meetings remaining | Title
GC0159 | (1 before 2nd CAC) | (1 before 2nd CAC) | [8 empty] | Introducing Competitively Appointed Transmission Owners
GC0139 | 1 | 1 | This proposal has been raised following instruction from the Authority following the 9 August investigation and therefore the Panel concluded that this work should be completed as soon as possible. | Mark Horley | National Grid ESO | 2020-03-11 | High. Updates to compliance testing and modelling process requirements further to Ofgem/BEIS reports on 9th August event. Particularly impactful for complex arrangements. Requires changes to OC, PC, CC, ESS, CP, ECP, DRC, and possibly sections of STC. Includes new five-year compliance repeat plan requirement. Likely to also result in STC changes, and an update to the DRC. Likely to be 6+ workgroups remaining. | High Direct result of Ofgem/BEIS Actions from 9th August. Failure to deliver in a timely fashion would leave ESO exposed to further scrutiny and appropriate consequences. Compliance testing and modelling standards would not be deemed robust enough without this review by the industry. | High. Given the complexity and importance, and the implications of the 9th August reports, timely progression of these mods is vital. With 4-6 workgroups estimated as remaining, we must ensure momentum is maintained within the ESO and wider industry. | An estimate of 6> meetings remaining. To be run concurrently with GC0138 | Enhanced Planning Data Exchange to Facilitate Whole System Planning
GC0117 | (2 before CAC) | (2 before CAC) | New modification presented at May 2020 Panel | Nicola Barberis Negra | Ørsted | 2020-05-12 | We believe this modification is not complex and small amount of works should be required to address the questions raised by NGESO and progress the NG modification further | The proposed change of the Grid code would allow developers to reduce the costs of their frequency controller design and this would ultimately provide a benefit (reduced costs) for the end consumer as the design would be cheaper | The sooner the change is accepted, the sooner developers can implement the change to their design and benefit for the larger flexibility in the Grid Code. Until the Grid Code change is not approved, developers will still be forced to opt for more expensive design solution, which in our view do not provide any additional benefit to the overall operation of the network | The working group hasn’t started yet, but we would expect a reduced number of meetings (1 or 2?) to be required, given the relatively simple issues raised by NGESO on the proposed changes to the Grid Code. | Improving transparency and consistency of access arrangements across GB by the creation of a pan-GB commonality of PGM requirements
GC0155 | 2 | 2 | [8 empty] | Clarification of Fault Ride Through Technical Requirements
GC0166 | 3 | 3 | [8 empty] | Introducing new Balancing Programme Parameters for Limited Duration Assets
GC0168 | 4 | 4 | [8 empty] | Submission of Electro Magnetic Transient (EMT) Models
GC0174 | 5 | 5 | [8 empty] | Removal of obligation to provide EU Transparency Availability Data as specified in OC2.4.7
GC0169 | 6 | 6 | [8 empty] | Material changes identified from Grid Code Modification GC0136 and Consistency of requirements between the Connection Conditions and European Connection Conditions
GC0173 | 6 | 6 | [8 empty] | Consistency of Technical and Compliance Requirements between GB and European Users
GC0164 | 7 | 7 | [8 empty] | Simplification of Operating Code No.2
GC0103 | 8 | 8 | This change was not deemed to be as high a priority when compared to those above it currently. | Garth Graham | SSE Generation Ltd | 2017-07-01 | This is a simple quick win change, to harmonise on a set of applicable Electrical Standards in GB. The Workgroup has met on a number of occasions and has come to the view that there are simply four options: namely to use the Electrical Standards from one of the three existing onshore TO (NGET, SHE-T, SPT) or adopt a new version not based on one of the existing three. | Generators are connecting to the GB system and procuring equipment based on three different standards which is inefficient, non-harmonised and leads to higher consumer costs. | This Modification was raised on 1st July 2017 – we are now a few days shy of its third birthday. To complete the Workgroup consultation should require two more Workgroup meetings, followed by a further two Workgroup meetings to conclude the work on this Modification. |  | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes
GC0140 | 9 | 9 | A key change that should be progressed in a joint workgroup with CUSC. Time passed and should proceed as soon as possible to enable more innovation. | Phil Smith | National Grid ESO | 2020-03-11 | Medium. Not expected to be hugely resource intensive, as it is implementing something that’s already been done for BSC and DCUSA and has a good amount of guidance from Ofgem. It does need a new process to be developed though so there's some complexity. Medium impact for a few parties, including ESO's Code Admin team and Panel, but not expected to have big impacts across the industry. Joint workgroup with Grid Code may add complexity and to the number of workgroups needed. | Medium. It's important that this is done as it reflects CACOP Principle 14 ('to develop cross code processes, and identify and facilitate changes to their codes to support Ofgem’s innovation activities'). However, to date there doesn't appear to be significant push from industry for this to be progressed for CUSC (and Grid Code - it's a joint workgroup). | Low. We committed to raising this by the end of the last financial year which we've done. There's no set timeline that this needs to be delivered to, but we support it, it's also in the CACOP and encouraged by Ofgem, and will support customers who want to test new approaches so should not be delayed unnecessarily. | An estimate of 5 meetings remaining. | Grid Code Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions