## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | ND | Share the SECULF model with the work group to enable replication of the calculation. |  | WG2 | Ongoing
2 | WG1 | Proposer & PJ | Submit written arguments detailing the implications of the security factor on network reinforcement and incremental cost, including perspectives on whether it implies an ever-growing N minus number. | This was covered in presentations given by the Proposer and the Workgroup member in Workgroup 2 | WG2 | Closed | WG2
3 | WG1 | ND | NESO to speak to teams internally to request industry access to VBA code within the Transport and Tariff Model |  | WG2 | Ongoing
4 | WG1 | Proposer | Share the SSE Consultant’s report |  | WG2 | Ongoing
5 | WG1 | Chair | Liaise with the Chair of CMP444 to ensure modifications are running in alignment. | Spoke to the chair and the modifications are aligned with HH also confirming this | WG2 | Closed | WG2
6 | WG2 | Chair | Loop in with the Chair of CMP444 regarding an Ofgem call | Spoke to CG but I wasn't needed for the call as they are two separate modifications with different timelines The FMRs will be submitted to Ofgem with a few weeks difference and will align for the authority decision We will record the interactions in our report | WG3 | Closed | WG3
7 | WG2 | Chair | Reach out to suggested members to join the Workgroup | Email sent on 07/02 to NGET | WG3 | Closed | WG3
8 | WG2 | Chair | Send invites with the amended time for the next Workgroup | Actioned | WG3 | Closed | WG3
9 | WG2 | ND | Keep Workgroup Updated on whether someone from NESO can attend the next Workgroup |  | WG3
10
11
12
13
14
15
16
17