## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | Workgroup Members | Review legal text and share comments. |  | WG2 | Closed | WG3
2 | WG1 | AJ | Organise meeting with MK to discuss SI units in the Grid Code Glossary & Definitions |  | WG2 | Closed | WG2
3 | WG1 | AJ | Circulate legal text to NESO SMEs for feedback. |  | WG2 | Closed | WG2
4 | WG1 | AJ | Confirm with Legal if GC15.5 can be deleted. |  | WG2 | Closed | WG2
5 | WG1 | AJ | Confirm any further concerns on OC.9.6.4 with SB |  | WG2 | Closed | WG2
6 | WG1 | AC | Review and confirm GG11.2 draft |  | WG2 | Closed | WG2
7 | WG1 | Workgroup Members | Confirm if changes are needed to Annex GR.B of the Governance Rules regarding Electricity Balancing Guideline. | AJ confirmed no change will be needed | WG2 | Closed | WG3
8 | WG1 | MK | Review latest G99 draft to ensure concerns from C.9.3.3 are addressed. |  | WG2 | Closed | WG2
9 | WG3 | AJ | GC5.1 clarify if this could be simplified to detail who the obligation applies to (eg Network Operators, Non-Embedded Customers and Interconnectors) rather than currently detailing who it doesn’t (eg Generators an Suppliers). | Discussed with NESO Legal. General Conditions have been updated and shared with WG. | WG3 | Closed | WG4
10 | WG3 | AJ | GC5.2 investigate any interaction with DCUSA, CUSC and BSC with regards to any conflicts associated with notifications. | Discussed with NESO Legal. General Conditions have been updated and shared with WG. | WG3 | Closed | WG4
11 | WG4 | Chair | Chair to circulate updated Legal Text and Draft Workgroup Consultation Report. Workgroup Member comments required by 21 February 2025. |  | WG5 | Closed | WG5
12 | WG5 | AJ | Proposer to amend Annex 4 to highlight where each item cross-references the Proposer’s Solution summary, items (a) – (f). |  | WG6 | Closed | WG6
13 | WG5 | AJ | Proposer to discuss with Elexon potential interaction of GC0169 with Balancing and Settlement Code (BSC) Section H 9.2.1.(a). Proposer to include this in Workgroup Report and to include a related question in the Workgroup Consultation. | Consultation question included in Workgroup Consultation | WG6 | Closed | WG6
14
15
16
17