## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | Workgroup members | Review legal text and share comments. |  | WG3 | Closed | WG3
2 | WG1 | AJ | Check format of PC.A.3.4.2 (incorrect reference PC.A.3.1.4?) |  | WG2 | Closed | WG2
3 | WG1 | AJ | Confirm if the proposed text relating to frequency sensitive relays does not undermine RfG |  | WG2 | Closed | WG2
4 | WG1 | AJ | Review: ECC.8 – Mandatory Ancillary Services |  | WG2 | Closed | WG2
5 | WG1 | AJ | Review: ECP’s (ECP.A.6.4, ECP.A.6.2, ECP.A.6.5.1 and ECC.6.3.2) |  | WG2 | Closed | WG2
6 | WG2 | AJ/TK | Review and circulate Substantial Modification Table |  | WG3 | Closed | WG3
7 | WG3 | DS/IG/NBN/AJ/TK | DS/IG/NBN to collaborate and propose a solution for the ECP.A.6.2.1 issue discussed at WG3. Then AJ/TK will review and discuss the proposed change | The Proposer and Workgroup Members will continue to develop this solution, noting the potential interaction with G99. | WG4 | Closed | WG5
8 | WG4 | Chair | Chair to update the Terms of Reference to include a statement confirming no new obligations or costs will be incurred (item a) and that all necessary industry experts have been involved in the process (item c). Update to be shared with Workgroup. |  | WG5 | Closed | WG5
9 | WG4 | AJ | Proposer to update Legal Text, clear with NESO Engineering Compliance, and share updated version with Workgroup. | Closed during WG5. | WG5 | Closed | WG5
10 | WG4 | Chair | Chair to circulate updated Legal Text and Draft Workgroup Consultation Report. Workgroup Member comments required by 21 February 2025. |  | WG5 | Closed | WG5
11 | WG5 | AJ | Proposer to prepare an Annex table for GC0173 summarising the proposed changes, cross-referenced to the Proposer’s Solution summary, items (a) – (f). |  | WG6 | Open
12 | WG5 | AJ | Proposer to meet with NBN and TK to agree revised text for ECP A.5.8.8 and share revision with Workgroup for comment. |  | WG6 | Open
13
14
15
16
17